## PLAN 2011-2012
Ministry of Health & Social Welfare
Procurement Plan
July 1, 2011 - June 30, 2012
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | Remark
LOT # |  | item | CODE | Contract Package | QTY | EST COST | PROC METHOD | TECH SPEC | Preparation of Bidding Doc. | PC Approval | Advert/release bid doc | Bid subm opening | Bid Evaluation Report | PC Approval | Contract Award/Signing | Advance Payment | Delivery | Final Payment
| PLANNED | 1 | IFB/MH&SW/NCB/001/2011/2012 | Diesel Fuel & Gasoline | 427,620 GAL | 2245000 | NCB | 2011-06-01 | 2011-06-13 | 2011-06-20 | 2011-07-04 | 2011-07-07 | 2011-07-11 | 2011-07-25 | N/A | 2011-08-01 | 2011-09-30 | 2011-10-30
UPDATE
ACTUAL
| PLANNED | 2 | IFB/MH&SW/ICB/001/2011/2012 | Pediatric Hospital Construction | 1 | 5000000 | ICB | 2011-10-01 | 2011-10-10 | 2011-10-17 | 2011-10-24 | 2011-12-05 | 2011-12-12 | 2011-12-19 | 2012-01-03 | 2012-01-17 | 2012-03-17 | 2012-05-16
UPDATE
ACTUAL
ELECTRICAL POWER
LOT #1 | PLANNED | 3 | IFB/MH&SW/SS/001/2011/2012 | Electrical Power a year (LEC Power Supply) | 1 | 500000 | Sole Source | 2011-06-01 | 2011-06-08 | N/A | 2011-06-22 | 2011-06-27 | 2011-07-02 | 2011-07-16 | 2011-08-06 | 2011-08-27 | 2011-09-26 | 2011-10-10
UPDATE
ACTUAL
LOT #2 | PLANNED | 4 | IFB/MH&SW/SS/002/2011/2012 | New MH&SW Electrical High Voltage Connection | 1 | 65000 | Sole Source | 2011-06-15 | 2011-06-22 | 2011-06-30 | N/A | 2011-07-11 | 2011-07-14 | 2011-07-18 | 2011-07-28 | 2011-08-18 | 2011-08-23 | 2011-09-22
UPDATE
ACTUAL
| PLANNED | 5 | IFB/MH&SW/SS/003/2011/2012 | Water Supply (LWSC) | 1 | 20000 | Sole Source | N/A | 2011-07-01 | 2011-07-08 | N/A | 2011-07-22 | 2011-07-27 | 2011-08-01 | 2011-08-15 | 2011-09-05 | 2011-09-26 | 2011-10-26
UPDATE
ACTUAL
| PLANNED | 6 | IFB/MH&SW/ICB/002/2011 | National Blood Bank & Reference Lab. Construction | 1 | 1500000 | ICB | 2011-09-30 | 2011-10-21 | 2011-10-28 | 2011-11-04 | 2011-12-16 | 2012-01-06 | 2012-01-13 | 2012-01-27 | 2012-02-17 | 2012-03-09 | 2012-05-08
UPDATE
ACTUAL
| PLANNED | 7 | IFB/MH&SW/ICB/003/2011/2012 | Solar Panels for County Clinics | 45 | 1123555 | ICB | 2011-07-01 | 2011-07-22 | 2011-08-12 | 2011-08-19 | 2011-09-30 | 2011-10-21 | 2011-10-28 | 2011-11-18 | 2011-12-02 | 2012-03-31 | 2012-05-30
UPDATE
ACTUAL
| PLANNED | 8 | IFB/MH&SW/NCB/002/2011 | Staff Housing | 5 | 500000 | NCB | 2011-08-01 | 2011-08-22 | 2011-08-29 | 2011-09-05 | 2011-10-05 | 2011-10-26 | 2011-11-02 | 2011-11-23 | 2011-12-07 | 2012-04-05 | 2012-06-04
UPDATE
ACTUAL
| PLANNED | 9 | IFB/MH&SW/SS/004/2011/2012 | Procurement Management System Software installation, training and Maintenance | 1 | 197779 | Sole Source | 2011-07-01 | 2011-07-15 | 2011-07-29 | N/A | 2011-08-08 | 2011-08-15 | 2011-08-20 | 2011-09-05 | 2011-09-15 | 2011-11-14 | 2011-12-14
UPDATE
ACTUAL
| PLANNED | 10 | IFB/MH&SW/ICB/004/2011 | Procurement of transport equipment | Assorted | 675000 | ICB | 2011-09-01 | 2011-09-15 | 2011-09-22 | 2011-09-29 | 2011-11-10 | 2011-11-24 | 2011-12-01 | 2011-12-15 | 2011-12-29 | 2012-02-27 | 2012-04-27
UPDATE
ACTUAL
| PLANNED | 11 | IFB/MH&SW/SS/005/2011/2012 | Communication, Phone cards | 13877 | 69387 | Sole Source | 2011-06-16 | 2011-06-23 | 2011-06-28 | N/A | 2011-07-08 | 2011-07-11 | 2011-07-14 | 2011-07-25 | 2011-08-15 | 2011-08-22 | 2012-05-18
UPDATE
ACTUAL
| PLANNED | 12 | IFB/MH&SW/NCB/003/2011/2012 | Stationery Supplies | Assorted | 108388 | NCB | 2011-06-01 | 2011-06-15 | 2011-06-22 | 2011-06-29 | 2011-07-13 | 2011-07-18 | 2011-07-21 | 2011-08-04 | 2011-08-18 | 2012-04-24 | 2012-05-24
UPDATE
ACTUAL
IT EQUIPMENTS, SUPPLIES & ACCESSORIES
LOT#1 | PLANNED | 13 | IFB/MH&SW/NCB/004/2011/2012 | IT, Equipment | Assorted | 64112 | NCB | 2011-06-01 | 2011-06-15 | 2011-06-22 | 2011-06-29 | 2011-07-13 | 2011-07-18 | 2011-07-21 | 2011-08-04 | 2011-08-18 | 2012-04-24 | 2012-05-24
UPDATE
ACTUAL
LOT#2 | PLANNED | 14 | IFB/MH&SW/NCB/005/2011/2012 | IT Supplies & Accessories | Assorted | 21631 | NCB | 2011-06-01 | 2011-06-15 | 2011-06-22 | 2011-06-29 | 2011-07-13 | 2011-07-18 | 2011-07-21 | 2011-08-04 | 2011-08-18 | 2012-04-24 | 2012-05-24
UPDATE
ACTUAL
| PLANNED | 15 | IFB/MH&SW/SS/006/2011/2012 | Modems subscription | Assorted | 43200 | Sole Source | 2011-06-01 | 2011-06-15 | 2011-06-22 | 2011-06-29 | 2011-07-13 | 2011-07-18 | 2011-07-21 | 2011-08-04 | 2011-08-18 | 2012-04-24 | 2012-05-24
UPDATE
ACTUAL
| PLANNED | 16 | IFB/MH&SW/SS/007/2011/2012 | IT Service CONTRACT | 1 | 295993 | Sole Source | 2011-06-01 | 2011-06-15 | 2011-06-22 | 2011-06-29 | 2011-07-13 | 2011-07-18 | 2011-07-21 | 2011-08-04 | 2011-08-18 | 2012-04-24 | 2012-05-24
UPDATE
ACTUAL
Vehicles Maintenance & Repair
LOT #1A | PLANNED | 17 | IFB/MH&SW/SS/008/2011/2012 | Vehicles Repairs & Maintenance-(All Nissan & Hyundai Vehicles) | 26 | 83000 | Sole source | 2011-07-01 | 2011-07-11 | 2011-07-18 | N/A | 2011-07-28 | 2011-07-31 | 2011-08-03 | 2011-08-13 | 2011-09-02 | 2011-09-07 | 2012-04-30
UPDATE
ACTUAL
LOT #1B | PLANNED | 18 | IFB/MH&SW/SS/009/2011/2012 | Vehicles Repairs & Maintenance-(All FORD Vehicles) | 28 | 25750 | Sole source | 2011-07-01 | 2011-07-11 | 2011-07-18 | N/A | 2011-07-28 | 2011-07-31 | 2011-08-03 | 2011-08-13 | 2011-09-02 | 2011-09-07 | 2012-04-30
UPDATE
ACTUAL
LOT #2 | PLANNED | 19 | IFB/MH&SW/NCB/005/2011/2012 | Vehicles Repairs & Maintenance-Other vehicles | 78 | 72930 | NCB | 2011-06-15 | 2011-06-29 | 2011-07-06 | 2011-07-13 | 2011-07-27 | 2011-08-01 | 2011-08-04 | 2011-08-18 | 2011-09-01 | 2012-05-08 | 2012-06-07
UPDATE
ACTUAL
| PLANNED | 20 | IFB/MH&SW/SS/010/2011/2012 | Generator Repairs & Maintenance | 4 gensets | 24000 | Sole source | 2011-07-01 | 2011-07-11 | 2011-07-18 | N/A | 2011-07-28 | 2011-07-31 | 2011-08-03 | 2011-08-13 | 2011-09-02 | 2011-09-07 | 2012-04-30
UPDATE
ACTUAL
| PLANNED | 21 | IFB/MH&SW/RFQ/010/2011/2012 | Maintenance-Civil works | Assorted | 28330 | Request for Quotation | 2011-07-01 | 2011-07-11 | 2011-07-18 | N/A | 2011-07-28 | 2011-07-31 | 2011-08-03 | 2011-08-13 | 2011-09-02 | 2011-09-07 | 2012-04-30
UPDATE
ACTUAL
| PLANNED | 22 | IFB/MH&SW/NCB/005/2011 | Furnishings | Assorted | 292534 | NCB | 2011-07-01 | 2011-07-22 | 2011-07-29 | 2011-08-05 | 2011-09-04 | 2011-09-25 | 2011-10-16 | 2011-11-06 | 2011-11-20 | 2012-04-30 | 2012-05-30
UPDATE
ACTUAL
Printing , binding & Publication Services
Lot #1 | PLANNED | 23 | IFB/MH&SW/NCB/006/2011/2012 | Publication | Assorted | 55050 | NCB | 2011-07-01 | 2011-07-22 | 2011-07-29 | 2011-08-05 | 2011-09-04 | 2011-09-25 | 2011-10-16 | 2011-11-06 | 2011-11-20 | 2012-04-30 | 2012-05-30
UPDATE
ACTUAL
Lot #2 | PLANNED | 24 | IFB/MH&SW/NCB/007/2011/2012 | Printing & binding | Assorted | 185295 | NCB | 2011-07-01 | 2011-07-22 | 2011-07-29 | 2011-08-05 | 2011-09-04 | 2011-09-25 | 2011-10-16 | 2011-11-06 | 2011-11-20 | 2012-04-30 | 2012-05-30
UPDATE
ACTUAL
| PLANNED | 25 | IFB/MH&SW/CC/001/2011/2012 | Rental; | Assorted | 35000 | NCB* | 2011-07-01 | 2011-07-22 | 2011-07-29 | 2011-08-05 | 2011-09-04 | 2011-09-25 | 2011-10-16 | 2011-11-06 | 2011-11-20 | 2012-04-30 | 2012-05-30
UPDATE
ACTUAL
Drugs, Medical Supplies and Equipment
LOT#1 | PLANNED | 26 | IFB/MH&SW/ICB/005/2011/2012 | Essential Drugs & medical consumables | Assorted | 1200000 | ICB | 2011-07-01 | 2011-07-15 | 2011-07-22 | 2011-07-29 | 2011-09-09 | 2011-09-23 | 2011-09-30 | 2011-10-14 | 2011-10-28 | 2011-12-27 | 2012-02-27
UPDATE
ACTUAL
LOT#2 | PLANNED | 27 | IFB/MH&SW/DC/005/2011/2012 | HIV/AIDS Drugs | Assorted | 14531810 | Direct Contracting ( VPP) | 2011-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-04-30 | 2012-06-29
UPDATE
ACTUAL
LOT#3 | PLANNED | 28 | IFB/MH&SW/RB/002/2011/2012 | other medical supplies | Assorted | 15800 | Restrictive bidding | 2011-06-01 | 2011-06-13 | 2011-06-20 | 2011-07-04 | 2011-07-07 | 2011-07-11 | 2011-07-25 | N/A | 2011-08-01 | 2011-09-30 | 2011-11-29
UPDATE
ACTUAL
| PLANNED | 29 | IFB/MH&SW/NCB/008/2011/2012 | Food Stuff | Assorted | 392985 | NCB | 2011-07-01 | 2011-07-22 | 2011-07-29 | 2011-08-05 | 2011-09-04 | 2011-09-25 | 2011-10-16 | 2011-11-06 | 2011-11-20 | 2012-04-30 | 2012-05-30
UPDATE
ACTUAL
| PLANNED | 30 | IFB/MH&SW/NCB/009/2011/2012 | Foreign Means of Travel | Assorted | 478000 | NCB | N/A | 2011-07-01 | 2011-07-11 | 2011-07-16 | 2011-07-30 | 2011-08-02 | 2011-08-05 | 2011-08-19 | N/A | 2011-08-24 | 2012-05-30
UPDATE
ACTUAL
| PLANNED | 31 | IFB/MH&SW/NCB/009/2011/2012 | Domestic Means of Travel | Assorted | 105381 | NCB | N/A | 2011-07-01 | 2011-07-11 | 2011-07-16 | 2011-07-30 | 2011-08-02 | 2011-08-05 | 2011-08-19 | N/A | 2011-08-24 | 2012-05-30
UPDATE
ACTUAL
| PLANNED | 32 | IFB/MH&SW/NCB/010/2011/2012 | Insurance, Vehicle | 132 | 101560 | NCB | 2011-07-01 | 2011-07-22 | 2011-07-29 | 2011-08-05 | 2011-09-04 | 2011-09-25 | 2011-10-16 | 2011-11-06 | 2011-11-20 | 2012-04-30 | 2012-05-30
UPDATE
ACTUAL
| PLANNED | 33 | IFB/MH&SW/NCB/011/2011/2012 | Catering Services | Assorted | 199980 | NCB | N/A | 2011-07-01 | 2011-07-11 | 2011-07-16 | 2011-08-01 | 2011-08-04 | 2011-08-07 | 2011-08-21 | N/A | 2011-08-26 | 2012-06-01
UPDATE
ACTUAL
| PLANNED | 34 | IFB/MH&SW/QCBS/001/2011/2012 | Consultant Services | Assorted | 227692 | QCBS | 2011-07-01 | 2011-07-22 | 2011-07-29 | 2011-08-05 | 2011-09-16 | 2011-10-07 | 2011-10-14 | 2011-11-04 | 2011-11-18 | 2012-03-17 | 2012-05-16
UPDATE
ACTUAL
| PLANNED | 35 | IFB/MH&SW/RFQ/003/2011/2012 | Moving Cost | Assorted | 9780 | RFQ | 2011-07-01 | 2011-07-22 | 2011-07-29 | 2011-08-05 | 2011-09-04 | 2011-09-25 | 2011-10-16 | 2011-11-06 | 2011-11-20 | 2012-04-30 | 2012-05-30
UPDATE
ACTUAL
| PLANNED | 36 | IFB/MH&SW/NCB/013/2011/2012 | Vehicle Rentals | Assorted | 53520 | NCB | 2011-07-01 | 2011-07-22 | 2011-07-29 | 2011-08-05 | 2011-09-04 | 2011-09-25 | 2011-10-16 | 2011-11-06 | 2011-11-20 | 2012-04-30 | 2012-05-30
UPDATE
ACTUAL
| PLANNED | 37 | IFB/MH&SW/NCB/015/2011/2012 | Tools Small/Equipment and Household | Assorted | 62871 | NCB | 2011-07-01 | 2011-07-22 | 2011-07-29 | 2011-08-05 | 2011-09-04 | 2011-09-25 | 2011-10-16 | 2011-11-06 | 2011-11-20 | 2012-04-30 | 2012-05-30
UPDATE
ACTUAL
| PLANNED | 38 | IFB/MH&SW/RFQ/004/2011/2012 | Entertainment & Gift | Assorted | 6000 | RFQ | 2011-08-01 | 2011-08-08 | N/A | 2011-08-22 | 2011-08-27 | 2011-09-01 | 2011-09-15 | 2011-10-06 | 2011-10-27 | 2011-11-26 | 2012-05-16
UPDATE
ACTUAL
30616313
|  |  | Prepared By: _________________________________ |  |  |  |  | 2011-06-29: Approved By: ________________________________
|  |  |  | Procurement Director |  |  |  | 2011-07-13: Head Of Entity
Signed By: _________________________________
Deputy Minister/Administration
* Line item #1: Diesel Fuel & Gasoline in the Plan refers to Projected usage 427,620 gallons annually @ US$5.25 = US$2,245,000 based on CY 2010 Usage 307,392 gallons @ US$ 4.00 = US$1,229,569; CY Y 2011 JAN-APR 126,122 gallons @ US$4.50 = US$567,550; FY 2011-2012 projected cost fuel @ US$5.25 X 380,000 = US$1,995,000 PLUS Global Fund Round 10 Malaria & TB 47,620 gallons @ US$5.25 = US$250,000 totals US$ 2,245,000. Funding Source: GOL Funds, Global Fund HIVgrant, Global Fund malaria & TB, GAVI, UNICEF, WHO, UNHCR, UNFPA and other donors
* Line item #2 Pediatric Hospital construction refers to the Old Ministry Building to be used for the Pediatric Hospital, funding is provided for in the GOL Special Project Budget
* Line item #3: electric power Supply refers to Sole Sourcing LEC to provide Electrical Supply for new MH&SW Building based on MSAADA, LEC & MOHSW powerhouse supervisor joint report. This is electric utility bills
* Line item #4: New MH&SW High Electric Voltage connection refers to Sole Sourcing LEC for 22000 Volts Transmission line and 1000kva for electrical power connection to the New Ministry Building based on LEC, MSAADA & MOHSW power house supervisor joint report
* Line item#5: Water Supply refers to Sole Sourcing Liberian Water & Sewer Corporation for Water Supply to the new MH&SW Building
* Line item#7: Solar Panel for county clinics refers to installation of solar panels at health facilities in the counties with Matching grant from EU of $623,555.00
* Line item#8 staff housing refers to health workers housing, this fund is provided for in Special Project budget 2011/2012
*Line item#9: procurement of management system software installation, training and maintenance refers to continuation of a service hired by MOHSW through an ICB; now wants to include procurement into the package to link MOHSW Finance & MOHSW Procurement
*Line item #10: Procurement of transport Equipment refers to purchase of new motor vehicles & Motorbikes for health facilities with Funding from GOL, GFATM, USAID other private donors
* Line item #11 refers to Communication/Phone cards An estimated $63,078 cost for 12,616 unit of phone cards @ US$ 5 based on CY 2011 usage plus an estimated 10% increase usage for FY 2011-12 Projection. The Young Shall Business Center is the Sole Source Agent
* Line item # 13 LOT 1 refers to IT equipment which include, Laptop, Desktop, printer etc.
* Line item # 14 LOT 2, IT supplies & Accessories refer to hardrives, and other related IT equipment
* Line item #15 refers to GPRS Edges used by different programs based on the different GSM Companies coverage area (sole source for Lonestar GPRS & Subscription, Sole source for Comium GRPS & subscription, sole source for Cellcom GPRS & subscription, sole source for LIBTELCO GRPS & subscription, Sole source for LIBERCELL GPRS & Subscription
* Line item#16 IT Contract refers to sole sourcing subscription for VSAT connectivity equipment purchased from Power Tech. Inc
* Line item #17 LOT1A, refers to Sole Sourcing Africa Motors for Preventive Maintenance, Maintenance and repairs, and original equipment manufacturer, or OEM replacement parts and supplies of all Nissan & Hyundai Vehicles
*Line item #18 LOT 1B, refers to Sole Sourcing Prestige Motors for Preventive Maintenance and repairs, and original equipment, or OEM supplies of all Ford vehicles. All Ford vehicles are currently in their first year of service
*Line item #19 LOT2, other vehicles maintenance refers to acquisition of spare parts/outsourcing garage through NCB for the servicing of other vehicles
*Line Item # 20, refers to sole sourcing H&A for Preventive Maintenance, Maintenance and repairs, and original equipment manufacturer, or OEM replacement parts and supplies of all MH&SW Generators
*Line Item # 21, refers to Renovation & Painting of MH&SW office Building
*Line Item # 22, refers to the procurement & furnishings of MH&SW's offices, Conference hall & other MH&SW's facilities
*Line Item # 23, refers to publication of Procurement notices, health messages and jingles
*Line Item # 24, refers to printing & binding Health cards, stock cards, reports and etc.
*Line Item # 25, refers to the rental of existing housing facilities for MH&SW Minister and foreign staff Doctors recruted by the MH&SW, mthod is NCB.
*Line Item # 26 LOT 1, refers to the procurement of essential drugs for MH&SW health facilities.
* Line Item # 27 LOT 2, refers to the contracting the Voluntary Pool Procurement Agency for the Procurement of HIV/AIDS drugs and supplies through the Global Fund Grant Arrangement
* Line Item # 28 LOT 3, refers to the procurement of other medical supplies which includes the Fistula Project for treatment of the fistula desease. Funding is from UNFPA
* Line Item # 29, refers to the procurement of foods stuff for inpatient at several referal Hospitals & TB annex through a National Competitive Bidding Process. Funding is by GOL and other Donors
* Line Item # 30, refers to budgeted item to facilitate foreign means of travel to international conferences etc.
* Line Item # 31, refers to budgeted item to facilitate domestic means of travel.
* Line Item # 32, refers to insurrance of MH&SW 132 vehicles
* Line Item # 33, refers to catering services for workshops, joint review meeting and Health plan review.
* Line Item # 34, refers to hiring external audit services for Pool Fund grant, the Global Fund and other Health Plan & Consultant Services
* Line Item # 35, refers to Budgetary Line Item for Unbudgeted Activities and Incidentals
* Line Item # 36, refers to Moving Cost which include clearing & forwarding of MH&SW goods and services from various port of entries
* Line Item # 37, refers to the rental of vehicles for the various Polio Campaigns, transportation of beds nets to targeted beneficiaries.
* Line Item # 38, refers to a Budgetary Line Item for Obtaining Refreshment Items for Visitors During Meetings Conferences, Etc.
Formulas:
Preparation of Bidding Doc. = [TECH SPEC]+12
PC Approval = [Preparation of Bidding Doc.]+7
PC Approval = [Bid Evaluation Report]+14
Advert/release bid doc = [PC Approval]+14
Advert/release bid doc = [Preparation of Bidding Doc.]+14
Bid subm opening = [Advert/release bid doc]+3
Bid subm opening = [PC Approval]+11
Bid Evaluation Report = [Bid subm opening]+4
Advance Payment = [PC Approval]+7
Advance Payment = [Contract Award/Signing]+14
Delivery = [Advance Payment]+60
Final Payment = [Delivery]+30
Contract Award/Signing = [PC Approval]+15

## Funding sources-2011-2012
FUNDING SOURCES
| Description | ITEM CODE | GOL | GFATM | GAVI | WORLD BANK | GOL SPECIAL PROJECT | DFID (POOL FUND) | EU | OTHER DONORS | TOTAL
1 | Diesel Fuel & Gasoline | IFB/MH&SW/NCB/001/2011 | 531409 | 368591 | 300000 | 400000 | 0 | 400000 | 0 | 245000 | 2245000
2 | Pediatric Hospital | IFB/MH&SW/ICB/001/2011 | 0 | 0 | 0 | 0 | 5000000 | 0 |  | 0 | 5000000
3 | Electrical Power a year (LEC Power Supply) | IFB/MH&SW/SS/001/2011 | 0 | 0 | 0 | 0 | 500000 | 0 |  | 0 | 500000
4 | New MH&SW Electrical High Voltage Connection | IFB/MH&SW/SS/002/2011 | 1734 | 0 | 0 | 0 | 0 | 0 |  | 18266 | 20000
5 | Water Supply (LWSC) | IFB/MH&SW/SS/003/2011 |  | 0 | 0 | 0 | 65000 | 0 |  | 0 | 65000
6 | National Blood Bank & Reference Lab. | IFB/MH&SW/ICB/002/2011 | 0 | 0 | 0 | 0 | 1500000 | 0 |  | 0 | 1500000
7 | Solar Panels for County Clinics | IFB/MH&SW/ICB/003/2011 | 0 | 0 | 0 | 0 | 500000 | 0 | 623555 |  | 1123555
8 | Staff Housing | IFB/MH&SW/NCB/002/2011 | 0 | 0 | 0 | 0 | 500000 | 0 |  | 0 | 500000
9 | Procurement Management System Software installation, training and Maintenance | IFB/MH&SW/SS/004/2011 | 20000 | 120000 | 0 | 0 | 0 | 0 |  | 57779 | 197779
10 | Procurement of transport equipment | IFB/MH&SW/ICB/004/2011 | 74000 | 300000 | 0 | 105000 | 0 | 0 |  | 196000 | 675000
11 | Communication, Phone cards | IFB/MH&SW/SS/005/2011 | 30000 | 20000 | 0 | 1318 | 0 | 0 |  | 18069 | 69387
12 | Stationery Supplies | IFB/MH&SW/NCB/003/2011 | 80388 | 10000 | 5000 | 7000 | 0 | 4000 |  | 2000 | 108388
13 | IT, Equipment | IFB/MH&SW/NCB/004/2011 | 3787 | 15000 | 10000 | 20000 | 0 | 12000 |  | 3325 | 64112
14 | IT Supplies & Accessories | IFB/MH&SW/NCB/005/2011 |  | 15000 | 2000 | 0 | 0 | 2000 |  | 2631 | 21631
15 | Modems subscription | IFB/MH&SW/SS/006/2011 | 1318 | 20000 | 7000 | 0 | 0 | 12000 |  | 2882 | 43200
16 | IT Service CONTRACT | IFB/MH&SW/SS/007/2011 | 0 | 20000 | 0 | 100000 | 75000 | 0 | 0 | 100993 | 295993
17 | Vehicles Repairs & Maintenance-(All Nissan & Hyundai Vehicles) | IFB/MH&SW/SS/008/2011 | 72930 | 10070 | 0 | 0 | 0 | 0 | 0 | 0 | 83000
18 | Vehicles Repairs & Maintenance-(All FORD Vehicles) | IFB/MH&SW/SS/009/2011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25750 | 25750
19 | Vehicles Repairs & Maintenance-Other vehicles | IFB/MH&SW/NCB/005/2011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72930 | 72930
20 | Generator Repairs & Maintenance | IFB/MH&SW/SS/010/2011 | 15661 | 0 | 0 | 0 | 0 | 0 | 0 | 8339 | 24000
21 | Maintenance-Civil works | IFB/MH&SW/RFQ/010/2011 | 11831 | 10000 | 0 | 0 | 0 | 0 | 0 | 6499 | 28330
22 | Furnishings | IFB/MH&SW/NCB/005/2011 | 7000 | 15000 | 45000 | 23000 |  | 80000 |  | 122534 | 292534
23 | Publication | IFB/MH&SW/NCB/006/2011 | 15000 | 12000 | 7000 | 0 | 0 | 18320 | 0 | 2730 | 55050
24 | Printing & binding | IFB/MH&SW/NCB/007/2011 | 18320 | 50000 | 25000 | 20000 | 0 | 15000 | 0 | 56975 | 185295
25 | Rental; | IFB/MH&SW/CC/001/2011 | 0 | 12000 | 5000 | 0 | 0 | 15000 | 0 | 3000 | 35000
26 | Essential Drugs & medical consumables | IFB/MH&SW/ICB/005/2011 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000
27 | HIV/AIDS Drugs | IFB/MH&SW/DC/005/2011 | 0 | 14531810 | 0 | 0 | 0 | 0 | 0 | 0 | 14531810
28 | other medical supplies | IFB/MH&SW/RB/002/2011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15800 | 15800
29 | Food Stuff | IFB/MH&SW/NCB/008/2011 | 34830 | 120000 | 75000 | 100000 | 0 | 0 | 0 | 63155 | 392985
30 | Foreign Means of Travel | IFB/MH&SW/NCB/009/2011 | 478000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 478000
31 | Domestic Means of Travel | IFB/MH&SW/NCB/009/2011 | 105381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105381
32 | Insurance, Vehicle | IFB/MH&SW/NCB/010/2011 | 96310 | 5250 | 0 | 0 | 0 | 0 | 0 | 0 | 101560
33 | Catering Services | IFB/MH&SW/NCB/011/2011 | 0 | 75000 | 50000 | 25000 | 0 | 45000 | 0 | 4980 | 199980
34 | Consultant Services | IFB/MH&SW/QCBS/001/2011 | 50000 | 30000 | 30000 | 0 | 0 | 107800 | 0 | 9892 | 227692
35 | Moving Cost | IFB/MH&SW/NCB/012/2011 | 9780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9780
36 | Vehicle Rentals | IFB/MH&SW/NCB/013/2011 | 9780 | 0 | 25500 | 0 | 0 | 0 | 0 | 18240 | 53520
37 | Tools Small/Equipment and Household | IFB/MH&SW/NCB/015/2011 | 62871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62871
38 | Entertainment & Gift | IFB/MH&SW/RFQ/002/2011 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000
GRAND TOTAL | [10 empty] | 30616313