## FINAL CORE BUDGET PLAN
MINISTRY OF AGRICULTURE
PROCUREMENT PLAN (CORE BUDGET)
SOURCE OF FUNDING: GOVERNMENT OF LIBERIA
FISCAL YEAR(FY) 2014 - 2015
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
BASIC DATA IMPLEMENTATION DATES
| Item No. | Code | Contract package | Qty | Est. Cost (USD) | Procurement method | Tech Spec/BOQ/ Drawings | Preparation of bidding document | PC App.1-bid doc./tech spec | Bid invitation & Release Doc | Bid sub/pub opening | Submission of Bid Evaluation report | Pc App. 2 of bid Evaluation report | Cont. Award /Signature | Advance payment (mobilization) | Delivery, inspection (subtantial completion) | Acceptance & final payment | Remarks
PLANNED | 1 | IFB No. MOA/NCB/001/14/15 | Foreign Travel - Means of travel | Assorted | 16501 | NCB | 2014-07-21 | 2014-07-25 | 2014-07-31 | 2014-08-05 | 2014-09-02 | 2014-09-16 | 2014-09-23 | 2014-10-07 | N/A | 2015-11-04 | 2015-06-12 | Find Detail Notes Attached
UPDATE
ACTUAL
PLANNED | 2 | IFB No. MOA/S.S/001/14/15 | Domestic Travel - Means of Travel | Assorted | 25000 | S.S | 2014-06-23 | 2014-06-27 | 2014-06-30 | N/A | N/A | N/A | N/A | 2014-07-04 | N/A | 2015-06-30 | 2015-06-30
UPDATE
ACTUAL
PLANNED | 3 | IFB No. MOA/S.S/002/14/15 | Internet | 3 modems subscription fees | 1690 | S.S | 2014-10-01 | 2014-10-07 | 2014-10-09 | N/A | N/A | N/A | N/A | 2014-10-27 | N/A | 2014-11-10 | 2015-06-05
UPDATE
ACTUAL
PLANNED | 4 | IFB No. MOA/RFQ/001/14/15 | Telecommunication | Assorted | 9765 | RFQ | 2014-07-04 | 2014-07-10 | 2014-07-16 | 2014-07-21 | 2014-08-27 | 2014-09-16 | 2014-09-18 | 2014-09-22 | N/A | 2015-06-11 | 2015-06-24
UPDATE
ACTUAL
PLANNED | 5 | IFB No. MOA/RB/001/14/15 | Petroluem Product-Vehicle & Generators | 53,968.5 gallons | 210274 | RB | 2014-07-10 | 2014-07-17 | 2014-07-18 | 2014-07-22 | 2014-08-29 | 2014-09-19 | 2014-09-24 | 2015-01-26 | N/A | 2015-06-15 | 2015-06-29
UPDATE
ACTUAL
PLANNED | 6 | IFB No. MOA/RFQ/002/14/15 | Repairs & Maint. Civil | 1- LIBSUCO Compound | 9750 | RFQ | 2014-11-05 | 2014-11-10 | 2014-11-12 | 2014-11-12 | 2014-11-19 | 2014-11-21 | 2014-11-24 | 2014-12-01 | N/A | 2014-12-15 | 2015-06-19
UPDATE
ACTUAL
PLANNED | 7 | IFB No. MOA/NCB/002/14/15 | Repairs & Maint. Vehicles | 93 Vehicles | 175644 | NCB | 2014-08-04 | 2014-08-11 | 2014-08-18 | 2014-08-20 | 2014-09-16 | 2014-09-30 | 2014-10-07 | 2014-10-21 | N/A | 2015-06-10 | 2015-06-29
UPDATE
ACTUAL
PLANNED | 8 | IFB No. MOA/NCB/003/14/15 | Repairs & Maint. Generator | Assorted | 27212 | NCB | 2015-01-12 | 2015-01-19 | 2015-01-28 | 2015-01-30 | 2015-02-26 | 2015-03-12 | 2015-03-19 | 2015-04-02 | N/A | 2015-04-30 | 2015-06-11
UPDATE
ACTUAL
PLANNED | 9 | IFB No. MOA/RFQ/003/14/15 | Repairs & Maint. Machinery, Equipment & Furniture | Assorted | 2999 | RFQ | 2014-09-05 | 2014-09-10 | 2014-09-12 | 2014-09-15 | 2014-09-24 | 2014-09-24 | 2014-09-29 | 2014-09-30 | N/A | 2015-06-04 | 2015-06-26
UPDATE
ACTUAL
PLANNED | 10 | IFB No. MOA/NCB/004/14/15 | Stationery | Assorted | 36950 | NCB | 2014-07-24 | 2014-07-04 | 2014-07-15 | 2014-07-21 | 2014-08-27 | 2014-10-01 | 2014-10-09 | 2015-01-23 | N/A | 2015-06-08 | 2015-06-22
UPDATE
ACTUAL
PLANNED | 11 | IFB No. MOA/RFQ/004/14/15 | Printing & Publication Services | Assorted | 9106 | RFQ | 2015-01-26 | 2015-01-30 | 2015-02-04 | 2015-02-05 | 2015-02-12 | 2015-02-13 | 2/16/2015 | 2015-02-23 | N/A | 2015-03-09 | 2015-05-27
UPDATE
ACTUAL
PLANNED | 12 | IFB No. MOA/RFQ/005/14/15 | Other Office Materials & Consumables | Assorted | 5625 | RFQ | 2014-09-03 | 2014-09-09 | 2014-09-11 | 2014-09-12 | 2014-09-23 | 2014-09-23 | 2014-09-25 | 2014-09-26 | N/A | 2015-04-17 | 2014-04-30
UPDATE
ACTUAL
PLANNED | 13 | IFB No. MOA/RFQ/006/14/15 | Workshops, conference &Siminars | Assorted | 1144 | RFQ | 2015-02-05 | 2015-02-09 | 2015-02-11 | 2015-02-12 | 2015-02-19 | 2015-02-20 | 2015-02-23 | 2015-03-02 | N/A | 2015-03-16 | 2015-04-30
UPDATE
ACTUAL
PLANNED | 14 | IFB No. MOA/RFQ/007/14/15 | Food and Catering Services | Assorted | 4502 | RFQ | 2014-11-12 | 2014-11-17 | 2014-11-19 | 2014-11-20 | 2014-11-27 | 2014-11-28 | 2014-12-01 | 2014-12-08 | N/A | 2014-12-22 | 2015-03-26
UPDATE
ACTUAL
PLANNED | 15 | IFB No. MOA/RFQ/008/14/15 | Adversting & Public Relations | Assorted | 3750 | RFQ | 2014-07-03 | 2014-07-09 | 2014-07-15 | 2014-07-16 | 2015-08-25 | 2014-09-12 | 2014-09-23 | 2014-10-13 | N/A | 2015-01-19 | 2015-01-29
UPDATE
ACTUAL
PLANNED | 16 | IFB No. MOA/NCB/005/14/15 | Guard & Security Services | 1 Firm | 138389 | NCB | 2014-07-04 | 2014-07-15 | 2014-07-21 | 2014-07-22 | 2014-12-09 | 2015-01-12 | 2015-01-22 | 2015-02-05 | N/A | 2015-06-15 | 2015-06-30
UPDATE
ACTUAL
PLANNED | 17 | IFB No. MOA/S.S/003/14/15 | Vehicle Insurance | 93 Vehicles | 60000 | S.S | 2015-01-16 | 2015-01-21 | 2015-01-26 | N/A | N/A | N/A | N/A | 2015-02-18 | N/A | 2015-03-17 | 2015-04-30
UPDATE
ACTUAL
PLANNED | 18 | IFB No. MOA/NCB/006/14/15 | Transport equipment | 2 motorbikes with helmets | 11250 | NCB | 2015-01-19 | 2015-01-26 | 2015-01-27 | 2015-02-02 | 2015-03-02 | 2015-03-16 | 2015-03-23 | 2015-04-06 | N/A | 2015-05-04 | 2015-05-18
UPDATE
ACTUAL
PLANNED | 19 | IFB No. MOA/NCB/007/14/15 | Agriculture Supplies & Inputs | Assorted | 108177 | NCB | 2015-01-23 | 2015-01-30 | 2015-02-05 | 2015-02-09 | 2015-03-09 | 2015-03-23 | 2015-03-30 | 2015-04-13 | N/A | 2015-05-11 | 2015-06-25
UPDATE
ACTUAL
|  |  |  | Grand Total:USD | 857728
| PREPARED BY: _______________________________________ | [6 empty] | APPROVED BY: ___________________________________________ | [6 empty] | DATE: _________________________________
|  | DIRECTOR OF PROCUREMENT | [6 empty] | CHAIRMAN, PROCUREMENT COMMITTEE

## FINAL CONSULTANCY PLAN
MINISTRY OF AGRICULTURE
PROCUREMENT PLAN: CONSULTANCY SERVICES (CORE BUDGET)
SOURCE OF FUNDING: GOVERNMENT OF LIBERIA
FISCAL YEAR: 2014/2015
1 | 2 | 3 | 4 | 5 | 6 |  | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
BASIC DATA | [6 empty] | FISCAL YEAR: 2014/2015 8: IMPLEMENTATION DATES
[9 empty] | REQUEST FOR EXPRESSION OF INTEREST, if applicable |  |  |  | REQUEST FOR PROPOSALS AND APPROVAL OF AWARD
| ITEM NO. | PACKAGE NUMBER (CODE) | CONTRACT PACKAGE | No. of FIRMS/PERSONS | ESTIMATED COST (USD) | SELECTION METHOD |  | PREP. OF TOR & PC APPROVAL | PUBLICATION OF REOI | REOI CLOSING/ OPENING | SUBMISSION OF EVALUATION REPORT | PC APPROVAL- EVALUATION REPORT/SHORTLIST | PREPARATION & SUBMISSION OF RFP DOCUMENT | PC APPROVAL - FINAL TOR/RFP DOCUMENT | INVITATION OF PROPOSALS | PROPOSAL SUBMISSION & OPENING | SUBMISSION OF TECHNICAL & FINANCIAL EVALUATION REPORT | PC APPROVAL- COMBINED EVALUATION REPORT | CONTRACT AWARD & SIGNING | COMPLETION (FINAL REPORT) AND PAYMENT
PLANNED | 1 | IFB No: MOA/S.S/001/14/15 | CONSULTANCY | 2 PERSONS | 32000 | S.S |  | 2014-11-10 | N/A | N/A | N/A | N/A | N/A | 2014-11-16 | N/A | N/A | N/A | N/A | 2015-01-28 | 2015-06-30
UPDATE
ACTUAL
GRAND TOTAL USD: |  |  |  |  | 32000
PREPARED BY: ___________________________________ | [5 empty] | APPROVED BY: ______________________________________ | FISCAL YEAR: 2014/2015 15: DATE: _____________________________________
PROCUREMENT DIRECTOR CHAIRMAN, PROCUREMENT COMMITTEE
Detail Note:
1 | IFB NO. MOA/S.S/001/14/15: This is for payment toward 2 Consultant for services to be rendered. In the current budget, the line consultancy services is use to make payment for the existing professionals
and non professionals at Central Agriculture Research Institute (CARI) and Professionals at Ministry of Agriculture Central office. Due to the changes made in the budget few years ago, the lines professional
services was taken out of the budget. The Ministry is now left to have its professional $ non-professionals who are are not on the payroll paid from the budget line consultancy services. Out of the
budget value for consultancy services in the amount of US$1,120,757.00 an amount of US$32,000.00 will be use toward the payment of the 2 consultants for FY 2014/2015.

## FINAL PLAN LIBERIA FOOD AID PRO
MINISTRY OFAGRICULTURE
PROCUREMENT PLAN: (JAPAN-LIBERIA FOOD AID PROJECT BUDGET)
SOURCE OF FUNDING: JAPANESE GOVERNMENT
FISCAL YEAR (FY) 2014 - 2015
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
BASIC DATA IMPLEMENTATION DATES
| Item | Code | Contract Package | Qty | Est. Cost | Procurement Method | Tech. Spec./BOQ | Preparation of Bid Documents | PC App.-1 bid doc/tech spec | Bid invitation & Release | Bid subm/pub opening | Submission of Bid Evaluation Report | PC App.-2 of bid evaluation report | Contract Award/ Signature | Advance Payment/ (mobiliation) | Delivery, inspection (subtantial completion) | Acceptance & Final Payment | Remarks
Planned | 1 | IFB no: MOA/JLFAP/NCB/001/'14/15 | Agriculture Inputs & Supplies | Assorted rice bags & milled rice processing materials | 122000 | NCB | 2015-01-19 | 2015-01-26 | 2015-01-30 | 2015-02-02 | 2015-03-02 | 2015-03-16 | 2015-03-23 | 2015-04-06 | N/A | 2015-05-05 | 2015-05-19
Update
Actual
Planned | 2 | IFB no: MOA/JLFAP/RB/001/'14/15 | Petroleum Product Vehicles & Motorbikes | 14,050 gallons | 56200 | RB | 2015-01-14 | 2015-01-21 | 2015-01-27 | 2015-01-26 | 2015-02-23 | 2015-03-09 | 2015-03-17 | 2015-03-31 | N/A | 2015-04-28 | 2015-06-11
Update
Actual
Planned | 3 | IFB no: MOA/JLFAP/S.S/001/'14/15 | Repairs & Maintenance Vehicles | Trucks & Pick-ups | 55000 | S.S | 2015-01-16 | 2015-01-21 | 2015-01-27 | N/A | N/A | N/A | N/A | 2015-02-10 | N/A | 2015-04-30 | 2015-06-12
Update
Actual
Planned | 4 | IFB no: MOA/JLFAP/RFQ/001/'14/15 | Advertising & Public Relations | Assorted | 4320 | RFQ | 2015-12-30 | 2014-01-06 | 2015-01-13 | 2015-01-15 | 2015-01-21 | 2015-01-23 | 2015-01-26 | 2015-02-02 | N/A | 2015-02-16 | 2015-06-24
Update
Actual
Planned | 5 | IFB no: MOA/JLFAP/RFQ/002/'14/15 | Tool & small equipment | 6 Units - bag sowing machines | 3000 | RFQ | 2015-02-02 | 2015-02-09 | 2015-02-11 | 2015-02-13 | 2015-02-19 | 2015-02-20 | 2015-02-23 | 2015-03-02 | N/A | 2015-03-16 | 2015-03-27
Update
Acual
Planned | 6 | IFB no: MOA/JLFAP/RFQ/003/'14/15 | ICT equipment | Assorted | 2075 | RFQ | 2015-01-09 | 2015-01-16 | 2015-01-20 | 2015-01-22 | 2015-01-28 | 2015-01-29 | 2015-02-02 | 2015-02-09 | N/A | 2015-02-16 | 2015-03-02
Update
Acual
Planned | 7 | IFB no: MOA/JLFAP/RFQ/004/'14/15 | Stationery | Assorted | 2400 | RFQ | 2015-01-09 | 2015-01-16 | 2015-01-20 | 2015-01-22 | 2015-01-28 | 2015-01-29 | 2015-02-02 | 2015-02-09 | N/A | 2015-02-16 | 2015-03-02
Update
Acual
Planned | 8 | IFB no: MOA/JLFAP/RFQ/005/'14/15 | Furniture & Fixture | Assorted | 2500 | RFQ | 2015-01-12 | 2015-01-19 | 2015-01-21 | 2015-01-22 | 2015-01-29 | 2015-01-30 | 2015-02-02 | 2015-02-06 | N/A | 2015-02-20 | 2015-03-06
Update
Acual
Planned | 9 | IFB no: MOA/JLFAP/NCB/002/'14/15 | Transport Equipment | 1 Unit-Truck | 49000 | NCB | 2015-01-09 | 2015-01-16 | 2015-01-21 | 2015-01-23 | 2015-02-19 | 2015-03-05 | 2015-03-12 | 2015-03-26 | N/A | 2015-04-23 | 2015-05-07
Update
Actual
|  |  | Grand Total: USD |  | 296495
Prepared by: __________________________________ | [5 empty] | Approved: ___________________________________________ | [5 empty] | Date: _______________________________
| DIRECTOR OF PROCUREMENT | [5 empty] | CHAIRPERSON, PROCUREMENT COMMITTEE
Detailed Notes:
1 | IFB No: MOA/JLFAP/NCB/001/14/15: |  | Purchase of 80,000.00 rice bags- 60 kg size, 45,000.00 rice bags-25kg and assorted milled rice processing materials
2 | IFB No: MOA/JLFAP/RB/001/14/15: |  | Purchase of fuel & gasoline for vehicles and motorbikes
3 | IFB No: MOA/JLFAP/S.S/001/14/15: |  | Repairs & Maintenace of vehicle which include trucks & pickups to be sole source to Alliance Motors Company, this entity is the sole distributor of Mecede truck, of which these
these trucks were purchase through the above entity. The trucks drives the activities of the Japan -Liberia Food Aid Project by collecting paddy & seed rices from the farmer within counties.
As a result, we want to ensure that these trucks are service with genuine spare part to avoid break down.
4 | IFB No: MOA/JLFAP/RFQ/001/14/15: |  | Payment for advertising of bids and other public relations activies
5 | IFB No: MOA/JLFAP/RFQ/002/14/15: |  | purchase of bag sowing machines
6 | IFB No: MOA/JLFAP/RFQ/003/14/15: |  | purchase of laptop and color printer
7 | IFB No: MOA/JLFAP/RFQ/004/14/15: |  | purchase of office material,which include: Paper, pen, binder clips, box files, cartridges ects
8 | IFB No: MOA/JLFAP/RFQ/005/14/15: |  | purchase of office desks, chairs
9 | IFB No: MOA/JLFAP/NCB/002/14/15: |  | Purchase of 1 Unit of 2.6 tons truck