|  | 2 | 3 | 4 |  | 5 |  | 6 |  | 7 | 8 |  | 9 |  | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | ITEM NO. | BASIC DATA |  |  |  |  |  |  |  | IMPLEMENTATION DATES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | REQUEST FOR EXPRESSION OF INTEREST, if applicable |  |  |  |  |  | REQUEST FOR PROPOSALS AND APPROVAL OF AWARD |  |  |  |  |  |  |  |
|  |  | PACKAGE NUMBER (CODE) | CONTRACT PACKAGE | No. of FIRMS/PERSONS |  | ESTIMATED COST (USD) |  | SELECTION METHOD |  | PREP. OF TOR& PC APPROVAL | PUBLICATION OF REOI |  | REOI CLOSING/ OPENING |  | SUBMISSION OF EVALUATION REPORT | PC APPROVAL- EVALUATION REPORT/SHORTLIST | PREPARATION & SUBMISSION OF RFP DOCUMENT | PC APPROVAL - FINAL TOR/RFP DOCUMENT | INVITATION OF PROPOSALS | PROPOSAL SUBMISSION & OPENING | SUBMISSION OF TECHNICAL & FINANCIAL EVALUATION REPORT | PC APPROVAL- COMBINED EVALUATION REPORT | CONTRACT AWARD & SIGNING | COMPLETION (FINAL REPORT) AND PAYMENT |
| PLANNED | 1 | IFB No./FDA/CQS/001/14/15 | Legal Services | 5 |  | $ 397,308.00 |  | CQS |  | 7-Jan-15 | 14-Jan-15 |  | 3-Feb-15 |  | 17-Feb-15 | 27-Feb-15 | 19-MAr-15 | 31-Mar-15 | 7-Apr-15 | 30-Apr-15 | 14-May-15 | 22-May-15 | 5-Jun-15 | 30-June-15 |
| UPDATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| GRAND TOTAL |  |  |  |  |  | $ 397,308.00 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

FORESTRY DEVELPOMENT AUTHORITY

PROCUREMENT PLAN (CODE BUDGET)

Source of Funding:  GOVERNMENT OF LIBERIA

Fiscal year:	 2014/2015

Prepared by: ___________________________________				Approved by: ________________________________________	    Date: ________________

Manager, Procurement Unit     						                Head of Entity/Chairman Proc. Committee

ITEM 1.		Consultancy Services will be procured through CQS method and will be for five professional services both legal and forestry related specialty.