FORESTRY DEVELPOMENT AUTHORITY

PROCUREMENT PLAN (CODE BUDGET)

Source of Funding: GOVERNMENT OF LIBERIA

Fiscal year: 2014/2015

| 1 | 2 | 3 | 4 | 5 |  | 6 |  | 7 |  |  | 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | 17 | 18 |  |  | 19 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | ITEM NO. | BASIC DATA |  |  |  |  |  |  |  |  | IMPLEMENTATION DATES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | . |  |
|  |  | PACKAGE NUMBER (CODE) | CONTRACT PACKAGE | QTY | ESTIMATED COST (USD) |  | PROCURE-MENT METHOD |  |  |  | TECHNICAL SPECS/BOQ/DRAWINGS | PREP. OF BID DOCUMENT |  | PC APPROVAL - BID DOC/TECH SPECS |  | BID INVITATION & RELEASE OF BID DOC |  | BID SUBMISSION/PUBLIC OPENING |  | SUBMISSION OF BID EVALUATION REPORT |  | PC APPROVAL - BID EVALUATION REPORT |  | CONTRACT AWARD & SIGNING |  |  | ADVANCE PAYMENT (MOBILIZATION) | DELIVERY, INSPECTION (SUBSTANTIAL COMPLETION) |  |  | ACCEPTANCE & FINAL PAYMENT | REMARKS |  |
| PLANNED | 1 | IFB No.FDA/NCB/001/14/15 | Telecommunication, Internet, Postage and Courier | Assorted | $ 39,138.00 |  | NCB |  |  |  | 5-Jan-15 | 16-Jan-15 |  | 23-Jan-15 |  | 30-Jan-15 |  | 3-Mar-15 |  | 17-Mar-15 |  | 26-Mar-15 |  | 16-April-15 |  |  | N/A | 5-Jun-15 |  |  | 30-Jun-15 |  |  |
| UPDATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PLANNED | 2 | IFB No.FDA/RB/001/14/15 | Fuel and Lubricant/Petroleum Products (Vehicle/Generator) | 21,444.95gals | $ 140,250.00 |  | RB |  |  |  | 5-Jan-15 | 16-Jan-15 |  | 23-Jan-15 |  | 30-Jan-15 |  | 3-Mar-15 |  | 17-Mar-15 |  | 26-Mar-15 |  | 16-April-15 |  |  | N/A | 5-Jun-15 |  |  | 30-Jun-15 |  |  |
| UPDATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PLANNED | 3 | IFB No.FDA/RB/001/14/15 | Repair and Maintenance - Civil | 7 | $ 9 ,750.00 |  | RFQ |  |  |  | 13-Jan-15 | 27-Jan-15 |  | 3-Feb-15 |  | 10-Feb-15 |  | 17-Feb-15 |  | 26-Feb-15 |  | 11-Mar-15 |  | 26-Mar-15 |  |  | N/A | 2-April-15 |  |  | 16-April-15 |  |  |
| UPDATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PLANNED | 4 | IFB No.FDA/NCB/002/14/15 | Repair and Maintenance - Vehicles | 86 | $ 79,125.00 |  | NCB |  |  |  | 12 -Jan-15 | 26-Jan-15 |  | 5-Feb-15 |  | 11-Feb-15 |  | 11-Mar-15 |  | 27-Mar-15 |  | 7-April-15 |  | 28-April-15 |  |  | N/A | 2-Jun-15 |  |  | 30-Jun-15 |  |  |
| UPDATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | 2 | 3 | 4 | 5 | 6 |  | 7 |  |  |  | 8 | 9 |  | 10 |  | 11 |  | 12 |  | 13 |  | 14 |  | 15 |  |  | 16 | 17 |  |  | 18 | 19 |  |
|  | ITEM NO. | BASIC DATA |  |  |  |  |  |  |  |  | IMPLEMENTATION DATES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | PACKAGE NUMBER (CODE) | CONTRACT PACKAGE | QTY | ESTIMATED COST (USD) |  | PROCURE-MENT METHOD |  |  |  | TECHNICAL SPECS/BOQ/DRAWINGS | PREP. OF BID DOCUMENT |  | PC APPROVAL - BID DOC/TECH SPECS |  | BID INVITATION & RELEASE OF BID DOC |  | BID SUBMISSION/PUBLIC OPENING |  | SUBMISSION OF BID EVALUATION REPORT |  | PC APPROVAL - BID EVALUATION REPORT |  | CONTRACT AWARD & SIGNING |  |  | ADVANCE PAYMENT (MOBILIZATION) | DELIVERY, INSPECTION (SUBSTANTIAL COMPLETION) |  |  | ACCEPTANCE & FINAL PAYMENT | REMARKS |  |
| PLANNED | 5 | IFB No.FDA/NCB/003/14/15 | Repairs & Maintenance - Plant, Machinery, Equipment | Assorted | $ 39,375.00 |  | NCB |  |  |  | 9 -Jan-15 | 23-Jan-15 |  | 31-Jan-15 |  | 6-Feb-15 |  | 6-Feb-15 |  | 26-Mar-15 |  | 3-April-15 |  | 24-April-15 |  |  | N/A | 2-Jun-15 |  |  | 30-Jun-15 |  |  |
| UPDATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PLANNED | 6 | IFB No.FDA/NCB/004/14/15 | Stationery | Assorted | $ 66,675.00 |  | NCB |  |  |  | 12 -Jan-15 | 26-Jan-15 |  | 5-Feb-15 |  | 11-Feb-15 |  | 11-Mar-15 |  | 27-Mar-15 |  | 7-April-15 |  | 28-April-15 |  |  | N/A | 2-Jun-15 |  |  | 30-Jun-15 |  |  |
| UPDATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PLANNED | 7 | IFB No.FDA/NCB/005/14/15 | Printing, Binding and Publication Services | Assorted | $ 14,653.00 |  | NCB |  |  |  | 9 -Jan-15 | 23-Jan-15 |  | 31-Jan-15 |  | 6-Feb-15 |  | 6-Feb-15 |  | 26-Mar-15 |  | 3-April-15 |  | 24-April-15 |  |  | N/A | 2-Jun-15 |  |  | 30-Jun-15 |  |  |
| UPDATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PLANNED | 8 | IFB No.FDA/RFQ/002/14/15 | Newspapers, Books and Periodicals | Assorted | $ 5,693.00 |  | RFQ |  |  |  | 29-Jan-15 | 5-Feb-15 |  | 10-Feb-15 |  | 17-Feb-15 |  | 24-Feb-15 |  | 7-Mar-15 |  | 19-Mar-15 |  | 27-Mar-15 |  |  | N/A | 25-May-15 |  |  | 19-Jun-15 |  |  |
| UPDATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PLANNED | 9 | IFB No.FDA/RFQ/003/14/15 | Other Office Materials & Consumables | Assorted | $ 4,670.00 |  | RFQ |  |  |  | 3-Feb-15 | 17-Feb-15 |  | 24-Feb-15 |  | 3-Mar-15 |  | 10-Mar-15 |  | 21-Mar-15 |  | 31-Mar-15 |  | 14-April-15 |  |  | N/A | 24-April-15 |  |  | 14-May-15 |  |  |
| UPDATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | 2 | 3 | 4 | 5 | 6 |  | 7 |  |  |  | 8 | 9 |  | 10 |  | 11 |  | 12 |  | 13 |  | 14 |  | 15 |  |  | 16 | 17 |  |  | 18 | 19 |  |
|  | ITEM NO. |  | BASIC DATA IMPLEMENTATION DATES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | PACKAGE NUMBER (CODE) | CONTRACT PACKAGE | QTY |  | ESTIMATED COST (USD) |  |  | PROCUREMENT METHOD | TECHNICAL SPECS/BOQ/DRAWINGS |  | PREP. OF BID DOC9UMENT |  | PC APPROVAL - BID DOC/TECH SPECS |  | BID INVITATION & RELEASE OF BID DOC |  | BID SUBMISSION/PUBLIC OPENING |  | SUBMISSION OF BID EVALUATION REPORT |  | PC APPROVAL - BID EVALUATION REPORT |  | CONTRACT AWARD & SIGNING |  |  | ADVANCE PAYMENT (MOBILIZATION) | DELIVERY, INSPECTION (SUBSTANTIAL COMPLETION) |  |  | ACCEPTANCE & FINAL PAYMENT | REMARKS |  |
| PLANNED | 10 | IFB No.FDA/RFQ/00414/15 | Agriculture Supplies and Inputs | Assorted |  | $ 4,125.00 |  |  | RFQ | 6-Feb-15 |  | 20-Feb-15 |  | 26-Feb-15 |  | 6-Mar-15 |  | 13-Mar-15 |  | 27-Mar-15 |  | 10-April-15 |  | 22-April-15 |  |  | N/A | 29-April-15 |  |  | 13-May -15 |  |  |
| UPDATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PLANNED | 11 | IFB No.FDA/RFQ/005/14/15 | Workshops, Conferences, Symposia & Seminars | 3 |  | $ 8,318.00 |  |  | RFQ | 2-Jan-15 |  | 16-Jan-15 |  | 23-Jan-15 |  | 30-Jan-15 |  | 6-Feb-15 |  | 18-Feb-15 |  | 6-Mar-15 |  | 27-Mar-15 |  |  | N/A | 16 -Jun-15 |  |  | 30-Jun-15 |  |  |
| UPDATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PLANNED | 12 | IFB No.FDA/NCB/006/14/15 | Food & Catering Services | 9 |  | $62,650.00 |  |  | NCB | 2-Jan-15 |  | 21-Jan-15 |  | 4-Fbe-15 |  | 10-Feb-15 |  | 10-Mar-15 |  | 27-Mar-15 |  | 6-April-15 |  | 23-April-15 |  |  | N/A | 31-May-15 |  |  | 30-Jun-15 |  |  |
| UPDATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PLANNED | 13 | IFB No.FDA/RFQ/006/14/15 | Small Tools/Equipment and Household Materials | Assorted |  | $7,125.00 |  |  | RFQ | 3-Feb-15 |  | 17-Feb-15 |  | 24-Feb-15 |  | 3-Mar-15 |  | 10-Mar-15 |  | 18-Mar-15 |  | 25-Mar-15 |  | 8-April-15 |  |  | N/A | 20-April-15 |  |  | 7-May-15 |  |  |
| UPDATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | 2 | 3 | 4 | 5 |  | 6 |  |  | 7 | 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13 |  | 14 |  | 15 |  |  | 16 | 17 |  |  | 18 | 19 |  |
|  | ITEM NO. | BASIC DATA |  |  |  |  |  |  |  | IMPLEMENTATION DATES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | PACKAGE NUMBER (CODE) | CONTRACT PACKAGE | QTY |  | ESTIMATED COST (USD) |  |  | PROCUREMENT METHOD | TECHNICAL SPECS/BOQ/DRAWINGS |  | PREP. OF BID DOC9UMENT |  | PC APPROVAL - BID DOC/TECH SPECS |  | BID INVITATION & RELEASE OF BID DOC |  | BID SUBMISSION/PUBLIC OPENING |  | SUBMISSION OF BID EVALUATION REPORT |  | PC APPROVAL - BID EVALUATION REPORT |  | CONTRACT AWARD & SIGNING |  | ADVANCE PAYMENT (MOBILIZATION) |  | DELIVERY, INSPECTION (SUBSTANTIAL COMPLETION) |  |  | ACCEPTANCE & FINAL PAYMENT | REMARKS |  |
| PLANNED | 14 | IFB No.FDA/RFQ/007/14/15 | Entertainment, Representation & Gifts | 8 |  | $7,420.00 |  |  | RFQ | 2-Mar-15 |  | 9-Mar-15 |  | 16-Mar-15 |  | 23-Mar-15 |  | 30-Mar-15 |  | 8-April-15 |  | 20-April-15 |  | 4-May-15 |  | N/A |  | 15-May-15 |  |  | 29-May-15 |  |  |
| UPDATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PLANNED | 15 | IFB No.FDA/NCB/007/14/15 | Personnel Insurance | 1 |  | $78,000.00 |  |  | NCB | 2-Jan-15 |  | 23-Jan-15 |  | 5-Feb-15 |  | 12-Feb-15 |  | 13-Mar-15 |  | 3-April-15 |  | 15-April-15 |  | 6-May-15 |  | N/A |  | 5-Jun-15 |  |  | 30-Jun-15 |  |  |
| UPDATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PLANNED | 16 | IFB No.FDA/NCB/008/14/15 | Vehicles Insurance | 1 |  | $115,500.00 |  |  | NCB | 2-Jan-15 |  | 23-Jan-15 |  | 5-Feb-15 |  | 12-Feb-15 |  | 13-Mar-15 |  | 3-April-15 |  | 15-April-15 |  | 6-May-15 |  | N/A |  | 5-Jun-15 |  |  | 30-Jun-15 |  |  |
| UPDATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PLANNED | 17 | IFB No.FDA/NCB/009/14/15 | Transport Equipment | 12 |  | $477,500.00 |  |  | NCB | 15-Jan-15 |  | 26-Jan-15 |  | 4-Feb-15 |  | 12-Feb-15 |  | 12-Mar-15 |  | 24-Mar-15 |  | 7-April-15 |  | 21-April-15 |  | N/A |  | 15-May-15 |  |  | 16- jun-15 |  |  |
| UPDATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PLANNED | 18 | IFB No.FDA/NCB/010/14/15 | Machinery & Other Equipment | Assorted |  | 100,000.00 |  |  | NCB | 29-Jan-15 |  | 17-Feb-15 |  | 4-Mar-15 |  | 10-Mar-15 |  | 10-April-15 |  | 24-April-15 |  | 1-May-15 |  | 15-May-15 |  | N/A |  | 29-May-15 |  |  | 30-Jun-15 |  |  |
| UPDATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PLANNED | 19 | IFB No.FDA/NCB/011/14/15 | Furniture and Fixtures | Assorted |  | 50,000.00 |  |  | NCB | 29-Jan-15 |  | 17-Feb-15 |  | 4-Mar-15 |  | 10-Mar-15 |  | 10-April-15 |  | 24-April-15 |  | 1-May-15 |  | 15-May-15 |  | N/A |  | 29-May-15 |  |  | 30-Jun-15 |  |  |
| UPDATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| GRAND TOTAL |  |  |  |  |  | $457,850.00 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Prepared by: ___________________________________				Approved by: ________________________________________	        		Date: ________________

Manager, Procurement Unit     							 Head of Entity/Chairman Proc. Committee

ITEM 1.	Telecommunication, Internet, Postage and Courier will be procured through NC B method, this item line has different services and will required competent vendors to take part in the NCB process and supply the services if qualified.

ITEM 2.	Fuel and lubricant will be procured through RB method; we will look into our data base of fuel and lubricants companies, survey the petroleum market and invite legitimate petroleum companies to bid for the supply of the product.

ITEM 3.	Repair and Maintenance Civil will be procured through RFQ method; this service will be done upon the request and need of all the entity’s sub offices in the four forest regions of the FDA.

ITEM 4.	Repair and Maintenance Vehicles will be procured through NCB method; this service is provided through a Bidding process after which contract will be sign with the less evaluated bidder for spare parts for repair of any of the entity’s vehicle, the maintenance is dome by the mechanic section of the entity except for major cases that requires mechanical specialty.

ITEM 5.	Repair and Maintenance Plant, Machinery, Equipment and Furniture will be procured through NCB method; this service will be provided upon the request and need of all the entity’s central and sub offices in the four Forest Regions of the FDA. This item line is a combination of small and different expertise of required job.  Items may include; Chairs, Desks, Tables, Air-conditions, Refrigerators, Printers, Computers, etc.

ITEM 6.	Stationery will be provided through NCB method; this is an assorted quantity of items and below is just to name a few:

1. A4 papers, 		6. Staple machines		11. Binding papers		16. Manila folders		21. Bind clips		26. Desk pad

2. Cartridges, 		7. Staple pins			12. Binding plastics		17. Hanging folders		22. Scotch tapes	27. Pens

3. HP toners, 		8. Perforator			13. Binding tapes		18. Steno pads			23. Highlighters	28. Pencils

4. Envelops		9. Desk tray			14. Color papers		19. Yellow pads		24. Markers		29. Clip board

5. Legal papers	10. Bind comb			15. Box files			20. Paper clips			25. Flip charts		30. Flip chart marker

ITEM 7.	Printing Binding and Publications services will be procured through NCB method; this item line has different services and will required competent vendors to take part in the NCB process and supply the services if qualified. These may include; Annual Reports, Advertisement, Newspapers, etc.

ITEM 8.	Newspaper, Books and Periodicals will be procured through RFQ method; these services are procure from different vendors

ITEM 9.	Other Office Materials and Consumable will be procured through RFQ method; these items are procured from different vendors.

ITEM 10.	Agricultural Supplies and Inputs will be procured through RFQ method; these items are procured from different vendors, the local and hardware markets. These services are also required in the four forest regions of the FDA. Items may include; Seeds, Polythene bags, Fertilizers, Insecticides, Hoes, etc.

ITEM 11.	Workshop Conference, Symposium and Seminar will be procured through RFQ method; these services are offered by different vendors and in various locations as the need may arise.

ITEM 12.	Food and Catering Services will be procured through NCB method; will be procured in different locations of the of the forest regions as the need may arise

ITEM 13.	Small Tools/Equipment and Household Materials will be procured through RFQ method; this service is provided through a Bidding process after which contract will be sign with the less evaluated bidder.

ITEM 14.	Entertainment Representation and Gifts will be procured through RFQ method; these services and items are provided by different   vendors and locations

ITEM 15.	Personnel Insurance will be procured through NCB method.

ITEM 16.	Vehicle Insurance will be procured through NCB method.

ITEM 17.	Transport Equipment will be procured through NCB method.

ITEM 18.	Machinery & other Equipment will be procured through NCB method. (Generators, Grass cutter, Water pump etc)

ITEM 19.	Furniture & Fixtures will be procured through NCB method. (Desk, Chair, Bookshelf, Corkboard etc)