## 2014 2015 Goods Procurement P
GOVERNANCE COMMISSION
PROCUREMENT PLAN (CORE BUDGET)
Source of funding: GOVERNMENT OF LIBERIA (GoL)
Budget period: 2014/2015
1 | 2 | 3 | 4 | 5 |  |  | 6 |  | 7 |  | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 |  | 17 |  |  | 18 | 19
| ITEM NO. | BASIC DATA | [8 empty] | 8: IMPLEMENTATION DATES | [5 empty] | .
|  | PACKAGE NUMBER (CODE) | CONTRACT PACKAGE |  | QTY |  |  | ESTIMATED COST (USD) |  | PROCUREMENT METHOD | TECHNICAL SPECS/BOQ/DRAWINGS | PREP. OF BID DOCUMENT | PC APPROVAL - BID DOC/TECH SPECS | BID INVITATION & RELEASE OF BID DOC | BID SUBMISSION/PUBLIC OPENING | SUBMISSION OF BID EVALUATION REPORT | PC APPROVAL - BID EVALUATION REPORT | CONTRACT AWARD & SIGNING |  | ADVANCE PAYMENT (MOBILIZATION) |  | DELIVERY, INSPECTION (SUBSTANTIAL COMPLETION) | ACCEPTANCE & FINAL PAYMENT |  | REMARKS
PLANNED | 1 | IFB No. GC/RB/001/14/15 | Petroleum Products |  |  | 28,978.61 US Gallons | 100266 |  |  | RB | 2014-12-24 | 2014-12-31 | 2015-01-07 | 2015-01-14 | 2015-02-11 | 2015-02-25 | 2015-03-04 | 2015-03-18 |  | N/A |  | 2015-06-11 | 2015-06-25
UPDATE
[6 empty] | 27,865.30 US Gallons | 101987 |  |  | RB | 2014-12-24 | 2014-12-31 | 2015-01-07 | 2015-01-14 | 2015-02-11 | 2015-02-25 | 2015-03-04 | 2015-03-18 |  | N/A |  | 2015-05-11 | 2015-05-25
ACTUAL
PLANNED | 2 | IFB No. GC/NCB/001/14/15 | Transport Equipment (Vehicle - Van) |  |  | 1 Vehicle |  | 40000 |  | NCB | 2014-12-26 | 2015-01-02 | 2015-01-09 | 2015-01-16 | 2015-02-13 | 2015-02-27 | 2015-03-06 | 2015-03-20 |  | N/A |  | 2015-04-01 | 2015-04-15
UPDATE
ACTUAL
PLANNED | 3 | IFB No. GC/NCB/002/14/15 | Guard & Security Services |  |  | 1 Firm |  | 21000 |  | NCB | 2014-12-29 | 2015-01-05 | 2015-01-12 | 2015-01-19 | 2015-02-16 | 2015-03-02 | 2015-03-09 | 2015-03-23 |  | N/A |  | 2015-06-03 | 2015-06-17
UPDATE
ACTUAL
PLANNED | 4 | IFB No. GC/Various/001/14/15 | Telecommunications, internet, Postage, & Courier |  |  | Assorted |  | 34400 |  | Various | 2014-12-31 | 2015-01-07 | 2015-01-14 | 2015-01-21 | 2015-02-18 | 2015-03-04 | 2015-03-11 | 2015-03-25 |  | N/A |  | 2015-06-05 | 2015-06-19
UPDATE
ACTUAL
PLANNED | 5 | IFB No. GC/NCB/003/14/15 | Repair & Maintenance - Vehicles |  |  | 12 Vehicles |  | 24000 |  | NCB | 2014-12-30 | 2015-01-06 | 2015-01-13 | 2015-01-20 | 2015-02-17 | 2015-03-03 | 2015-03-10 | 2015-03-24 |  | N/A |  | 2015-04-01 | 2015-04-15
UPDATE
ACTUAL
PLANNED | 6 | IFB No. GC/NCB/004/14/15 | Printing |  |  | 10,000 Books |  | 27500 |  | NCB | 2014-12-31 | 2015-01-07 | 2015-01-14 | 2015-01-21 | 2015-02-18 | 2015-03-04 | 2015-03-11 | 2015-03-25 |  | N/A |  | 2015-06-08 | 2015-06-22
UPDATE
ACTUAL
1 | 2 | 3 | 4 | 5 |  |  | 6 |  | 7 |  | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 |  | 17 |  |  | 18 | 19
| ITEM NO. | BASIC DATA | [8 empty] | 8: IMPLEMENTATION DATES | [5 empty] | .
|  | PACKAGE NUMBER (CODE) | CONTRACT PACKAGE |  | QTY |  |  | ESTIMATED COST (USD) |  | PROCUREMENT METHOD | TECHNICAL SPECS/BOQ/DRAWINGS | PREP. OF BID DOCUMENT | PC APPROVAL - BID DOC/TECH SPECS | BID INVITATION & RELEASE OF BID DOC | BID SUBMISSION/PUBLIC OPENING | SUBMISSION OF BID EVALUATION REPORT | PC APPROVAL - BID EVALUATION REPORT | CONTRACT AWARD & SIGNING |  | ADVANCE PAYMENT (MOBILIZATION) |  | DELIVERY, INSPECTION (SUBSTANTIAL COMPLETION) | ACCEPTANCE & FINAL PAYMENT |  | REMARKS
PLANNED | 7 | IFB No. GC/RFQ/001/14/15 | Stationery / Materials |  |  | Assorted |  | 5000 |  | RFQ | 2014-12-09 | 2014-12-16 | 2014-12-23 | 2014-12-30 | 2015-01-13 | 2015-01-27 | 2015-02-03 | 2015-02-17 |  | N/A |  | 2015-06-08 | 2015-06-22
UPDATE
ACTUAL
PLANNED | 8 | IFB No. GC/RFQ/002/14/15 | Repair & Maintenance - Generators |  |  | 2 Generators |  | 2850 |  | RFQ | 2014-12-10 | 2014-12-17 | 2014-12-24 | 2014-12-31 | 2015-01-14 | 2015-01-28 | 2015-02-04 | 2015-02-18 |  | N/A |  | 2015-03-11 | 2015-03-25
UPDATE
ACTUAL
PLANNED | 9 | IFB No. GC/RFQ/003/14/15 | Repair & Maintenance - Machinery & Equipment |  |  | Assorted |  | 4000 |  | RFQ | 2014-12-12 | 2014-12-19 | 2014-12-26 | 2015-01-02 | 2015-01-16 | 2015-01-30 | 2015-02-06 | 2015-02-20 |  | N/A |  | 2015-04-01 | 2015-04-15
UPDATE
ACTUAL
PLANNED | 10 | IFB No. GC/RFQ/004/14/15 | Cleaning Materials & Services |  |  | Assorted |  | 1000 |  | RFQ | 2014-12-15 | 2014-12-22 | 2014-12-29 | 2015-01-05 | 2015-01-19 | 2015-02-02 | 2015-02-09 | 2015-02-23 |  | N/A |  | 2015-03-16 | 2015-03-30
UPDATE
ACTUAL
PLANNED | 11 | IFB No. GC/RFQ/005/14/15 | Computer Supplies & ICT Service |  |  | Assorted | 5000 |  |  | RFQ | 2014-12-17 | 2014-12-24 | 2014-12-31 | 2015-01-07 | 2015-01-21 | 2015-02-04 | 2015-02-11 | 2015-02-25 |  | N/A |  | 2015-04-07 | 2015-04-21
UPDATE
ACTUAL
PLANNED | 12 | IFB No. GC/RFQ/006/14/15 | Workshop (Entertainment) |  |  | 1 |  | 5500 |  | RFQ | 2014-12-19 | 2014-12-26 | 2015-01-02 | 2015-01-09 | 2015-01-23 | 2015-02-06 | 2015-02-13 | 2015-02-27 |  | N/A |  | 2015-03-17 | 2015-03-31
UPDATE
ACTUAL
PLANNED | 13 | IFB No. GC/RFQ/007/14/15 | Vehicle Insurance |  |  | 12 Vehicles |  | 2400 |  | RFQ | 2014-12-22 | 2014-12-29 | 2015-01-05 | 2015-01-12 | 2015-01-26 | 2015-02-09 | 2015-02-16 | 2015-03-02 |  | N/A |  | 2015-03-20 | 2015-04-03
UPDATE
ACTUAL
1 | 2 | 3 | 4 | 5 |  |  | 6 |  | 7 |  | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 |  | 17 |  |  | 18 | 19
| ITEM NO. | BASIC DATA | [8 empty] | 8: IMPLEMENTATION DATES | [5 empty] | .
|  | PACKAGE NUMBER (CODE) | CONTRACT PACKAGE |  | QTY |  |  | ESTIMATED COST (USD) |  | PROCUREMENT METHOD | TECHNICAL SPECS/BOQ/DRAWINGS | PREP. OF BID DOCUMENT | PC APPROVAL - BID DOC/TECH SPECS | BID INVITATION & RELEASE OF BID DOC | BID SUBMISSION/PUBLIC OPENING | SUBMISSION OF BID EVALUATION REPORT | PC APPROVAL - BID EVALUATION REPORT | CONTRACT AWARD & SIGNING |  | ADVANCE PAYMENT (MOBILIZATION) |  | DELIVERY, INSPECTION (SUBSTANTIAL COMPLETION) | ACCEPTANCE & FINAL PAYMENT |  | REMARKS
PLANNED | 14 | IFB No. GC/RFQ/008/14/15 | Entertainment, Representation & Gifts |  |  | Assorted |  | 1000 |  | RFQ | 2014-12-24 | 2014-12-31 | 2015-01-07 | 2015-01-14 | 2015-01-28 | 2015-02-11 | 2015-02-18 | 2015-03-04 |  | N/A |  | 2015-03-19 | 2015-04-02
UPDATE
ACTUAL
PLANNED | 15 | IFB No. GC/RFQ/009/14/15 | Personnel Insurance |  |  | 1 Firm |  | 9600 |  | RFQ | 2014-12-29 | 2015-01-05 | 2015-01-12 | 2015-01-19 | 2015-02-02 | 2015-02-16 | 2015-02-23 | 2015-03-09 |  | N/A |  | 2015-06-11 | 2015-06-25
UPDATE
ACTUAL
PLANNED | 16 | IFB No. GC/RFQ/010/14/15 | Advertising & Publication Relations |  |  | Assorted |  | 7500 |  | RFQ | 2014-12-31 | 2015-01-07 | 2015-01-14 | 2015-01-21 | 2015-02-04 | 2015-02-18 | 2015-02-25 | 2015-03-11 |  | N/A |  | 2015-04-01 | 2015-04-15
UPDATE
ACTUAL
PLANNED | 17 | IFB No. GC/RFQ/011/14/15 | Furniture & Fixture |  |  | Assorted |  | 4000 |  | RFQ | 2014-11-14 | 2014-11-21 | 2014-11-28 | 2014-12-05 | 2014-12-19 | 2015-01-02 | 2015-01-09 | 2015-01-23 |  | N/A |  | 2015-02-02 | 2015-02-16
UPDATE
ACTUAL
PLANNED | 18 | IFB No. GC/RFQ/012/14/15 | ICT Infracture, Hardware |  |  | 4 Desktop Computers |  | 5000 |  | RFQ | 2014-11-17 | 2014-11-24 | 2014-12-01 | 2014-12-08 | 2014-12-22 | 2015-01-05 | 2015-01-12 | 2015-01-26 |  | N/A |  | 2015-02-03 | 2015-02-17
UPDATE
ACTUAL
PLANNED | 19 | IFB No. GC/RFQ/013/14/15 | Machinery & Other Equipment |  |  | Assorted |  | 5000 |  | RFQ | 2014-11-28 | 2014-12-05 | 2014-12-12 | 2014-12-19 | 2015-01-02 | 2015-01-16 | 2015-01-23 | 2015-02-06 |  | N/A |  | 2015-02-13 | 2015-02-27
UPDATE
ACTUAL
PLANNED | 20 | IFB No. GC/RFQ/014/14/15 | Scholarship/Travel - Foreign |  |  | 2 Plane Tickets |  | 3100 |  | RFQ | 2014-12-01 | 2014-12-08 | 2014-12-15 | 2014-12-22 | 2015-01-05 | 2015-01-19 | 2015-01-26 | 2015-02-09 |  | N/A |  | 2015-02-16 | 2015-03-02
UPDATE
ACTUAL
PLANNED | 21 | IFB No. GC/RFQ/015/14/15 | Repairs & Maintenance - Civil |  |  | 1 Building |  | 8500 |  | RFQ | 2014-09-23 | 2014-09-30 | 2014-10-07 | 2014-10-14 | 2014-10-28 | 2014-11-11 | 2014-11-18 | 2014-12-02 |  | N/A |  | 2015-02-03 | 2015-02-17
UPDATE
ACTUAL
| GRAND TOTAL | [6 empty] | 316616
Prepared by: ___________________________ |  | Date: _____________________ | [5 empty] | Approved by: _______________________ |  |  | 2014-10-07: Date: ____________________
Quoquoi Z. Gayflor Stephen S. Manley
PROCUREMENT DIRECTOR CHAIRMAN PROC. COMMITTEE

## 2014 2015 Service P Plan
GOVERNANCE COMMISSION
DRAFT PROCUREMENT PLAN CORE BUDGET
GOVERNMENT OF LIBERIAL (GoL)
2014/2015
1 | 2 | 3 | 4 | 5 |  |  | 6 |  |  | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
|  | BASIC DATA | [7 empty] | 2014/2015 8: IMPLEMENTATION DATES
[12 empty] | REQUEST FOR EXPRESSION OF INTEREST, if applicable |  |  |  | REQUEST FOR PROPOSALS AND APPROVAL OF AWARD
| ITEM NO. | PACKAGE NUMBER (CODE) | CONTRACT PACKAGE |  | No. of FIRMS/PERSONS |  |  | ESTIMATED COST (USD) | SELECTION METHOD |  | PREP. OF TOR & PC APPROVAL | PUBLICATION OF REOI | REOI CLOSING/ OPENING | SUBMISSION OF EVALUATION REPORT | PC APPROVAL- EVALUATION REPORT/SHORTLIST | PREPARATION & SUBMISSION OF RFP DOCUMENT | PC APPROVAL - FINAL TOR/RFP DOCUMENT | INVITATION OF PROPOSALS | PROPOSAL SUBMISSION & OPENING | SUBMISSION OF TECHNICAL & FINANCIAL EVALUATION REPORT | PC APPROVAL- COMBINED EVALUATION REPORT | CONTRACT AWARD & SIGNING | COMPLETION (FINAL REPORT) AND PAYMENT
PLANNED |  | IFB No. GC/SS/001/14/15 | Scholarship - Local (Training) |  |  | 5 Staff | 5000 |  | SS |  | 2014-11-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2014-12-26 | N/A | 2015-01-09 | 2015-01-06
UPDATE
ACTUAL
| GRAND TOTAL $ | [5 empty] | 5000
Prepared by: ____________________________________ | [6 empty] | Date: ________________________
Quoquoi Z. Gayflor
Procurement Director
Approved by: ___________________________________ | [6 empty] | Date: ________________________
Stephen S. Manley
Executive Director