Name of Entity: INTERNAL AUDIT AGENCY

PROCUREMENT PLAN (Core budget)

Source of Funding: Government of Liberia

Budget Period/Fiscal year: 2014/2015

| 1 | 2 | 3 | 4 |  | 5 |  | 6 |  | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | ITEM NO. | BASIC DATA |  |  |  |  |  |  |  | IMPLEMENTATION DATES |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | REQUEST FOR EXPRESSION OF INTEREST, if applicable |  |  |  | REQUEST FOR PROPOSALS AND APPROVAL OF AWARD |  |  |  |  |  |  |  |
|  |  | PACKAGE NUMBER (CODE) |  | CONTRACT PACKAGE | No. of FIRMS/ PERSONS | ESTIMATED COST (USD) |  | SELECTION METHOD |  | PREP. OF TOR& PC APPROVAL | PUBLICATION OF REOI | REOI CLOSING/ OPENING | SUBMISSION OF EVALUATION REPORT | PC APPROVAL- EVALUATION REPORT/SHORTLIST | PREPARATION & SUBMISSION OF RFP DOCUMENT | PC APPROVAL - FINAL TOR/RFP DOCUMENT | INVITATION OF PROPOSALS | PROPOSAL SUBMISSION & OPENING | SUBMISSION OF TECHNICAL & FINANCIAL EVALUATION REPORT | PC APPROVAL- COMBINED EVALUATION REPORT | CONTRACT AWARD & SIGNING | COMPLETION (FINAL REPORT) AND PAYMENT |
| PLANNED | 1 | IFB No. IAA SS/001/14/15 |  | Audit/ Quality Assurance Consult | 1 | 120,000.00 |  | SS |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | continues |
| UPDATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PLANNED | 2 | IFB No. IAA SS/002/14/15 |  | Audit/ Report Writing Consultant | 1 | 106,020.00 |  | SS |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Continues |
| UPDATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PLANNED | 3 | IFB No. IAA SS/003/14/15 |  | Legal Services Consultant | 1 | 18,000.00 |  | SS |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Retainer |
| UPDATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PLANNED | 4 | IFB No. IAA RFP /001/14/15 |  | Audit /Strategic Writing Consultant | 1 | 60,000.00 |  | RFP |  | 12/19/14 | 12/23/14 | 1/23/15 | 1/30/15 | 2/4/15 | N/A | N/A | N/A | N/A | N/A | N/A | 2/27/15 | Time-Based |
| UPDATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PLANNED | 5 | IFB No. IAA LCS /001/14/15 |  | Accounting Software Consultant | 1 | 6,000.00 |  | LCS |  | 11/27/14 | N/A | 12/4/14 | 12/8/14 | 12/9/14 | N/A | N/A | N/A | N/A | N/A | N/A | 12/11/14 | 12/20/14 |
| UPDATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| GRAND TOTAL |  |  |  |  |  | $310,020.00 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Prepared by: ___________________________________				Approved by:________________________________________	    Date: ________________

Procurement Director/ Manager                                                                                                Head of Entity/Chairman Proc. Committee