Name of Entity: LIBERIA AGENCY FOR COMMUNITY EMPOWERMENT

PROCUREMENT PLAN

LEGISLATURE PROJECT

Budget Period/Fiscal year: 2014/2015

| 1 | 2 | 3 | 4 | 5 |  |  | 6 |  |  | 7 | 8 | 9 |  | 10 | 11 |  | 12 | 13 | 14 | 15 | 16 |  | 17 |  | 18 | 19 | 20 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | ITEM NO. | BASIC DATA |  |  |  |  |  |  |  |  | IMPLEMENTATION DATES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | REQUEST FOR EXPRESSION OF INTEREST, if applicable |  |  |  |  | REQUEST FOR PROPOSALS AND APPROVAL OF AWARD |  |  |  |  |  |  |  |  |  |  |
|  |  | PACKAGE NUMBER (CODE) | CONTRACT PACKAGE |  | No. of FIRMS/PERSONS |  |  | ESTIMATED COST (USD) | SELECTION METHOD |  | PREP. OF TOR& PC APPROVAL |  | PUBLICATION OF REOI | REOI CLOSING/ OPENING |  | SUBMISSION OF EVALUATION REPORT | PC APPROVAL- EVALUATION REPORT/SHORTLIST | PREPARATION & SUBMISSION OF RFP DOCUMENT | PC APPROVAL - FINAL TOR/RFP DOCUMENT | INVITATION OF PROPOSALS |  | PROPOSAL SUBMISSION & OPENING |  | SUBMISSION OF TECHNICAL & FINANCIAL EVALUATION REPORT | PC APPROVAL- COMBINED EVALUATION REPORT | CONTRACT AWARD & SIGNING |  | COMPLETION (FINAL REPORT) AND PAYMENT |
| PLANNED | 1 | IFBNO./LACE/RFQ/001/2014/2015 | Accounting and Auditing Services |  |  | 3 | 4,000.00 |  | LCS |  | 4/10/2015 |  | 4/17/2015 | 4/24/2015 |  | 5/1/2015 | 5/8/2015 | 5/15/2015 | 5/15/2015 | 5/22/2015 |  | 5/29/2015 |  | N/A | 6/5/2015 | 6/12/2015 |  | 6/26/2015 |
| UPDATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| GRAND TOTAL |  |  |  |  |  |  | 4,000.00 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Prepared by: ___________________________________   				Approved by: ________________________________________	    Date: ________________

Kornema Y. Mulbah											Julius K. Sele

Senior Procurement Officer                                                                                                                 		Executive Director

Head of Entity/Chairman Proc. Committee