## Consultancy Service
liberia Extractive Industries Transparency Initiave (LEITI)
Procurement Plan( Core Budget )
Source of Funding: GOL National Budget
Fiscal Period: 2014 - 2015
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
| ITEM NO. | BASIC DATA |  |  |  |  | IMPLEMENTATION DATES
[8 empty] | REQUEST FOR EXPRESSION OF INTEREST, if applicable |  |  |  | REQUEST FOR PROPOSALS AND APPROVAL OF AWARD
|  | PACKAGE NUMBER (CODE) | CONTRACT PACKAGE | No. of FIRMS /PERSONS | ESTIMATED COST (USD) | SELECTION METHOD | PREP. OF TOR& PC APPROVAL | PUBLICATION OF REOI | REOI CLOSING/ OPENING | SUBMISSION OF EVALUATION REPORT | PC APPROVAL- EVALUATION REPORT/SHORTLIST | PREPARATION & SUBMISSION OF RFP DOCUMENT | PC APPROVAL - FINAL TOR/RFP DOCUMENT | INVITATION OF PROPOSALS | PROPOSAL SUBMISSION & OPENING | SUBMISSION OF TECHNICAL & FINANCIAL EVALUATION REPORT | PC APPROVAL- COMBINED EVALUATION REPORT | CONTRACT AWARD & SIGNING | COMPLETION (FINAL REPORT) AND PAYMENT
PLANNED | 1 | RFP No. LEITI/QCBS/001/2014-2015 | EITI Validation (Consultancy Service) | 1 Firm | 75000 | QCBS | 2014-11-08 | 18/8/2014 | 2014-08-09 | 15/9/2014 | 22/9/2014 | 29/9/2014 | 2014-06-10 | 2014-08-10 | 22/10/2014 | 2014-05-11 | 2014-12-11 | 29/1/2015 | 30/6/2015
UPDATE
ACTUAL
GRAND TOTAL |  |  |  |  | 75000
Prepared By: _______________ | [5 empty] | Approved By:__________________________ | [6 empty] | Date________________
|  | HEAD OF PROCUREMENT UNIT |  |  |  | CHAIRMAN, PROCUREMENT COMMITTEE

## Goods, Works & Non-consultancy
Liberia Extractive Industries Transparency Initiative
Procurement Plan (Core Budget)
Source of Funding: GOL National Budget
FISCAL YEAR: 2014-2015
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
.
| ITEM NO. | PACKAGE NUMBER (CODE) | CONTRACT PACKAGE | QTY | ESTIMATED COST (USD) | PROCUREMENT METHOD | TECHNICAL SPECS/BOQ/DRAWINGS | PREP. OF BID DOCUMENT | PC APPROVAL - BID DOC/TECH SPECS | BID INVITATION & RELEASE OF BID DOC | BID SUBMISSION/PUBLIC OPENING | SUBMISSION OF BID EVALUATION REPORT | PC APPROVAL - BID EVALUATION REPORT | CONTRACT AWARD & SIGNING | ADVANCE PAYMENT (MOBILIZATION) | DELIVERY, INSPECTION (SUBSTANTIAL COMPLETION) | ACCEPTANCE & FINAL PAYMENT | REMARKS
PLANNED | 1 | IFB No.LEITI/SS/001/14/15 | Telecommunications( Scratch card & Internet sticks) | 2424 | 12120 | SS | 30/6/2014 | 2014-07-07 | 14/7/2014 | 17/7/2014 | 14/8/2014 | 21/8/2014 | 28/8/2014 | 2015-06-01 | N/A | 30/6/2015 | 30/6/2015
UPDATE
ACTUAL
PLANNED | 2 | IFB No.LEITI/RB/001/14/15 | Fuel & Lub. (Vehicles & Motor Cycles) | 6,729 Gallons @ 4.50 | 30281 | RB | 2014-02-07 | 2014-09-07 | 16/7/2014 | 21/7/2014 | 18/8/2014 | 2014-01-09 | 2014-08-09 | 2015-08-01 | N/A | 16/6/2015 | 30/6/2015
UPDATE
ACTUAL
PLANNED | 3 | IFB No.LEITI/RFQ/001/14/15 | Repairs & Maintenance - Vehicles | 3 | 6000 | RFQ | 28/7/2014 | 2014-04-08 | 2014-11-08 | 18/8/2014 | 26/8/2014 | 2014-02-09 | 2014-09-09 | 2015-12-01 | N/A | 30/6/2015 | 30/6/2015
UPDATE
ACTUAL
PLANNED | 4 | IFB No.LEITI/RFQ/002/14/15 | Repairs & Maintenance - ICT Materials * | Assorted | 4800 | RFQ | 2014-04-08 | 2014-11-08 | 18/8/2014 | 26/8/2014 | 2014-02-09 | 2014-09-09 | 16/9/2014 | 13/1/2015 | N/A | 30/6/2015 | 30/6/2015
UPDATE
ACTUAL
PLANNED | 5 | IFB No.LEITI/RFQ/003/14/15 | Repairs & Maintenance - Motor Cycle | 1 | 1000 | RFQ | 2014-04-08 | 2014-11-08 | 18/8/2014 | 26/8/2014 | 2014-02-09 | 2014-09-09 | 16/9/2014 | 15/1/2015 | N/A | 30/6/2015 | 30/6/2015
UPDATE
ACTUAL
PLANNED | 6 | IFB No.LEITI/NCB/001/14/15 | Stationary * | Assorted | 16000 | NCB | 30/6/2014 | 2014-07-07 | 14/7/2014 | 17/7/2014 | 14/8/2014 | 21/8/2014 | 28/8/2014 | 19/1/2015 | N/A | 17/6/2015 | 30/6/2015
UPDATE
ACTUAL
PLANNED | 7 | IFB No.LEITI/NCB/002/14/15 | Printing & Binding (Printing of EITI 5th Report) | 3013 | 14000 | NCB | 2014-02-07 | 2014-09-07 | 16/7/2014 | 21/7/2014 | 18/8/2014 | 2014-01-09 | 2014-08-09 | 20/1/2015 | N/A | 29/5/2015 | 30/6/2015
UPDATE
ACTUAL
PLANNED | 8 | IFB No.LEITI/NCB/003/14/15 | Advertising and Publication * | Assorted | 28064 | NCB | 2014-07-07 | 14/7/2014 | 21/7/2014 | 23/7/2014 | 20/8/2014 | 2014-03-09 | 2014-10-09 | 21/1/2015 | N/A | 18/6/2015 | 30/6/2015
UPDATE
ACTUAL
PLANNED | 9 | IFB No/LEITI/RFQ/004/2014/215 | Personnel Insurance | 1 Firm | 8640 | RFQ | 2014-10-11 | 17/11/2014 | 24/11/2014 | 2014-01-12 | 2014-08-12 | 15/12/2014 | 22/12/2014 | 22/1/2015 | N/A | 30/6/2015 | 30/6/2015
UPDATE
ACTUAL
PLANNED | 10 | IFB No/LEITI/RFQ/005/2014/2015 | Vehichle Insurance | 1 Firm | 3932 | RFQ | 2014-10-11 | 17/11/2014 | 24/11/2014 | 2014-01-12 | 2014-08-12 | 15/12/2014 | 22/12/2014 | 26/1/2015 | N/A | 30/6/2015 | 30/6/2015
UPDATE
ACTUAL
PLANNED | 12 | NO/LEITI/RFQ/006/2014/2015 | Postage | Assorted | 345 | RFQ | 2014-12-11 | 19/11/2014 | 30/11/2014 | 2014-05-12 | 2014-11-12 | 18/12/2014 | 24/12/2014 | 31/12/2014 | N/A | 30/06/2015 | 30/62015
UPDATE
ACTUAL
PLANNED | 13 | NO.LEITI/RFQ/007/2014/2015 | Internet Wireless | 1 | 1575 | RFQ | 13/11/2014 | 20/11/2014 | 27/11/2014 | 2014-04-12 | 2014-12-12 | 19/12/2014 | 26/12/2014 | 2015-05-01 | N/A | 30/06/2015 | 30/6/2015
UPDATE
ACTUAL
GRAND TOTAL |  |  |  |  | 126757
Prepared By: ________________ |  |  |  |  | Approved By:___________________________ | [7 empty] | Date:__________
|  | HEAD OF PROCUREMENT UNIT |  |  | CHAIRMAN PROCUREMENT COMMITTEE
Explanatory Note
*IFB No.LEITI/RB/001/14/15: It is intended to purchase 6,729 gallons of fuel @ 4.50 per gallon
*IFB No.LEITI/SS/001/14/15: It is intended to purchase Lonestar and Cellcom scratch cards for employees' phones and internet modems recharge: this procurement will be implemented on a lot to lot basis.
Lot 1: Cellcom 11,280@$5.00 & Lot 2: Lonestar 840@ $5.00. The reason for single sourcing is that our staff use only Cellcom and Lonestar phones and internet modems.
*IFB No.LEITI/RFQ/002/14/15: Include the preventive and curative maintenance of laptops, desktop computers, printers and other ICT Equipment
*IFB No/LEITI/NCB/001/2014/2015: Includes reams of sheets, cartridges for printers, envelops, binding clibs, box files, etc
*IFB No/LEITI/NCB/003/14/15: refers to budgetary allocation for the payment of newspaper publications, radio and jingles. Additionally, this contract package includes budget items, publication and advertising and public relations.
* IFB No.LEITI/NCB/RFQ/001/14/15: Inclue the preventive and curative maintenace of vehecles
* /RFQ/006/14/15: It is used to pay charges for mails
*IFB No.LEITI/RFQ/002/14/15: Include the preventive and curative maintenance of laptops, desktop computers, printers and other ICT Equipment
IFB No. LEITI/RFQ/007/14/15: It is intented to pay for thr provision of wireless internet subscription service

## Sheet3
Liberia Extractive Industries Transparency Initiative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Procurement Plan (Core Budget) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Source of Funding: GOL National Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FISCAL YEAR: 2014-2015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | .
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | ITEM NO. | PACKAGE NUMBER (CODE) | CONTRACT PACKAGE | QTY | ESTIMATED COST (USD) | PROCUREMENT METHOD | TECHNICAL SPECS/BOQ/DRAWINGS | PREP. OF BID DOCUMENT | PC APPROVAL - BID DOC/TECH SPECS | BID INVITATION & RELEASE OF BID DOC | BID SUBMISSION/PUBLIC OPENING | SUBMISSION OF BID EVALUATION REPORT | PC APPROVAL - BID EVALUATION REPORT | CONTRACT AWARD & SIGNING | ADVANCE PAYMENT (MOBILIZATION) | DELIVERY, INSPECTION (SUBSTANTIAL COMPLETION) | ACCEPTANCE & FINAL PAYMENT | REMARKS
PLANNED | 1 | IFB No.LEITI/SS/001/14/15 | Telecommunications( Scratch card & Internet sticks) | 2424 | 12120 | SS | 30/6/2014 | 41827 | 14/7/2014 | 17/7/2014 | 14/8/2014 | 21/8/2014 | 28/8/2014 | 42156 | N/A | 30/6/2015 | 30/6/2015 | 0
UPDATE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ACTUAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PLANNED | 2 | IFB No.LEITI/RB/001/14/15 | Fuel & Lub. (Vehicles & Motor Cycles) | 6,729 Gallons @ 4.50 | 30281 | RB | 41677 | 41889 | 16/7/2014 | 21/7/2014 | 18/8/2014 | 41648 | 41860 | 42217 | N/A | 16/6/2015 | 30/6/2015 | 0
UPDATE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ACTUAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PLANNED | 3 | IFB No.LEITI/RFQ/001/14/15 | Repairs & Maintenance - Vehicles | 3 | 6000 | RFQ | 28/7/2014 | 41737 | 41951 | 18/8/2014 | 26/8/2014 | 41679 | 41891 | 42339 | N/A | 30/6/2015 | 30/6/2015 | 0
UPDATE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ACTUAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PLANNED | 4 | IFB No.LEITI/RFQ/002/14/15 | Repairs & Maintenance - ICT Materials * | Assorted | 4800 | RFQ | 41737 | 41951 | 18/8/2014 | 26/8/2014 | 41679 | 41891 | 16/9/2014 | 13/1/2015 | N/A | 30/6/2015 | 30/6/2015 | 0
UPDATE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ACTUAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PLANNED | 5 | IFB No.LEITI/RFQ/003/14/15 | Repairs & Maintenance - Motor Cycle | 1 | 1000 | RFQ | 41737 | 41951 | 18/8/2014 | 26/8/2014 | 41679 | 41891 | 16/9/2014 | 15/1/2015 | N/A | 30/6/2015 | 30/6/2015 | 0
UPDATE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ACTUAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PLANNED | 6 | IFB No.LEITI/NCB/001/14/15 | Stationary * | Assorted | 16000 | NCB | 30/6/2014 | 41827 | 14/7/2014 | 17/7/2014 | 14/8/2014 | 21/8/2014 | 28/8/2014 | 19/1/2015 | N/A | 17/6/2015 | 30/6/2015 | 0
UPDATE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ACTUAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PLANNED | 7 | IFB No.LEITI/NCB/002/14/15 | Printing & Binding (Printing of EITI 5th Report) | 3013 | 14000 | NCB | 41677 | 41889 | 16/7/2014 | 21/7/2014 | 18/8/2014 | 41648 | 41860 | 20/1/2015 | N/A | 29/5/2015 | 30/6/2015 | 0
UPDATE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ACTUAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PLANNED | 8 | IFB No.LEITI/NCB/003/14/15 | Advertising and Publication * | Assorted | 28064 | NCB | 41827 | 14/7/2014 | 21/7/2014 | 23/7/2014 | 20/8/2014 | 41707 | 41921 | 21/1/2015 | N/A | 18/6/2015 | 30/6/2015 | 0
UPDATE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ACTUAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PLANNED | 9 | IFB No/LEITI/RFQ/004/2014/215 | Personnel Insurance | 1 Firm | 8640 | RFQ | 41923 | 17/11/2014 | 24/11/2014 | 41651 | 41863 | 15/12/2014 | 22/12/2014 | 22/1/2015 | N/A | 30/6/2015 | 30/6/2015 | 0
UPDATE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ACTUAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PLANNED | 10 | IFB No/LEITI/RFQ/005/2014/2015 | Vehichle Insurance | 1 Firm | 3932 | RFQ | 41923 | 17/11/2014 | 24/11/2014 | 41651 | 41863 | 15/12/2014 | 22/12/2014 | 26/1/2015 | N/A | 30/6/2015 | 30/6/2015 | 0
UPDATE | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ACTUAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GRAND TOTAL | 0 | 0 | 0 | 0 | 126757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Prepared By: ________________ | 0 | 0 | 0 |  | Approved By:___________________________ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Date:__________ | 0 | 0 | 0 | 0 | 0
0 |  | HEAD OF PROCUREMENT UNIT | 0 | 0 | CHAIRMAN PROCUREMENT COMMITTEE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Explanatory Note | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | *IFB No.LEITI/RB/001/14/15: It is intended to purchase 6,729 gallons of fuel @ 4.50 per gallon | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | *IFB No.LEITI/SS/001/14/15: It is intended to purchase Lonestar and Cellcom scratch cards for employees' phones and internet modems recharge: this procurement will be implemented on a lot to lot basis. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | *IFB No.LEITI/RFQ/002/14/15: Include the preventive and curative maintenance of laptops, desktop computers, printers and other ICT Equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | *IFB No/LEITI/NCB/001/2014/2015: Includes reams of sheets, cartridges for printers, envelops, binding clibs, box files, etc | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | *IFB No/LEITI/NCB/003/14/15: refers to budgetary allocation for the payment of newspaper publications, radio and jingles. Additionally, this contract package includes budget items, publication and advertising and public relations. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | * IFB No.LEITI/NCB/RFQ/001/14/15: Inclue the preventive and curative maintenace of vehecles | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | * /RFQ/006/14/15: It is used to pay charges for mails | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | *IFB No.LEITI/RFQ/002/14/15: Include the preventive and curative maintenance of laptops, desktop computers, printers and other ICT Equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | IFB No. LEITI/RFQ/007/14/15: It is intented to pay for thr provision of wireless internet subscription service | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0