## CONSULTANCY SERVICES PLAN
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
|  | BASIC DATA |  |  |  |  | IMPLEMENTATION DATES
[8 empty] | REQUEST FOR EXPRESSION OF INTEREST, if applicable |  |  |  | REQUEST FOR PROPOSALS AND APPROVAL OF AWARD
| ITEM NO. | PACKAGE NUMBER (CODE) | CONTRACT PACKAGE | No. of FIRMS/PERSONS | ESTIMATED COST (USD) | SELECTION METHOD | PREP. OF TOR & PC APPROVAL | PUBLICATION OF REOI | REOI CLOSING/ OPENING | SUBMISSION OF EVALUATION REPORT | PC APPROVAL- EVALUATION REPORT/SHORTLIST | PREPARATION & SUBMISSION OF RFP DOCUMENT | PC APPROVAL - FINAL TOR/RFP DOCUMENT | INVITATION OF PROPOSALS | PROPOSAL SUBMISSION & OPENING | SUBMISSION OF TECHNICAL & FINANCIAL EVALUATION REPORT | PC APPROVAL- COMBINED EVALUATION REPORT | CONTRACT AWARD & SIGNING | COMPLETION (FINAL REPORT) AND PAYMENT
PLANNED | 1 | RFP No./LRA/CQS/001/014-015 | Fixed Assets System | 1 | 10000 | CQS | 2014-12-15 | 2014-12-22 | 2015-01-12 | 2015-01-19 | 2015-01-26 | 2015-02-09 | 2015-02-16 | 2015-02-23 | 2015-03-23 | 2015-03-30 | 2015-04-06 | 2015-05-04 | 2015-06-30
UPDATE
ACTUAL
PLANNED | 2 | RFP No./LRA/CQS/002/014-015 | GSM Contract Services | 1 | 25000 | CQS | 2014-12-15 | 2014-12-22 | 2015-01-12 | 2015-01-19 | 2015-01-26 | 2015-02-09 | 2015-02-16 | 2015-02-23 | 2015-03-23 | 2015-03-30 | 2015-04-06 | 2015-05-04 | 2015-06-30
UPDATE
ACTUAL
PLANNED | 3 | RFP No./LRA/CQS/003/014-015 | Strategic Planning Contract Services | 1 | 15000 | CQS | 2014-12-15 | 2014-12-22 | 2015-01-12 | 2015-01-19 | 2015-01-26 | 2015-02-09 | 2015-02-16 | 2015-02-23 | 2015-03-23 | 2015-03-30 | 2015-04-06 | 2015-05-04 | 2015-06-30
UPDATE
ACTUAL
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
|  | BASIC DATA |  |  |  |  | 2014-12-15: IMPLEMENTATION DATES
[8 empty] | REQUEST FOR EXPRESSION OF INTEREST, if applicable |  |  |  | REQUEST FOR PROPOSALS AND APPROVAL OF AWARD
| ITEM NO. | PACKAGE NUMBER (CODE) | CONTRACT PACKAGE | No. of FIRMS/PERSONS | ESTIMATED COST (USD) | SELECTION METHOD | PREP. OF TOR & PC APPROVAL | PUBLICATION OF REOI | REOI CLOSING/ OPENING | SUBMISSION OF EVALUATION REPORT | PC APPROVAL- EVALUATION REPORT/SHORTLIST | PREPARATION & SUBMISSION OF RFP DOCUMENT | PC APPROVAL - FINAL TOR/RFP DOCUMENT | INVITATION OF PROPOSALS | PROPOSAL SUBMISSION & OPENING | SUBMISSION OF TECHNICAL & FINANCIAL EVALUATION REPORT | PC APPROVAL- COMBINED EVALUATION REPORT | CONTRACT AWARD & SIGNING | COMPLETION (FINAL REPORT) AND PAYMENT
PLANNED | 4 | RFP No./LRA/CQS/004/014-015 | Insurance Sector Contract Services | 1 | 14000 | CQS | 2014-12-15 | 2014-12-22 | 2015-01-12 | 2015-01-19 | 2015-01-26 | 2015-02-09 | 2015-02-16 | 2015-02-23 | 2015-03-23 | 2015-03-30 | 2015-04-06 | 2015-05-04 | 2015-06-30
UPDATE
ACTUAL
PLANNED | 4 | RFP No./LRA/CQS/005/014-015 | Mining Sector Contract Services | 1 | 15000 | CQS | 2014-12-15 | 2014-12-22 | 2015-01-12 | 2015-01-19 | 2015-01-26 | 2015-02-09 | 2015-02-16 | 2015-02-23 | 2015-03-23 | 2015-03-30 | 2015-04-06 | 2015-05-04 | 2015-06-30
UPDATE
ACTUAL
GRAND TOTAL |  |  |  |  | 79000
Prepared by: ________________________ | [6 empty] | 2015-01-12: Approved: ___________________________
HEAD OF PROCUREMENT UNIT | [6 empty] | 2015-01-12: CHAIRMAN-PROCUREMENT COMMITTEE

## NOTES TO PLAN
Notes to Procurement Plan
Item | Contract Package | Description
1 | Fixed Assets System | Hiring an individual to setup & implement the asset management system and train staff to use and manage the system
2 | GSM Contract Services | Hiring a subject matter expert to train staff on revenue related technical intricacies of the sector and help develop related enforcement strategies
3 | Strategic Planning Contract Services | Hiring a local consultant to develop LRA medium term(5 years) Strategic Plan
4 | Insurance Sector Contract Services | Hiring a subject matter expert to develop LRA revenue growth Strategy for the Insurance Sector
5 | Mining Sector Contract Services | Hiring a subject matter expert to train staff on revenue related technical intricacies of the sector and help develop related enforcement strategies