## Core Budget FINAL(3)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
|  | BASIC DATA |  |  |  |  | IMPLEMENTATION DATES
| Item No. | Package Number (code) | Contract Package | Qty | Estimated Cost (USD) | Procurement Method | Technical Specs/BOQ/Drawings | Prep. of Bid Document | PC Approval- Bid Doc./Tech. Specs. | Bid Invitation & Release of Bid Doc. | Bid submission/Public Opening | Submission of Bid Evaluation Report | PC Approval-Bid Evaluation Report | Contract Award & Signing | Advance Payment (Mobilization) | Delivery, Inspection (Substantial completion) | Acceptance & Final Payment | REMARKS
Planned | 1 | IFB No.LRA/NCB/001/014-015 | Stationery & Office Supplies | Assorted | 283723 | NCB | 2014-11-10 | 2014-11-17 | 2014-11-24 | 2014-11-27 | 2014-12-25 | 2015-01-01 | 2015-01-08 | 2015-01-22 | N/A | 2015-06-30 | 2015-06-30 | See note 1 annex 1
Update
Act.
Planned | 2 | IFB No.LRA/RB/001/014-015 | Fuel and Lubricant (for vehicle, Bikes & Generators) | 146,196 gls | 520461 | RB | 2014-11-10 | 2014-11-17 | 2014-11-24 | 2014-11-27 | 2014-12-25 | 2015-01-08 | 2015-01-15 | 2015-02-05 | N/A | 2015-06-30 | 2015-06-30 | See note 2 annex 1
Update
Act.
Planned | 3 | IFB No.LRA/NCB/002/014-015 | Uniforms & Specialized Clothing | Assorted | 265000 | NCB | 2014-11-11 | 2014-11-18 | 2014-11-25 | 2014-11-28 | 2014-12-26 | 2015-01-02 | 2015-01-09 | 2015-01-23 | 2015-02-06 | 2015-02-20 | 2015-03-20 | See note 3 annex 1
Update
Act.
Planned | 4 | IFB No.LRA/NCB/003/014-015 | Personnel Insurance | Assorted | 195860 | NCB | 2014-11-11 | 2014-11-18 | 2014-11-25 | 2014-11-28 | 2014-12-26 | 2015-01-02 | 2015-01-09 | 2015-01-23 | N/A | 2015-06-30 | 2014-06-30 | See note 4 annex 1
Update
Act.
Planned | 5 | IFB No.LRA/RB/002/014-015 | *Revenue Instrument | Assorted | 10000 | RB | 2014-11-11 | 2014-11-18 | 2014-11-25 | 2014-11-28 | 2014-12-26 | 2015-01-02 | 2015-01-09 | 2015-01-23 | N/A | 2015-02-06 | 2015-03-06 | See note 5 annex 1
Update
Act.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
|  | BASIC DATA |  |  |  |  | 2014-11-11: IMPLEMENTATION DATES
| Item No. | Package Number (code) | Contract Package | Qty | Estimated Cost (USD) | Procurement Method | Technical Specs/BOQ/Drawings | Prep. of Bid Document | PC Approval- Bid Doc./Tech. Specs. | Bid Invitation & Release of Bid Doc. | Bid submission/Public Opening | Submission of Bid Evaluation Report | PC Approval-Bid Evaluation Report | Contract Award & Signing | Advance Payment (Mobilization) | Delivery, Inspection (Substantial completion) | Acceptance & Final Payment | REMARKS
Planned | 6 | IFB No.LRA/NCB/004/014-015 | Transport Equipment(Motor Bikes) | 36 | 40000 | NCB | 2014-11-09 | 2014-11-16 | 2014-11-23 | 2014-11-26 | 2014-12-24 | 2014-12-31 | 2015-01-07 | 2015-01-21 | N/A | 2015-02-04 | 2015-03-04 | See note 6 annex 1
Update
Act.
Planned | 7 | IFB No.LRA/NCB/005/014-015 | Printing & Publication Services | Assorted | 60000 | NCB | 2014-10-24 | 2014-10-31 | 2014-11-07 | 2014-11-10 | 2014-12-08 | 2014-12-15 | 2014-12-22 | 2015-01-05 | N/A | 2015-01-19 | 2015-02-16 | See note 7 annex 1
Update
Act.
Planned | 8 | IFB No.LRA/NCB/006/014-015 | *Miscellaneous Office Equipment | Assorted | 80000 | NCB | 2014-10-24 | 2014-10-31 | 2014-11-07 | 2014-11-10 | 2014-12-08 | 2014-12-15 | 2014-12-22 | 2015-01-05 | N/A | 2015-01-19 | 2015-02-16 | See note 8 annex 1
Update
Act.
Planned | 9 | IFB No.LRA/NCB/007/014-015 | Foreign Means of Travel (Air Ticket) | various | 70000 | NCB | 2014-10-25 | 2014-11-01 | 2014-11-08 | 2014-11-11 | 2014-12-09 | 2014-12-16 | 2014-12-23 | 2015-01-06 | N/A | 2015-06-30 | 2015-06-30 | See note 9 annex 1
Update
Act.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
|  | BASIC DATA |  |  |  |  | 2014-10-25: IMPLEMENTATION DATES
| Item No. | Package Number (code) | Contract Package | Qty | Estimated Cost (USD) | Procurement Method | Technical Specs/BOQ/Drawings | Prep. of Bid Document | PC Approval- Bid Doc./Tech. Specs. | Bid Invitation & Release of Bid Doc. | Bid submission/Public Opening | Submission of Bid Evaluation Report | PC Approval-Bid Evaluation Report | Contract Award & Signing | Advance Payment (Mobilization) | Delivery, Inspection (Substantial completion) | Acceptance & Final Payment | REMARKS
Planned | 10 | IFB No.LRA/NCB/008/014-015 | Cleaning Material | Assorted | 46000 | NCB | 2014-10-24 | 2014-10-31 | 2014-11-07 | 2014-11-10 | 2014-12-08 | 2014-12-15 | 2014-12-22 | 2015-01-05 | N/A | 2015-01-19 | 2015-02-16 | See note 10 annex 1
Update
Act.
Planned | 11 | IFB No.LRA/RFQ/001/014-015 | Domestic Means of Travel | 36 | 5000 | RFQ | 2014-11-13 | 2014-11-20 | 2014-11-27 | 2014-12-04 | 2014-12-18 | 2014-12-25 | 2015-01-01 | 2015-01-08 | N/A | 2015-01-15 | 2015-01-29 | See note 11 annex 1
Update
Act.
Planned | 12 | IFB No.LRA/NCB/009/014-015 | Repair & Maint. Vehicles & Bikes | 66 vehicles, 93 Bikes | 70770 | NCB | 2014-10-24 | 2014-10-31 | 2014-11-07 | 2014-11-10 | 2014-12-08 | 2014-12-15 | 2014-12-22 | 2015-01-05 | N/A | 2015-06-30 | 2015-06-30 | See note 12 annex 1
Update
Act.
Planned | 13 | IFB No.LRA/RB/003/014-015 | Telecommunication, Internet, Postage & Courier | Assorted | 216096 | RB | 2014-10-24 | 2014-10-31 | 2014-11-07 | 2014-11-10 | 2014-12-08 | 2014-12-15 | 2014-12-22 | 2015-01-12 | N/A | 2015-06-30 | 2015-06-30 | See note 13 annex 1
Update
Act.
Planned | 14 | IFB No.LRA/SS/001/014-015 | *Repair & Maint. Property ( civil works) | 5 | 104000 | SS | 2014-10-20 | 2014-11-10 | 2014-11-24 | 2014-12-01 | 2014-12-29 | 2015-01-12 | 2015-01-26 | 2015-02-23 | 2015-03-09 | 2015-06-30 | 2015-06-30 | See note 14 annex 1
Update
Act.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
|  | BASIC DATA |  |  |  |  | 2014-10-24: IMPLEMENTATION DATES
| Item No. | Package Number (code) | Contract Package | Qty | Estimated Cost (USD) | Procurement Method | Technical Specs/BOQ/Drawings | Prep. of Bid Document | PC Approval- Bid Doc./Tech. Specs. | Bid Invitation & Release of Bid Doc. | Bid submission/Public Opening | Submission of Bid Evaluation Report | PC Approval-Bid Evaluation Report | Contract Award & Signing | Advance Payment (Mobilization) | Delivery, Inspection (Substantial completion) | Acceptance & Final Payment | REMARKS
Planned | 15 | IFB No.LRA/NCB/010/014-015 | Repair & Maint. Generators | 35 est. | 32100 | NCB | 2014-10-24 | 2014-11-14 | 2014-11-28 | 2014-12-05 | 2015-01-02 | 2015-01-16 | 2015-01-30 | 2015-02-27 | N/A | 2015-06-30 | 2015-06-30 | See note 15 annex 1
Update
Act.
Planned | 16 | IFB No.LRA/NCB/011/014-015 | Revenue Forms | various | 22000 | NCB | 2014-10-25 | 2014-11-08 | 2014-11-22 | 2014-11-26 | 2014-12-24 | 2015-01-07 | 2015-01-14 | 2015-02-18 | N/A | 2015-04-01 | 2015-05-27 | See note 16 annex 1
Update
Act.
Planned | 17 | IFB No.LRA/SS/002/014-015 | Elevator Maintenance | 1 firm | 24358 | SS | 2014-09-22 | 2014-10-06 | 2014-10-20 | 2014-10-24 | 2014-11-21 | 2014-12-05 | 2014-12-12 | 2015-01-16 | N/A | 2015-06-30 | 2015-06-30 | See note 17 annex 1
Update
Act.
Planned | 18 | IFB No.LRA/SS/003/014-015 | Central Cooling System Maintance | 1 firm | 30000 | SS | 2014-09-23 | 2014-10-07 | 2014-10-21 | 2014-10-25 | 2014-11-22 | 2014-12-06 | 2014-12-13 | 2015-01-17 | N/A | 2015-06-30 | 2015-06-30 | See note 18 annex 1
Update
Act.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
|  | BASIC DATA |  |  |  |  | 2014-09-23: IMPLEMENTATION DATES
| Item No. | Package Number (code) | Contract Package | Qty | Estimated Cost (USD) | Procurement Method | Technical Specs/BOQ/Drawings | Prep. of Bid Document | PC Approval- Bid Doc./Tech. Specs. | Bid Invitation & Release of Bid Doc. | Bid submission/Public Opening | Submission of Bid Evaluation Report | PC Approval-Bid Evaluation Report | Contract Award & Signing | Advance Payment (Mobilization) | Delivery, Inspection (Substantial completion) | Acceptance & Final Payment | REMARKS
Planned | 19 | IFB No.LRA/NCB/012/014-015 | Security Service | 1 firm | 183000 | NCB | 2014-09-18 | 2014-10-02 | 2014-10-16 | 2014-10-20 | 2014-11-17 | 2014-12-01 | 2014-12-08 | 2015-01-12 | N/A | 2015-06-30 | 2015-06-30 | See note 19 annex 2
Update
Act.
Planned | 20 | IFB No.LRA/NCB/013/014-015 | Janitorial Service | 1 firm | 81600 | NCB | 2014-09-19 | 2014-10-03 | 2014-10-17 | 2014-10-21 | 2014-11-18 | 2014-12-02 | 2014-12-09 | 2015-01-13 | N/A | 2015-06-30 | 2015-06-30 | See note 20 annex 2
Update
Act.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
|  | BASIC DATA |  |  |  |  | 2014-09-19: IMPLEMENTATION DATES
| Item No. | Package Number (code) | Contract Package | Qty | Estimated Cost (USD) | Procurement Method | Technical Specs/BOQ/Drawings | Prep. of Bid Document | PC Approval- Bid Doc./Tech. Specs. | Bid Invitation & Release of Bid Doc. | Bid submission/Public Opening | Submission of Bid Evaluation Report | PC Approval-Bid Evaluation Report | Contract Award & Signing | Advance Payment (Mobilization) | Delivery, Inspection (Substantial completion) | Acceptance & Final Payment | REMARKS
Planned | 21 | IFB No.LRA/SS/004/014-015 | ICT Infrastructure (Asycuda License) | 1 | 30100 | SS | 2014-09-23 | 2014-10-07 | 2014-10-21 | 2014-10-25 | 2014-11-22 | 2014-12-06 | 2014-12-13 | 2015-01-17 | N/A | 2015-02-28 | 2015-04-25 | See note 21 annex 2
Update
Act.
Planned | 22 | IFB No.LRA/NCB/014/014-015 | Vehicles Insurance | 66 | 12853 | NCB | 2014-12-19 | 2015-01-02 | 2015-01-16 | 2015-01-20 | 2015-02-17 | 2015-03-03 | 2015-03-10 | 2015-04-14 | N/A | 2015-06-30 | 2015-06-30 | See note 22 annex 2
Update
Act.
Planned | 23 | IFB No.LRA/NCB/015/014-015 | *Repair & Maint. of Equipment | Assorted | 27000 | NCB | 2014-12-19 | 2015-01-02 | 2015-01-16 | 2015-01-20 | 2015-02-17 | 2015-03-03 | 2015-03-10 | 2015-04-14 | N/A | 2015-06-30 | 2015-06-30 | See note 23 annex 2
Update
Act.
Planned | 24 | IFB No.LRA/NCB/016/014-015 | Vehicles | 4 | 54000 | NCB | 2014-12-19 | 2015-01-02 | 2015-01-16 | 2015-01-20 | 2015-02-17 | 2015-03-03 | 2015-03-10 | 2015-04-14 | N/A | 2015-06-30 | 2015-06-30 | See note 24 annex 2
Update
Act.
Grand Total: |  |  |  |  | 2463921
Prepared by: ________________________ | [6 empty] | 2015-01-02: Approved: ___________________________; 2015-03-10: Date:_________________________________
HEAD of PROCUREMENT UNIT | [6 empty] | 2015-01-02: CHAIRMAN-PROCUREMENT COMMITTEE
Formulas:
Advance Payment (Mobilization) = [Contract Award & Signing]+14
Note on D4: plus miscellaneous office equipment
Note on D16: user: will be done in lots *receipts *seals & stamp *ID card & P. licesense
Note on D22: Bike
Note on D28: *Television, refrigerator, microwave, laminating machine, Fire Extinguisher
Note on O7: user: time include *Intent to award to PPCC *MOF & Justice
Note on O10: user: time include *Intent to award to PPCC *MOF & Justice
Note on O13: user: time include *Intent to award to PPCC *MOF & Justice
Note on O16: user: time include *Intent to award to PPCC *MOF & Justice
Note on O48: user: time include *Intent to award to PPCC *MOF & Justice

## Note FINAL (3)
Notes to Procurement Plan
Item | Contract Package | Description
1 | Stationery & Office Supplies | Envelopes, pens, pencils, papers, cartridges, etc. Business Cards @ US $24,000, Letter Heads @ US $35,000, Seals & Stamps @ US $5,000
2 | Fuel and Lubricant (for vehicle, Bikes & Generators) | Estimated 146,186 gallons of Diesel Fuel and Gasoline for LRA operations
3 | Uniforms & Specialized Clothing | Uniform for Customs & Tax staff including T-Shirts, caps, jackets, seals, name plates, ties and four sets Jerseys for LRA four teams
4 | Personnel Insurance | Insurance coverage for LRA employees and dependents: medical coverage for staff & dependents and life coverage for staff only
5 | *Revenue Instrument | Revenue Notary Stamps funded under the budget line: other office materials & consumables/notary seals and forms
6 | Transport Equipment(Motor Bikes) | Procurement of 36 motor bikes for out station staffs
7 | Printing & Publication services | Website Hosting annual subscription fees @ US $3,000. Printing and binding of Brochures, Tariff & Tax code, professional documents, annual report, strategic plan, etc.
8 | *Miscellaneous Office Equipment | Though the threshold requires NCB method , RFQ method may be used for some items given the variety of items being procured which include Fire Extinguisher, Artificial Flowers, Potraits, Sofas, Televisions, Office Size Refrigerators, Internet Modems/Routers, Binders, Shredders, Laminating Machines, Cutters, etc.
9 | Foreign Means of Travel | Airline tickets costs for estimated 30 trips of official foreign travel
10 | Cleaning Materials | Soap, clorox, towels, soft brooms, tissue, air freshener, floor mops, etc.
11 | Domestic Means of Travel | Transportation cost/fares to facilitate staff traveling to and from various Counties
12 | Repair & Maint. Vehicles & Bikes | Spare parts for vehicles & motor bikes including services
13 | Telecommunication, Internet, Postage & Courier | Scratch Cards (14,280pcs) @ US $71,400 for the year, Office Phones, Caller Users Group (CUG) for estimated 868 staff @ US $72,972 , prepaid lines for staffs & internet modems/routers for 28 Customs & Tax Business Offices @ US $25,032 and Courier Services @ US $4,500
14 | *Repair & Maint. Property ( civil works) | Modification works at LRA HQ for additional offices, bath room(s) and doorways by General Services Agency (GSA). Also, general repairs & maintenance of LRA properties
15 | Repair & Maint. Generators | Preventive maintenance & repairs service contract, spare parts & supplies for generators at HQ, Customs & Tax Offices
16 | *Revenue Forms | Production and printing of various Revenue Forms. This is funded under the budget line Other Office Materials & Consumables/notary seals and forms
17 | Elevator Maintenance | Maintenance service contract with company that supplied and installed the elevators at HQ. This include spare parts for the two elevators. This is funded under PROFESSIONAL SERVICES.
18 | Central Cooling System Maintenance | Maintenance service contract with the company that supplied and installed the cooling system at HQ. This include spare parts for the system. This is funded under PROFESSIONAL SERVICES.
19 | Security Service | Provision of Security Guard Services at HQ and other offices. This is funded under PROFESSIONAL SERVICES.
20 | Janitorial Service | Provision of Janitorial Services at HQ and other offices. This is funded under PROFESSIONAL SERVICES.
21 | *ICT Infrastructure (Asycuda License) | Procurement of Soclass License for Asycuda System using Sole Source method.
22 | Vehicles Insurance | Provision of third party insurance coverage for LRA fleet
23 | *Repair & Maint. of Equipment | Procurement of spare parts including server hard disks, external hard drives, mouse adoptors, etc. and regular servicing. Based on the threshold, the contract package requires NCB Method but realistically, RFQ Method will be used to procure these items given that repairs are required at different locations, at different time, with different IT materials and the potential difficulties. Also, the values of these items are usually within the RFQ threshold at the time of need.
24 | Vehicles | Procurement of four vehicles for operations. This is funded under the budget line Transport Equipment
25 | ID Cards | Provision of Provisional & Reqular ID Cards to LRA Staff by others & Civil Service Agency (CSA)
26 | Office Buildings Rental & Leases | Annual lease/rental of Customs & Tax Offices, additional office space at ELWA junction and warehouse to store LRA furniture procured under IPFMRP (World Bank).
27 | Vehicle & Bike Registration | Registration of about 66 vehicles and 93 Bikes
28 | Electricity | Power supply by LEC including connection to LEC grid and the procurement of solar panels for night lighting
29 | Water & Sewage | Water supply by LWSC including connection to main line
30 | Newspapers, Books & Specialized Publications | Payment for advertisements , press releases, newsletters, newspapers, etc.
31 | Entertainment, Representation & Gifts | Cost of hosting international guests, stakeholder meetings, outreach programs & gifts. Meetings will be held at different times, posibly in different locations locally.
32 | Asset Management System Software | Acquiring Asset Management System Software @10,000. This is funded under budget line Professional Services
33 | Tax Education | Tax & LRA sensitization messages on brochures, stickers, banners, fliers, walls, billboards, etc. Talk shows (studio discussions & call-in), airing of tax jingles & songs on various radio stations, airing of various dramatized tax messages on various radios & TV stations, text messages as reminder for tax filing and payment date, town hall meetings, tax clinics & outreach in various counties on different tax issues, honoring of taxpayers for tax compliance, etc.
34 | Board Fees & Management | Quarterly & other payments to Non-Statutory Board Members including communication, laptops etc.
35 | Local Training | Trainings & Certification of LRA staff. Also testing in some cases
36 | Foreign Training | Trainings & Certification of LRA staff
37 | Transferred Staff Placement | Management of transferred staff placement within the LRA. Activities will take place in all counties. This is funded under Professional Services