## Consultancy Service
Ministry of Finance & Development Planning
Procurement Plan
Core Budget
Fiscal Period: 2014 - 2015
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
| ITEM NO. | BASIC DATA |  |  |  |  | IMPLEMENTATION DATES
[8 empty] | REQUEST FOR EXPRESSION OF INTEREST, if applicable |  |  |  | REQUEST FOR PROPOSALS AND APPROVAL OF AWARD
|  | PACKAGE NUMBER (CODE) | CONTRACT PACKAGE | No. of FIRMS /PERSONS | ESTIMATED COST (USD) | SELECTION METHOD | PREP. OF TOR& PC APPROVAL | PUBLICATION OF REOI | REOI CLOSING/ OPENING | SUBMISSION OF EVALUATION REPORT | PC APPROVAL- EVALUATION REPORT/SHORTLIST | PREPARATION & SUBMISSION OF RFP DOCUMENT | PC APPROVAL - FINAL TOR/RFP DOCUMENT | INVITATION OF PROPOSALS | PROPOSAL SUBMISSION & OPENING | SUBMISSION OF TECHNICAL & FINANCIAL EVALUATION REPORT | PC APPROVAL- COMBINED EVALUATION REPORT | CONTRACT AWARD & SIGNING | COMPLETION (FINAL REPORT) AND PAYMENT
PLANNED | 1
UPDATE
ACTUAL
PLANNED | 2
UPDATE
ACTUAL
PLANNED | 3
UPDATE
ACTUAL
GRAND TOTAL

## Goods, Works & Non-consultancy
Ministry of Finance and Development Planning
Procurement Plan (Core Budget)
GOL National Budget
Fiscal Year: 2014 - 2015
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
l | BASIC DATA | [5 empty] | IMPLEMENTATION DATES | [10 empty] | .
| ITEM NO. | PACKAGE NUMBER (CODE) | CONTRACT PACKAGE | QTY | ESTIMATED COST (USD) | PROCUREMENT METHOD | TECHNICAL SPECS/BOQ/DRAWINGS | PREP. OF BID DOCUMENT | PC APPROVAL - BID DOC/TECH SPECS | BID INVITATION & RELEASE OF BID DOC | BID SUBMISSION/PUBLIC OPENING | SUBMISSION OF BID EVALUATION REPORT | PC APPROVAL - BID EVALUATION REPORT | CONTRACT AWARD & SIGNING | ADVANCE PAYMENT (MOBILIZATION) | DELIVERY, INSPECTION (SUBSTANTIAL COMPLETION) | ACCEPTANCE & FINAL PAYMENT | REMARKS
PLANNED | 1 | IFB No. MFDP/RB/001/14-15 | Fuel & Lubricants (Generator & Vehicles) | 183,275 gallons | 780750 | RB | 2014-10-30 | 2014-11-06 | 2014-11-13 | 2014-11-20 | 2014-12-18 | 2015-01-01 | 2015-01-08 | 2015-02-05 | N/A | 2015-06-10 | 2015-06-30
UPDATE
ACTUAL
PLANNED | 2 | IFB No. MFDP/NCB/001/14-15 | Stationery & Supplies | Assorted | 216500 | NCB | 2014-10-30 | 2014-11-06 | 2014-11-13 | 2014-11-20 | 2014-12-18 | 2015-01-01 | 2015-01-08 | 2015-01-29 | N/A | 2015-06-30 | 2015-06-30
UPDATE
ACTUAL
PLANNED | 3 | IFB No. MFDP/NCB/002/14-15 | Clearning Materials | Assorted | 29000 | NCB | 2014-10-30 | 2014-11-06 | 2014-11-13 | 2014-11-20 | 2014-12-18 | 2015-01-01 | 2015-01-08 | 2015-01-29 | N/A | 2015-06-30 | 2015-06-30
UPDATE
ACTUAL
PLANNED | 4 | IFB No. MFDP/RFQ/001/14-15 | Fumigation Services | 1 Firm | 7000 | RFQ | 2014-11-17 | 2014-11-24 | 2014-12-01 | 2014-12-03 | 2014-12-10 | 2014-12-17 | 2014-12-24 | 2014-12-31 | N/A | 2015-03-30 | 2015-04-28
UPDATE
ACTUAL
PLANNED | 5 | IFB No. MFDP/RFQ/002/14-15 | Employees ID Card | 600 | 6000 | RFQ | 2014-12-10 | 2014-12-17 | 2014-12-24 | 2014-12-26 | 2015-01-02 | 2015-01-09 | 2015-01-16 | 2015-01-23 | N/A | 2015-02-25 | 2015-03-25
UPDATE
ACTUAL
PLANNED | 6 | IFB No. MFDP/NCB/003/14-15 | Vehicle Insurance Services | 55 Vehicles | 41950 | NCB | 2014-11-06 | 2014-11-13 | 2014-11-20 | 2014-11-27 | 2014-12-25 | 2015-01-08 | 2015-01-15 | 2015-02-05 | N/A | 2015-06-30 | 2015-06-30
UPDATE
ACTUAL
PLANNED | 7 | IFB No. MFDP/NCB/004/14-15 | Personnel Insurance Service | 1 Firm | 85248 | NCB | 2014-10-06 | 2014-10-13 | 2014-10-20 | 2014-10-27 | 2014-11-24 | 2014-12-08 | 2014-12-15 | 2015-01-05 | N/A | 2015-06-30 | 2015-06-30
UPDATE
ACTUAL
PLANNED | 8 | IFB No. MFDP/NCB/005/14-15 | Printing & Binding Services | Assorted | 297550 | NCB | 2014-11-03 | 2014-11-10 | 2014-11-17 | 2014-11-24 | 2014-12-22 | 2015-01-05 | 2015-01-12 | 2015-02-02 | N/A | 2015-06-10 | 2015-06-30
UPDATE
ACTUAL
PLANNED | 9 | IFB No. MFDP/NCB/006/14-15 | Repairs and Maintenance (Civil) | 1 Building | 150000 | NCB | 2015-01-06 | 2015-01-13 | 2015-01-20 | 2015-01-27 | 2015-02-24 | 2015-03-10 | 2015-03-17 | 2015-04-07 | N/A | 2015-06-30 | 2015-06-30
UPDATE
ACTUAL
PLANNED | 10 | IFB No. MFDP/NCB/007/14-15 | Repairs and Maintenance (Vehicles) | 65 Vehicles | 186000 | NCB | 2014-11-10 | 2014-11-17 | 2014-11-24 | 2014-12-01 | 2014-12-29 | 2015-01-12 | 2015-01-19 | 2015-02-09 | N/A | 2015-06-30 | 2015-06-30
UPDATE
ACTUAL
PLANNED | 11 | IFB No. MFDP/SS/001/14-15 | Repair and Maintenance (Generator) | 1 | 12000 | SS | 2014-09-08 | 2014-09-15 | 2014-09-22 | 2014-09-29 | 2014-10-27 | 2014-11-10 | 2014-11-17 | 2014-12-08 | N/A | 2015-06-30 | 2015-06-30
UPDATE
ACTUAL
PLANNED | 12 | IFB No. MFDP/NCB/008/14-15 | Repair and Maintenance (Mach, Equip & Furniture) | Assorted | 65400 | NCB | 2014-09-16 | 2014-09-23 | 2014-09-30 | 2014-10-07 | 2014-11-04 | 2014-11-18 | 2014-11-25 | 2014-12-16 | N/A | 2015-06-30 | 2015-06-30
UPDATE
ACTUAL
PLANNED | 13 | IFB No. MFDP/NCB/009/14-15 | Machinery & Other Equipment | Assorted | 110000 | NCB | 2014-11-06 | 2014-11-13 | 2014-11-20 | 2014-11-27 | 2014-12-25 | 2015-01-08 | 2015-01-15 | 2015-02-05 | N/A | 2015-06-30 | 2015-06-30
UPDATE
PLANNED | 14 | IFB No. MFDP/NCB/010/14-15 | ICT Infrastructure | Assorted | 71380 | NCB | 2014-12-15 | 2014-12-22 | 2014-12-29 | 2015-01-05 | 2015-02-02 | 2015-02-16 | 2015-02-23 | 2015-03-16 | N/A | 2015-06-30 | 2015-06-30
UPDATE
ACTUAL
PLANNED | 15 | IFB No. MFDP/NCB/011/14-15 | Maintenance of Budget Software | Assorted | 44320 | NCB | 2014-09-23 | 2014-09-30 | 2014-10-07 | 2014-10-14 | 2014-11-11 | 2014-11-25 | 2014-12-02 | 2014-12-23 | N/A | 2015-06-30 | 2015-06-30
UPDATE
ACTUAL
PLANNED | 16 | IFB No. MFDP/SS/002/14-15 | Video Conferencing | 1 Firm | 32500 | SS | 2014-10-15 | 2014-10-22 | 2014-10-29 | 2014-11-05 | 2014-12-03 | 2014-12-17 | 2014-12-24 | 2015-01-14 | N/A | 2015-06-10 | 2015-06-30
UPDATE
ACTUAL
PLANNED | 17 | IFB No. MFDP/NCB/012/14-15 | Furniture & Fixtures | Assorted | 62500 | NCB | 2014-12-18 | 2014-12-25 | 2015-01-01 | 2015-01-08 | 2015-02-05 | 2015-02-19 | 2015-02-26 | 2015-03-19 | N/A | 2015-06-30 | 2015-06-30
UPDATE
ACTUAL
PLANNED | 18 | IFB No. MFDP/NCB/013/14-15 | Food & Catering Services | Assorted | 140418 | NCB | 2014-11-06 | 2014-11-13 | 2014-11-20 | 2014-11-27 | 2014-12-25 | 2015-01-08 | 2015-01-15 | 2015-02-05 | N/A | 2015-06-30 | 2015-06-30
UPDATE
ACTUAL
PLANNED | 19 | IFB No. MFDP/NCB/014/14-15 | Hall Rental | Assorted | 30000 | NCB | 2014-11-26 | 2014-12-03 | 2014-12-10 | 2014-12-17 | 2015-01-14 | 2015-01-28 | 2015-02-04 | 2015-02-25 | N/A | 2015-06-30 | 2015-06-30
UPDATE
ACTUAL
| 20 | IFB No. MFDP/NCB/015/14-15 | Public Address (PA) Systems Rental | Assorted | 12500 | NCB | 2014-09-01 | 2014-09-08 | 2014-09-15 | 2014-09-22 | 2014-10-20 | 2014-11-03 | 2014-11-10 | 2014-12-01 | N/A | 2015-06-30 | 2015-06-30
UPDATE
ACTUAL
PLANNED | 21 | IFB No. MFDP/NCB/016/14-15 | Entertainment | Assorted | 57600 | NCB | 2014-12-01 | 2014-12-08 | 2014-12-15 | 2014-12-22 | 2015-01-19 | 2015-02-02 | 2015-02-09 | 2015-03-02 | N/A | 2015-06-30 | 2015-06-30
UPDATE
ACTUAL
PLANNED | 22 | IFB No. MFDP/SS/003/14-15 | Internet Services | 1 firm | 90000 | SS | 2014-09-01 | 2014-09-08 | 2014-09-15 | 2014-09-22 | 2014-10-20 | 2014-11-03 | 2014-11-10 | 2014-12-01 | N/A | 2015-06-30 | 2015-06-30
UPDATE
ACTUAL
PLANNED | 23 | IFB No. MFDP/NCB/017/14-15 | Scratch Cards | 25,320 Pcs | 126600 | NCB | 2014-10-30 | 2014-11-06 | 2014-11-13 | 2014-11-20 | 2014-12-18 | 2015-01-01 | 2015-01-08 | 2015-01-29 | N/A | 2015-06-30 | 2015-06-30
UPDATE
ACTUAL
PLANNED | 24 | IFB No. MFDP/NCB/018/14-15 | Air Tickets | Assorted | 131000 | NCB | 2014-11-24 | 2014-12-01 | 2014-12-08 | 2014-12-15 | 2015-01-12 | 2015-01-26 | 2015-02-02 | 2015-02-23 | N/A | 2015-06-30 | 2015-06-30
UPDATE
ACTUAL
PLANNED | 25 | IFB No. MFDP/RFQ/003/14-15 | Mailing | Assorted | 3600 | RFQ | 2014-10-06 | 2014-10-06 | 2014-10-13 | 2014-10-15 | 2014-10-22 | 2014-10-29 | 2014-11-05 | 2014-11-27 | N/A | 2014-06-30 | 2015-01-07
UPDATE
ACTUAL
GRAND TOTAL |  |  |  |  | 2769616
Signature : ________________________________________________ | [6 empty] | Date: __________________________________ |  |  |  |  | Approved: _____________________________________________________
|  | THOMAS S. WRIGHT | [10 empty] | AMARA M. KONNEH
|  | ACTING DIRECTOR OF PROCUREMENT | [10 empty] | MINISTER/ PROCUREMENT COMMITTEE CHAIRPERSON
Formulas:
PREP. OF BID DOCUMENT = [IMPLEMENTATION DATES]+7
PC APPROVAL - BID DOC/TECH SPECS = [PREP. OF BID DOCUMENT]+7
BID INVITATION & RELEASE OF BID DOC = [PC APPROVAL - BID DOC/TECH SPECS]+7
BID SUBMISSION/PUBLIC OPENING = [BID INVITATION & RELEASE OF BID DOC]+28
SUBMISSION OF BID EVALUATION REPORT = [BID SUBMISSION/PUBLIC OPENING]+14
PC APPROVAL - BID EVALUATION REPORT = [SUBMISSION OF BID EVALUATION REPORT]+7
CONTRACT AWARD & SIGNING = [PC APPROVAL - BID EVALUATION REPORT]+28

## Explanatory Note
Ministry of Finance and Development Planning
Procurement Plan
Core Budget
Fiscal Period: 2014 - 2015
No | Description | Explanatory note
1 | Fuel & Lubricant | cost of purchasing 183,275 gallons @ $4.26 based on the approved LPRC and MOC price for vehicles and generators
2 | Stationery & Supplies | refers to the purchase of assorted stationery and supplies incuding Bond Paper, printer cartridges, notepads, ball point pens, etc. US$30,500.00 of this amount is charged to the budgetary line item, Workshop, Conferences, Seminars
3 | Cleaning Materials | cost of purchasing assorted household cleaning materials such as chlorax, soaps, detols, brooms to clean MFDP bathrooms and offices
4 | Fumigation Services | refers to cost for the spraying of the entire building for insects, flys, cockroaches, etc. This amount is charged to the Budgetary Line Cleaning Materials
5 | Employees ID Card | refers to the cost of hiring a desktop publishing firm to produce ID cards for employees and contractors of MFDP
6 | Vehicle Insurance Services | refers to the cost of hiring of an insurance service firm to provide comprehensive and third party insurance for MFDP vehicles
7 | Personnel Insurance Service | refers to cost of hiring of an insurance firm to cover insurance services for MFDP employees.
8 | Printing & Binding Services | refers to the cost for printing the Draft National Budget 2015/2016, the approved National Budget 2014/2015 (400) copies @ $65.00 per copy, Citizen Guide to the National Budget (3,000) copies @ $11.00 per copy, 2% Withholding Forms, Official Letterheads, Annual Economic Review, Fiscal Outturn, Debt Management Report, Aid Management Report, etc.
9 | Repairs and Maintenance (Civil) | refers to the cost of refurbishing some of MFDP Offices
10 | Repairs and Maintenance (Vehicles) | refers to the cost of hiring about two (2) or three (3) Mechanical Garages for the Preventive and Corrective Maintencance of all MFDP Vehicles
11 | Repair and Maintenance (Generator) | refers to the cost of sole sourcing Caterpillar (Liberia) Ltd. to carry out preventive and corrective maintenance on MFDP 810KVA generator as they are the only provider of spare parts and maintenance services for caterpillar Machines in Liberia.
12 | Repair and Maintenance (Mach, Equip & Furniture) | refers to the cost of hiring contrators to carry out preventive and corrective maintenance of air-conditioners, elevators and furnitures, etc.
13 | Machinery & Other Equipment | cost of purchasing air-conditioners, mini iceboxes, water dispensers, hand tools for maintenance purposes and other office equipment
14 | ICT Infrastructure | refers to the cost of procuring ICT Equipment such as laptops and desktop computers, network cables, printers, scanner, etc.
15 | Maintenance of Budget Software | refers to the cost of procuring Microsoft SQL Server enterprise edition and Microsoft Office professional for the updating and maintaning software for budgetration for the Department of Budget and Development Planning. This amount is charged to the budgetary line ICT Infrastructure in the cash plan
16 | Video Conferencing System | cost of sole sourcing Libtelco to supply and install a video conferencing system in the 10th Floor Conference room of MFDP. This amount is charged to the budgetary line ICT Infrastructure in the Cash Plan
17 | Furniture & Fixtures | cost of purchasing Desk, Chairs, conference table,etc. for the MFDP Main Building
18 | Food & Catering Services | refers to cost of hiring catering service providers to provide catering services for MFDP workshops, economic plan review meetings, budget preparation workshops, fiscal policy meetings, etc. US$43,418.00 of this amount is charged to the budgetary line item, Workshops, Conferences, Seminars while the balance is the amount for Food and Catering Services in the cash plan
19 | Hall Rental | refers to the cost of renting halls across the country for retreats, workshops, etc. This amout is taken from the budgetary line item Workshops, Conferences, Seminars in the Cash Plan.
20 | Public Address (PA) Systems Rental | refers to the cost of Public Address (PA) Systems Rental during conferences, workshops, seminars and other programs. This amount is charged to the budgetary line, Workshops, Conferences, Seminars in the Cash Plan
21 | Entertaiment Representation | refers to the cost of obtaining assorted food stuffs example soft drinks, water, snacks, crackers etc as refreshment for guests during meetings, conferences, and gifts for employees, etc.
22 | Internet Services | refers to the cost of Sole Sourcing Libtelco to provide internet subscription services for 12 months for MFDP
23 | Phone Cards | cost of purchasing phone cards for MFDP operations at an estimated price of $5.00 per unit for 25,320 units
24 | Foreign Means of Travel | refers to the budgetary line that facilitates payments for Air tickets for travels out of Liberia
25 | Mailing | cost of payment for services render for mailing MFDP communications to external partners by mailing companies
Explanatory Note for other budgetlines item that are not included in the Procurement Plan
1 | Newspapers, books and periodicals | refers to the budgetline that represent the cost of advertisemsnt, newspaper and puplication caption on the ministers in and out of the country
2 | Consultantcy services | refers to the payment of salary and wages for consultants providing professional services to the Ministry of Finance & Development Planning
3 | Non Residential Building | amount represent the cost for construction of the cash center that is ongoing in Bomi County by the Ministry of Finance & Development Planning
4 | Electricity | refers to Sourcing Electricity to LEC to supply the Ministry of Finance & development Planning main building with electric power.
5 | Water and sewage | refers to Sourcing Liberia Water and Sewer Corporation to supply water to the MFDP.
6 | Feasibility Studies | is used to provide DSA to technical working groups within the Ministry that will be charged with responsibility to clearly identify and establish the actual cost of MFDP projects in and around the country.
| Signed: | __________________________________________________________________
Acting Procurement Director

## Sheet1
Ministry of Finance and Development Planning
Procurement Plan (Core Budget)
GOL National Budget
Fiscal Year: 2014 - 2015
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
l | BASIC DATA | [5 empty] | IMPLEMENTATION DATES | [10 empty] | .
| ITEM NO. | PACKAGE NUMBER (CODE) | CONTRACT PACKAGE | QTY | ESTIMATED COST (USD) | PROCUREMENT METHOD | TECHNICAL SPECS/BOQ/DRAWINGS | PREP. OF BID DOCUMENT | PC APPROVAL - BID DOC/TECH SPECS | BID INVITATION & RELEASE OF BID DOC | BID SUBMISSION/PUBLIC OPENING | SUBMISSION OF BID EVALUATION REPORT | PC APPROVAL - BID EVALUATION REPORT | CONTRACT AWARD & SIGNING | ADVANCE PAYMENT (MOBILIZATION) | DELIVERY, INSPECTION (SUBSTANTIAL COMPLETION) | ACCEPTANCE & FINAL PAYMENT | REMARKS
PLANNED | 1 | IFB No. MFDP/RB/001/14-15 | Fuel & Lubricants (Generator & Vehicles) | 183,275 gallons | 780750 | RB | 2014-10-30 | 2014-11-06 | 2014-11-13 | 2014-11-20 | 2014-12-18 | 2015-01-01 | 2015-01-08 | 2015-02-05 | N/A | 2015-06-10 | 2015-06-30
UPDATE
ACTUAL
PLANNED | 2 | IFB No. MFDP/NCB/001/14-15 | Stationery & Supplies | Assorted | 216500 | NCB | 2014-10-30 | 2014-11-06 | 2014-11-13 | 2014-11-20 | 2014-12-18 | 2015-01-01 | 2015-01-08 | 2015-01-29 | N/A | 2015-06-30 | 2015-06-30
UPDATE
ACTUAL
PLANNED | 3 | IFB No. MFDP/NCB/002/14-15 | Clearning Materials | Assorted | 29000 | NCB | 2014-10-30 | 2014-11-06 | 2014-11-13 | 2014-11-20 | 2014-12-18 | 2015-01-01 | 2015-01-08 | 2015-01-29 | N/A | 2015-06-30 | 2015-06-30
UPDATE
ACTUAL
PLANNED | 4 | IFB No. MFDP/RFQ/001/14-15 | Fumigation Services | 1 Firm | 7000 | RFQ | 2014-11-17 | 2014-11-24 | 2014-12-01 | 2014-12-03 | 2014-12-10 | 2014-12-17 | 2014-12-24 | 2014-12-31 | N/A | 2015-03-30 | 2015-04-28
UPDATE
ACTUAL
PLANNED | 5 | IFB No. MFDP/RFQ/002/14-15 | Employees ID Card | 600 | 6000 | RFQ | 2014-12-10 | 2014-12-17 | 2014-12-24 | 2014-12-26 | 2015-01-02 | 2015-01-09 | 2015-01-16 | 2015-01-23 | N/A | 2015-02-25 | 2015-03-25
UPDATE
ACTUAL
PLANNED | 6 | IFB No. MFDP/NCB/003/14-15 | Vehicle Insurance Services | 55 Vehicles | 41950 | NCB | 2014-11-06 | 2014-11-13 | 2014-11-20 | 2014-11-27 | 2014-12-25 | 2015-01-08 | 2015-01-15 | 2015-02-05 | N/A | 2015-06-30 | 2015-06-30
UPDATE
ACTUAL
PLANNED | 7 | IFB No. MFDP/NCB/004/14-15 | Personnel Insurance Service | 1 Firm | 85248 | NCB | 2014-10-06 | 2014-10-13 | 2014-10-20 | 2014-10-27 | 2014-11-24 | 2014-12-08 | 2014-12-15 | 2015-01-05 | N/A | 2015-06-30 | 2015-06-30
UPDATE
ACTUAL
PLANNED | 8 | IFB No. MFDP/NCB/005/14-15 | Printing & Binding Services | Assorted | 297550 | NCB | 2014-11-03 | 2014-11-10 | 2014-11-17 | 2014-11-24 | 2014-12-22 | 2015-01-05 | 2015-01-12 | 2015-02-02 | N/A | 2015-06-10 | 2015-06-30
UPDATE
ACTUAL
PLANNED | 9 | IFB No. MFDP/NCB/006/14-15 | Repairs and Maintenance (Civil) | 1 Building | 150000 | NCB | 2015-01-06 | 2015-01-13 | 2015-01-20 | 2015-01-27 | 2015-02-24 | 2015-03-10 | 2015-03-17 | 2015-04-07 | N/A | 2015-06-30 | 2015-06-30
UPDATE
ACTUAL
PLANNED | 10 | IFB No. MFDP/RB/002/14-15 | Repairs and Maintenance (Vehicles) | 65 Vehicles | 186000 | RB | 2014-11-10 | 2014-11-17 | 2014-11-24 | 2014-12-01 | 2014-12-29 | 2015-01-12 | 2015-01-19 | 2015-02-09 | N/A | 2015-06-30 | 2015-06-30
UPDATE
ACTUAL
PLANNED | 11 | IFB No. MFDP/SS/001/14-15 | Repair and Maintenance (Generator) | 1 | 12000 | SS | 2014-09-08 | 2014-09-15 | 2014-09-22 | 2014-09-29 | 2014-10-27 | 2014-11-10 | 2014-11-17 | 2014-12-08 | N/A | 2015-06-30 | 2015-06-30
UPDATE
ACTUAL
PLANNED | 12 | IFB No. MFDP/NCB/007/14-15 | Repair and Maintenance (Mach, Equip & Furniture) | Assorted | 65400 | NCB | 2014-09-16 | 2014-09-23 | 2014-09-30 | 2014-10-07 | 2014-11-04 | 2014-11-18 | 2014-11-25 | 2014-12-16 | N/A | 2015-06-30 | 2015-06-30
UPDATE
ACTUAL
PLANNED | 13 | IFB No. MFDP/NCB/008/14-15 | Machinery & Other Equipment | Assorted | 110000 | NCB | 2014-11-06 | 2014-11-13 | 2014-11-20 | 2014-11-27 | 2014-12-25 | 2015-01-08 | 2015-01-15 | 2015-02-05 | N/A | 2015-06-30 | 2015-06-30
UPDATE
ACTUAL
PLANNED | 14 | IFB No. MFDP/NCB/009/14-15 | ICT Infrastructure | Assorted | 71380 | NCB | 2014-12-15 | 2014-12-22 | 2014-12-29 | 2015-01-05 | 2015-02-02 | 2015-02-16 | 2015-02-23 | 2015-03-16 | N/A | 2015-06-30 | 2015-06-30
UPDATE
ACTUAL
PLANNED | 15 | IFB No. MFDP/NCB/010/14-15 | Maintenance of Budget Software | Assorted | 44320 | NCB | 2014-09-23 | 2014-09-30 | 2014-10-07 | 2014-10-14 | 2014-11-11 | 2014-11-25 | 2014-12-02 | 2014-12-23 | N/A | 2015-06-30 | 2015-06-30
UPDATE
ACTUAL
PLANNED | 16 | IFB No. MFDP/SS/002/14-15 | Video Conferencing | 1 Firm | 32500 | SS | 2014-10-15 | 2014-10-22 | 2014-10-29 | 2014-11-05 | 2014-12-03 | 2014-12-17 | 2014-12-24 | 2015-01-14 | N/A | 2015-06-10 | 2015-06-30
UPDATE
ACTUAL
PLANNED | 17 | IFB No. MFDP/NCB/011/14-15 | Furniture & Fixtures | Assorted | 62500 | NCB | 2014-12-18 | 2014-12-25 | 2015-01-01 | 2015-01-08 | 2015-02-05 | 2015-02-19 | 2015-02-26 | 2015-03-19 | N/A | 2015-06-30 | 2015-06-30
UPDATE
ACTUAL
PLANNED | 18 | IFB No. MFDP/NCB/012/14-15 | Food & Catering Services | Assorted | 140418 | NCB | 2014-11-06 | 2014-11-13 | 2014-11-20 | 2014-11-27 | 2014-12-25 | 2015-01-08 | 2015-01-15 | 2015-02-05 | N/A | 2015-06-30 | 2015-06-30
UPDATE
ACTUAL
PLANNED | 19 | IFB No. MFDP/NCB/013/14-15 | Hall Rental | Assorted | 30000 | NCB | 2014-11-26 | 2014-12-03 | 2014-12-10 | 2014-12-17 | 2015-01-14 | 2015-01-28 | 2015-02-04 | 2015-02-25 | N/A | 2015-06-30 | 2015-06-30
UPDATE
ACTUAL
PLANNED | 20 | IFB No. MFDP/NCB/014/14-15 | Public Address (PA) Systems Rental | Assorted | 12500 | NCB | 2014-09-01 | 2014-09-08 | 2014-09-15 | 2014-09-22 | 2014-10-20 | 2014-11-03 | 2014-11-10 | 2014-12-01 | N/A | 2015-06-30 | 2015-06-30
UPDATE
ACTUAL
PLANNED | 21 | IFB No. MFDP/NCB/015/14-15 | Entertainment | Assorted | 20200 | NCB | 2014-12-01 | 2014-12-08 | 2014-12-15 | 2014-12-22 | 2015-01-19 | 2015-02-02 | 2015-02-09 | 2015-03-02 | N/A | 2015-06-30 | 2015-06-30
UPDATE
ACTUAL
PLANNED | 22 | IFB No. MFDP/RB/003/14-15 | Rice | 1,100 bags | 37400 | RB | 2014-10-23 | 2014-10-30 | 2014-11-06 | 2014-11-13 | 2014-12-11 | 2014-12-25 | 2015-01-01 | 2015-01-22 | N/A | 2015-06-10 | 2015-06-30
UPDATE
ACTUAL
PLANNED | 23 | IFB No. MFDP/SS/003/14-15 | Internet Services | 1 firm | 90000 | SS | 2014-09-01 | 2014-09-08 | 2014-09-15 | 2014-09-22 | 2014-10-20 | 2014-11-03 | 2014-11-10 | 2014-12-01 | N/A | 2015-06-30 | 2015-06-30
UPDATE
ACTUAL
PLANNED | 24 | IFB No. MFDP/NCB/016/14-15 | Scratch Cards | 25,320 Pcs | 126600 | NCB | 2014-10-30 | 2014-11-06 | 2014-11-13 | 2014-11-20 | 2014-12-18 | 2015-01-01 | 2015-01-08 | 2015-01-29 | N/A | 2015-06-30 | 2015-06-30
UPDATE
ACTUAL
PLANNED | 25 | IFB No. MFDP/NCB/017/14-15 | Air Tickets | Assorted | 131000 | NCB | 2014-11-24 | 2014-12-01 | 2014-12-08 | 2014-12-15 | 2015-01-12 | 2015-01-26 | 2015-02-02 | 2015-02-23 | N/A | 2015-06-30 | 2015-06-30
UPDATE
ACTUAL
PLANNED | 26 | IFB No. MFDP/RFQ/003/14-15 | Mailing | Assorted | 3600 | RFQ | 2014-10-06 | 2014-10-06 | 2014-10-13 | 2014-10-15 | 2014-10-22 | 2014-10-29 | 2014-11-05 | 2014-11-27 | N/A | 2014-06-30 | 2015-01-07
UPDATE
ACTUAL
GRAND TOTAL |  |  |  |  | 2769616
Signature : ________________________________________________ | [6 empty] | Date: __________________________________ |  |  |  |  | Approved: _____________________________________________________
|  | THOMAS S. WRIGHT | [10 empty] | AMARA M. KONNEH
|  | ACTING DIRECTOR OF PROCUREMENT | [10 empty] | MINISTER/ PROCUREMENT COMMITTEE CHAIRPERSON
Formulas:
PREP. OF BID DOCUMENT = [IMPLEMENTATION DATES]+7
PC APPROVAL - BID DOC/TECH SPECS = [PREP. OF BID DOCUMENT]+7
BID INVITATION & RELEASE OF BID DOC = [PC APPROVAL - BID DOC/TECH SPECS]+7
BID SUBMISSION/PUBLIC OPENING = [BID INVITATION & RELEASE OF BID DOC]+28
SUBMISSION OF BID EVALUATION REPORT = [BID SUBMISSION/PUBLIC OPENING]+14
PC APPROVAL - BID EVALUATION REPORT = [SUBMISSION OF BID EVALUATION REPORT]+7
CONTRACT AWARD & SIGNING = [PC APPROVAL - BID EVALUATION REPORT]+28