## 2011-2012
MINISTRY OF EDUCATION
Draft Procurement Plan
For FY 2011/2012
| Item | Code | Contract Package | Qty | Est. Cost | Procurement Method | Tech. Spec. | Prepare Bid Document | Entity/PC Approval 1 | Advertise Release Doc. | Bid Closing & Public Opening | Bid Evaluation Report | Entity/PC Approval II | Contract Award/ Signature | Advance Payment/ LoC | Delivery | Acceptance/Final Payment | REMARKS
| 1 | IFB No./MOE/NCB/001/011/012 | Petroleum Products | 101,506.9 gallons | 470439 | NCB | 2011-07-01 | 2011-07-11 | 2011-07-25 | 2011-08-01 | 2011-08-29 | 2011-09-12 | 2011-09-16 | 2011-09-23 | 2011-10-07 | 2011-12-22 | 2012-03-21
Update
Act.
| 2 | IFB No./MOE/NCB/002/011/012 | Stationery | Assorted | 77000 | NCB | 2011-07-04 | 2011-07-14 | 2011-07-28 | 2011-08-04 | 2011-09-01 | 2011-09-15 | 2011-09-20 | 2011-09-27 | 2011-10-11 | 2011-12-26 | 2012-03-25
Update
Act.
| 3 | IFB No./MOE/NCB/003/011/012 | Maintenance and Repairs-Vehicles | 60 vehicles | 132674 | NCB | 2011-07-05 | 2011-07-15 | 2011-07-29 | 2011-08-05 | 2011-09-02 | 2011-09-16 | 2011-09-21 | 2011-09-28 | 2011-10-12 | 2011-12-27 | 2012-03-26
Update
Act.
| 4 | IFB No./MOE/SS/001/011/012 | Land | 15 acres | 15000 | SS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-05-24
Update
Act.
| 5 | IFB No./MOE/RFQ/001/011/012 | Other Office Materials & Consumables | Assorted | 7289 | RFQ | 2011-07-02 | 2011-07-04 | N/A | 2011-07-05 | N/A | N/A | N/A | N/A | N/A | 2011-07-29 | 2011-08-15
Update
Act.
| 6 | IFB No./MOE/NCB/004/011/012 | Printing, Binding & Publication Services | Assorted | 78093 | NCB | 2011-07-12 | 2011-07-22 | 2011-08-05 | 2011-08-12 | 2011-09-09 | 2011-09-23 | 2011-09-28 | 2011-10-05 | 2011-10-19 | 2012-01-03 | 2012-04-02
Update
Act.
| 7 | IFB No./MOE/NCB/005/011/012 | Other Specialized Mats. & Services | Assorted | 26000 | NCB | 2011-07-28 | 2011-08-07 | 2011-08-21 | 2011-08-28 | 2011-09-25 | 2011-10-09 | 2011-10-14 | 2011-10-21 | 2011-11-04 | 2012-01-19 | 2012-04-18
Update
Act.
| 8 | IFB No./MOE/SS/002/011/012 | Office Building Rental/ Lease | 1 building | 130000 | SS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-05-10
Update
Act.
| 9 | IFB No./MOE/RFQ/002/011/012 | Tools & Small/Equipment & Household Materials | Assorted | 2500 | RFQ | 2011-08-10 | 2011-08-12 | N/A | 2011-08-15 | N/A | N/A | N/A | N/A | N/A | 2011-09-08 | 2011-09-22
Update
Act.
| 10 | IFB No./MOE/NCB/006/011/012 | Agricultural Supplies & Inputs | Assorted | 18907 | NCB | 2011-08-15 | 2011-08-25 | 2011-09-08 | 2011-09-15 | 2011-10-13 | 2011-10-27 | 2011-11-01 | 2011-11-08 | 2011-11-22 | 2012-02-06 | 2012-05-06
Update
Act.
| 11 | IFB No./MOE/NCB/007/011/012 | ICT Infrastructure, hardware, Networks and Facilities | Assorted | 91073 | NCB | 2011-08-11 | 2011-08-21 | 2011-09-04 | 2011-09-11 | 2011-10-09 | 2011-10-23 | 2011-10-28 | 2011-11-04 | 2011-11-18 | 2012-02-02 | 2012-05-02
Update
Act.
| 12 | IFB No./MOE/RFQ/003/011/012 | Laboratory Consumable | Assorted | 3500 | RFQ | 2011-08-16 | 2011-08-18 | N/A | 2011-08-19 | N/A | N/A | N/A | N/A | N/A | 2011-09-12 | 2011-09-26
Update
Act.
| 13 | IFB No./MOE/RFQ/004/011/012 | Drugs & Medical Consumable | Assorted | 10000 | RFQ | 2011-08-23 | 2011-08-25 | N/A | 2011-08-26 | N/A | N/A | N/A | N/A | N/A | 2011-09-19 | 2011-10-03
Update
Act.
| 14 | IFB No./MOE/NCB/008/011/012 | Transport Equipment(vehicles & motor bikes) | 17 pcs | 343230 | NCB | 2011-08-16 | 2011-08-26 | 2011-09-09 | 2011-09-16 | 2011-10-14 | 2011-10-28 | 2011-11-02 | 2011-11-09 | 2011-11-23 | 2012-02-07 | 2012-05-07
Update
Act.
| 15 | IFB No./MOE/NCB/009/011/012 | Entertainment Representation & Gifts | Assorted | 35935 | NCB | 2011-07-05 | 2011-07-15 | 2011-07-29 | 2011-08-05 | 2011-09-02 | 2011-09-16 | 2011-09-21 | 2011-09-28 | 2011-10-12 | 2011-12-27 | 2012-03-26
Update
Act.
| 16 | IFB No./MOE/NCB/010/011/012 | Telephone, telex., fax, internet, postage, courier | N/A | 38000 | NCB | 2011-08-26 | 2011-09-05 | 2011-09-19 | 2011-09-26 | 2011-10-24 | 2011-11-07 | 2011-11-12 | 2011-11-19 | 2011-12-03 | 2012-02-17 | 2012-05-17
Update
Act.
| 17 | IFB No./MOE/RFQ/005/011/012 | Repairs & Maintenance- Machinery, Equipment & Furniture | Assorted | 8879 | RFQ | 2011-09-05 | 2011-09-07 | N/A | 2011-09-08 | N/A | N/A | N/A | N/A | N/A | 2011-10-02 | 2011-10-16
Update
Act.
| 18 | IFB No./MOE/NCB/011/011/012 | Repairs & maintenance - Civil | 6 buildings | 294220 | NCB | 2011-09-20 | 2011-09-30 | 2011-10-14 | 2011-10-21 | 2011-11-18 | 2011-12-02 | 2011-12-07 | 2011-12-14 | 2011-12-28 | 2012-03-13 | 2012-06-11
Update
Act.
| 19 | IFB No./MOE/NCB/012/011/012 | Other Rental & Leases | Assorted | 95022 | NCB | 2011-08-31 | 2011-09-10 | 2011-09-24 | 2011-10-01 | 2011-10-29 | 2011-11-12 | 2011-11-17 | 2011-11-24 | 2011-12-08 | 2012-02-22 | 2012-05-22
Update
Act.
| 20 | IFB No./MOE/RFQ/006/011/012 | Repairs & Maintenance-Civil (C.H. Dewey High Sch.) | 1 | 30000 | RFQ | 2011-07-19 | 2011-07-21 | N/A | 2011-07-25 | N/A | N/A | N/A | N/A | N/A | 2011-08-18 | 2011-09-01
Update
Act.
| 21 | IFB No./MOE/RFQ/007/011/012 | Vehicle Insurance | 2 vehicles | 5500 | RFQ | 2011-07-23 | 2011-07-25 | N/A | 2011-07-27 | N/A | N/A | N/A | N/A | N/A | 2011-08-20 | 2011-09-03
Update
Act.
| 22 | IFB No./MOE/NCB/013/011/012 | Furniture & Fixtures | Assorted | 131122 | NCB | 2011-09-14 | 2011-09-24 | 2011-10-08 | 2011-10-15 | 2011-11-12 | 2011-11-26 | 2011-12-01 | 2011-12-08 | 2011-12-22 | 2012-03-07 | 2012-06-05
Update
Act.
| 23 | IFB No./MOE/RFQ/008/011/012 | Repairs & Maintenance-Civil (Saniquelle High Sch.) | 1 | 10000 | RFQ | 2011-08-02 | 2011-08-04 | N/A | 2011-08-05 | N/A | N/A | N/A | N/A | N/A | 2011-08-29 | 2011-09-12
Update
Act.
| 24 | IFB No./MOE/RFQ/009/011/012 | Carriage, Haulage, Freight and Transport Hire | Assorted | 18450 | RFQ | 2011-08-17 | 2011-08-19 | N/A | 2011-08-22 | N/A | N/A | N/A | N/A | N/A | 2011-09-15 | 2011-09-29
Update
Act.
| 25 | IFB No./MOE/RFQ/010/011/012 | Cleaning Materials & Services | Assorted | 2580 | RFQ | 2011-07-06 | 2011-07-08 | N/A | 2011-07-11 | N/A | N/A | N/A | N/A | N/A | 2011-08-04 | 2011-08-18
Update
Act.
| 26 | IFB No./MOE/RFQ/011/011/012 | Domestic Means of Travel | Assorted | 100610 | RFQ | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Update
Act.
| 27 | IFB No./MOE/RFQ/012/011/012 | Foreign Means of Travel | Assorted | 57000 | RFQ | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Update
Act.
| 28 | IFB No./MOE/NCB/014/011/012 | Machinery & Other Equipment | Assorted | 40218 | NCB | 2011-08-11 | 2011-08-21 | 2011-09-04 | 2011-09-11 | 2011-10-09 | 2011-10-23 | 2011-10-28 | 2011-11-04 | 2011-11-18 | 2012-02-02 | 2012-05-02
Update
Act.
| 29 | IFB No./MOE/SS/003/011/012 | Newspapers, Books & Special Publication | 900 pcs | 3000 | SS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-06-20
Update
Act.
| 30 | IFB No./MOE/NCB/015/011/012 | Local conferences, seminars, symposia & exhibitions | 2 | 38000 | NCB | 2011-07-06 | N/A | N/A | N/A | N/A | N/A | 2011-07-08 | 2011-07-15 | 2011-07-29 | 2011-10-13 | 2012-01-11
Update
Act.
Signature: ______________________________ | [6 empty] | 2011-10-23: Date: ____________________________________
PROCUREMENT DIVISION
Approved: __________________________________________ | [6 empty] | 2011-10-23: Grand Total:; 2011-11-04: 2314241
CHAIRMAN-PROCUREMENT COMMITTEE

## notes
Notes to Procurement Plan:
Item | Contract Package | Description
1 | Petroleum Products | Engine oil, Diesel, Gasoline, Brake fluid, etc.
2 | Stationery | envelopes, inks, pens, pencils, papers, etc.
3 | Maintenance and Repairs-Vehicles | Spare parts for vehicles(filters, tires, batteries, etc.) and maintenance services
4 | Land
5 | Other Office Materials & Consumables | record books, ledgers, catridges, desk trays, etc.
6 | Printing, Binding & Publication Services | document production and binding, advertisements, printing of vouchers, brochures
7 | Other Specialized Mats. & Services | materials and equipment for the TTIs and Voc. & Tech. Institutes/school furniture
8 | Office Building Rental/ Lease | rental expenses for private buildings housing public offices/schools
9 | Tools & Small/Equipment & Household Materials | screw drivers, hammers, brooms, pliers, etc.
10 | Agricultural Supplies & Inputs | fertilizers, seeds, etc.
11 | ICT Infrastructure, hardware, Networks and Facilities | laptops, desktops, radio, audio equipment, networks equipments, etc.
12 | Laboratory Consumable | chemicals
13 | Drugs & Medical Consumable | paracetamol, chloroquine, asprine, etc.
14 | Transport Equipment(vehicles & motor bikes) | vehicles, motor bikes, bicycles, wheelbarrow
15 | Entertainment Representation & Gifts | snacks, juices, gifts, etc.
16 | Telephone, telex., fax, internet, postage, courier | phones, scratch cards, gprs edge/modem, etc.
17 | Repairs & Maintenance- Machinery, Equipment & Furniture | parts for repair/replacement and maintenance service
18 | Repairs & maintenance - Civil | renovation and maintenance of building
19 | Other Rental & Leases | other rental expenses for private buildings housing public offices/schools
20 | Repairs & Maintenance-Civil (C.H. Dewey High Sch.) | renovation and maintenance of C.H. Dewey school in Bomi County
21 | Vehicle Insurance | insurance coverage for vehicles owned by the Ministry of Education
22 | Furniture & Fixtures | school furniture, office furniture, curtains, rugs, etc.
23 | Repairs & Maintenance-Civil (Saniquelle High Sch.) | renovation and maintenance of Saniquelle High school in Nimba County
24 | Carriage, Haulage, Freight and Transport Hire | vehicle hire for local travel/ food and school materials distribution
25 | Cleaning Materials & Services | soap, chlorax, dethol, towels, brooms, dirt tray, etc.
26 | Domestic Means of Travel | domestic travel tickets, transport costs including local transport for official in-country travel
27 | Foreign Means of Travel | airline tickets, transport costs including local transport for official foreign travel
28 | Machinery & Other Equipment | photocopiers, typewriters, air conditioners, clocks, etc.
29 | Newspapers, Books & Special Publication | newspapers, newsletters, advertisements, press releases, etc.
30 | Local conferences, seminars, symposia & exhibitions | stationery, venue hire, charts, transport of participants, etc. relative to the conference, seminar, or symposium being held
Signature: ______________________________ |  | Date: ____________________________________
PROCUREMENT DIVISION
Approved: __________________________________________ |  | Grand Total: US$2,314,241.00
CHAIRMAN-PROCUREMENT COMMITTEE