## MOCI 2014-15
1 | 2 | 3 | 4 | 5 |  | 6 | 7 |  | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 |  | 17 |  |  | 18 | 19
|  | BASIC DATA | [6 empty] | 8: IMPLEMENTATION DATES | [5 empty] | .
| ITEM NO. | PACKAGE NUMBER (CODE) | CONTRACT PACKAGE |  | QTY | ESTIMATED COST (USD) |  | PROCUREMENT METHOD | TECHNICAL SPECS/BOQ/DRAWINGS | PREP. OF BID DOCUMENT | PC APPROVAL - BID DOC/TECH SPECS | BID INVITATION & RELEASE OF BID DOC | BID SUBMISSION/PUBLIC OPENING | SUBMISSION OF BID EVALUATION REPORT | PC APPROVAL - BID EVALUATION REPORT | CONTRACT AWARD & SIGNING |  | ADVANCE PAYMENT (MOBILIZATION) |  | DELIVERY, INSPECTION (SUBSTANTIAL COMPLETION) | ACCEPTANCE & FINAL PAYMENT |  | REMARKS
PLANNED | 1 | IFB No. MCI/NCB/001/14/15 | Foreign Travel/Means of Travel |  | Assorted | 30000 |  | NCB | 2014-08-11 | 2014-08-18 | 2014-08-25 | 2014-09-01 | 2014-09-29 | 2014-10-13 | 2014-10-20 | 2014-11-03 |  | N/A |  | 2015-05-22 | 2015-06-19
UPDATE
ACTUAL
PLANNED | 2 | IFB No. MCI/RFQ/001/14/15 | Domestic travel |  | Assorted | 1613 |  | RFQ | 2014-08-12 | 2014-08-19 | 2014-08-26 | 2014-09-02 | 2014-09-09 | 2014-09-16 | 2014-09-23 | 2014-09-30 |  | N/A |  | 2015-05-28 | 2015-06-11
UPDATE
ACTUAL
PLANNED | 4 | IFB NO. MCI/NCB/002/14/15 | Telecommunication/Internet postage |  | Assorted | 39719 |  | NCB | 2014-08-11 | 2014-08-18 | 2014-08-25 | 2014-09-01 | 2014-09-29 | 2014-10-13 | 2014-10-20 | 2014-11-03 |  | N/A |  | 2015-05-07 | 2015-06-04
UPDATE
ACTUAL
PLANNED | 6 | IFB NO. MCI/RB/001/14/15 | Petroleum Products vehicle & Generator |  | 30603.626 | 118130 |  | Retricted Bidding | 2014-08-12 | 2014-08-19 | 2014-08-26 | 2014-09-02 | 2014-09-30 | 2014-10-07 | 2014-10-14 | 2014-10-28 |  | N/A |  | 2015-05-26 | 2015-06-23
UPDATE
ACTUAL
PLANNED | 7 | IFB/NO. MCI/NCB/003/14/15 | Repairs & Mantenance- Civil |  | 1 bldg | 20148 |  | NCB | 2014-09-02 | 2014-09-09 | 2014-09-16 | 2014-09-23 | 2014-10-21 | 2014-10-28 | 2014-11-04 | 2014-11-18 |  | N/A |  | 2015-05-22 | 2015-06-19
UPDATE
ACTUAL
PLANNED | 8 | IFB NO. MCI/RB/002/14/15 | Repairs Mantenance Vehicle |  | 37 vehicles | 35500 |  | Restricted Bidding | 2014-09-08 | 2014-09-15 | 2014-09-22 | 2014-09-29 | 2014-10-27 | 2014-11-03 | 2014-11-10 | 2014-11-24 |  | N/A |  | 2015-05-28 | 2015-06-25
UPDATE
ACTUAL
PLANNED | 9 | IFB NO. MCI/RFQ/002/14/15 | Repairs & Mantenance Mechinary/Equip & Forniture |  | Assorted | 3750 |  | RFQ | 2014-09-10 | 2014-09-17 | 2014-09-24 | 2014-10-01 | 2014-10-15 | 2014-10-22 | 2014-10-29 | 2014-11-05 |  | N/A |  | 2015-05-27 | 2015-06-10
UPDATE
ACTUAL
PLANNED | 10 | IFB NO. MCI/RFQ/003/14/15 | Cleaning material & Services |  | Assorted | 4808 |  | RFQ | 2014-08-13 | 2014-08-20 | 2014-08-27 | 2014-09-03 | 2014-10-01 | 2014-10-08 | 2014-10-22 | 2014-10-29 |  | N/A |  | 2015-06-16 | 2015-06-30
UPDATE
ACTUAL
PLANNED | 11 | IFB NO. MCI/NCB/004/14/15 | Stationery |  | Assorted | 16875 |  | NCB | 2014-08-13 | 2014-08-20 | 2014-08-27 | 2014-09-03 | 2014-10-01 | 2014-10-08 | 2014-10-22 | 2014-11-06 |  | N/A |  | 2015-05-15 | 2015-06-12
UPDATE
ACTUAL
PLANNED | 12 | IFB NO. MCI/RFQ/004/14/15 | Printing Binding & Publication |  | Assorted | 3750 |  | RFQ | 2014-09-15 | 2014-09-22 | 2014-09-29 | 2014-10-06 | 2014-10-20 | 2014-10-27 | 2014-11-03 | 2014-11-10 |  | N/A |  | 2015-06-08 | 2015-06-22
UPDATE
ACTUAL
PLANNED | 13 | IFB NO. MCI/RFQ/005/14/15 | Newspaper,Books Periodical |  | Assorted | 5245 |  | RFQ | 2014-09-22 | 2014-09-29 | 2014-10-06 | 2014-10-13 | 2014-10-20 | 2014-10-27 | 2014-11-03 | 2014-11-10 |  | N/A |  | 2015-06-08 | 2015-06-22
UPDATE
ACTUAL
PLANNED | 14 | IFB NO.MCI/RFQ/006/14/15 | Workshop,conferences, Sympiosium |  | Assorted | 9404 |  | RFQ | 2014-08-12 | 2014-08-19 | 2014-08-26 | 2014-09-02 | 2014-09-09 | 2014-09-16 | 2014-09-23 | 2014-09-30 |  | N/A |  | 2015-04-28 | 2015-05-26
UPDATE
ACTUAL
PLANNED | 15 | IFB NO. MCI/RFQ/007/14/15 | Food & Catering |  | Assorted | 6750 |  | RFQ | 2014-08-18 | 2014-08-25 | 2014-09-01 | 2014-09-08 | 2014-09-15 | 2014-09-22 | 2014-09-29 | 2014-10-06 |  | N/A |  | 2015-06-03 | 2015-06-17
UPDATE
ACTUAL
PLANNED | 16 | IFB NO. MCI/RFQ/008/14/15 | Advertising & Public Relations |  | Assorted | 8000 |  | RFQ | 2014-10-06 | 2014-10-13 | 2014-10-20 | 2014-10-27 | 2014-11-03 | 2014-11-10 | 2014-11-17 | 2014-11-24 |  | N/A |  | 2015-06-12 | 2015-06-26
UPDATE
ACTUAL
PLANNED | 17 | IFB NO. MCI/NCB/005/14/15 | Personnel Insurance |  | 292 | 19470 |  | NCB | 2014-09-24 | 2014-10-01 | 2014-10-08 | 2014-10-15 | 2014-11-12 | 2014-11-19 | 2014-12-03 | 2014-12-17 |  | N/A |  | 2015-05-26 | 2015-06-23
UPDATE
ACTUAL
PLANNED | 18 | IFB NO. MCI/RFQ/009/14/15 | Entertainment,Representation & Gifts |  | Assorted | 3750 |  | RFQ | 2014-10-14 | 2014-10-21 | 2014-10-28 | 2014-11-04 | 2014-11-11 | 2014-11-18 | 2014-11-24 | 2014-11-30 |  | N/A |  | 2015-05-29 | 2015-06-12
UPDATE
ACTUAL
GRAND TOTAL | [5 empty] | 326912
Prepared by: ___________________________________ |  |  |  | Approved by: ________________________________________ |  |  |  |  | 2014-10-27: Date__________________
Procurement Director/ Manager Head of Entity/Chairman Proc. Cmttee
Domestics means of travel |  |  | This contrat package include means of traveling to various counties on project assessment-Domestic meas Travel | Include approximately (6 trips) means of Traveling to various counties on project assessment (Domestic means of Travel)
Electricity |  | (us$13,681.00) | Contract package include-(sole sourcing) LEC electricitrification for power supply for the ministry of Commerce and Industry | This contract package include (sole sourcing) LEC electrification for power supply for the Ministry of Commerce and Industry
Office Building Rental (US$53,215.00) this contract package will be used for rental fees for the building on Gurley street which the MOCI is currently occupying; John H Thompsom Lessor. US$40,000 annually
Water & Sewer(US$3,593.00) |  |  | This contract package (Sole Sourcing, Water & Sewer) to supply the Ministry of Commerce with water to facilitate | Contract package include (Sole Sourcing water & Sewer) to supply the ministry of Commerce & industry with water to facilitate smooth operation of various bath rooms.
foreign means of Travel |  |  | This contract package include maens of travel to various countries for bilateral, multilateral agreement and also | contains approximately (20 trips) means of travel to various countries for bilaterl, mutilateral agreement and also involve plane tickets
Telecommunication, internet |  |  | This contract package include-internet facility to send information from one department to another. | This package is divided into (2 lots) which include-Lot 1 Internet facility for communication purpose and Lot 2.Scratch Cards amounting to (US$29,789.25) that is 75% of the total Amount
postage and courier
Repair and Maintenance |  |  | Include- Repair and Maint. Of Air conditioners, computers, photocopiers, Printers etc | Include- Repair and Maint of Air Conditioners, Computers, Photocopier, Printers etc
Machinery, Equipment
Cleaning materials |  |  | include-Tide soap, Tissues, Floor Mop, delta, Air fresheners, soap, chlora, Towels, brooms, dirt tray etc | Include- Tide Soap, Tissues, Floor Mop, delta, Air fresheners, soap, chloral, towels, brooms, dirt tray.
Stationery |  |  | Include reams of Sheet, Box file, pens, ledger, caculator, envelopes, inks, pens, pencils etc | Include -purchase of Reams of sheet, Box file, pens, Ledger, calculator, envelopes, inks, pencils including flip charts, marker note pad and materials for participants relative to the conference seminar
held and additional amount of US$2550.00 was deducted from workshops and Symposia for stationery materias that will be used during conference.
Printing Binding and |  |  | Include -Advertising of public notice, binding of reports, publication of publication of procurement Act, printing of | Include- Advertising of public notices, Binding of reports, publication of procurement Ad, Printing of letter heads
publication services |  |  | letter heads and envelopes etc | printing of envelopes etc.
Newspapers, Books |  |  | Include-purchase of Newspapers for the ministry, annual Report, press release etc. | purchase of Newspaper for the Ministry, Annual Report, press release etc
and periodical
Workhops, Conferences, |  |  | Good Manufacturing workshop venue, Fula Workshop, Liquour Workshop, charts transport of participants etc | Hall Rental & facilitators fees for the following workshops: Fula Workshop, Liguor Workshop, Good Manufacturing Workshop
Symposia and Seminar |  |  | relative to the conference seminar held | Additional amount of US$22550 was deducted froms, Conferences & symposia for stationery materials that will be used during conference
Food and Catering services |  |  | July 26th & Dec. 25th Celebration; Catering for workshops Seminars | July 26th & Dec. 25th Celebration, catering for workshops, seminars
Repair & Maintenance Vehicle |  |  | include spare parts for vehicles (filters, tires, batteries, etc) and maitenance services | Include- spare parts for vehicles (filters, tires, batteries etc) and maintenance services
Petroleum Product |  |  | Include purchasing of fuel and lubricants for vehicle assigned to Minister of Commerce, his principal Deputies | Include- the purchasing of fuel and lubricants for vehicle assigned to the Minister of the Ministry
for Vehicles & Generator |  |  | include Director of various sectional head, as well as to fuel the employees buses that drop them to | of Commerce, Deputy Ministers, Assistant Ministers, Directors, sectional head, as well as to fuel
|  |  | their destination. And to facility the fueling the generator the | the employees buses that drop them to their destination. And to facility the fueling the generator,
|  |  | Ministry of Commerce & Industry with electricity in the absence LEC | that supply the Ministry of Commerce & Industry with electricity in the absence of LEC
Personnel Insurance |  |  | 292, This include all insurance all employee within the entity, throuhg medical care, Accident, Death etc. | Include 292, sole Source Secure Risks for all employees within the entity, through medical care, Accident etc
Entertainment, |  |  |  | Include- Refreshment for visitors during meeting, conferences, snack, juice, gift, etc
Representation and Gift |  |  | Refreshment for visitors during meeting, Conferences, snack, juice, gift, etc.
Employees award- |  |  |  | package giving to hard working employees such as employee of the year among others, to motivate them at the end of the fiscal year
Repair & Maintenance Civil- |  |  |  | Include manor renovation of the building currently occupied by the Ministry of Commerce & Industry on Gurley Street; including repair of doors, Curtainss, rug etc.

## CONSULTANCY SERVICES
Name of Entity: __________________________
PROCUREMENT PLAN (specify whether Core budget or Project budget)
Source of Funding:
Budget Period/Fiscal year: ____________
1 | 2 | 3 | 4 | 5 |  | 6 |  |  | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
|  | BASIC DATA | [6 empty] | 8: IMPLEMENTATION DATES
[11 empty] | REQUEST FOR EXPRESSION OF INTEREST, if applicable |  |  |  | REQUEST FOR PROPOSALS AND APPROVAL OF AWARD
| ITEM NO. | PACKAGE NUMBER (CODE) | CONTRACT PACKAGE |  | No. of FIRMS/PERSONS |  | ESTIMATED COST (USD) | SELECTION METHOD |  | PREP. OF TOR & PC APPROVAL | PUBLICATION OF REOI | REOI CLOSING/ OPENING | SUBMISSION OF EVALUATION REPORT | PC APPROVAL- EVALUATION REPORT/SHORTLIST | PREPARATION & SUBMISSION OF RFP DOCUMENT | PC APPROVAL - FINAL TOR/RFP DOCUMENT | INVITATION OF PROPOSALS | PROPOSAL SUBMISSION & OPENING | SUBMISSION OF TECHNICAL & FINANCIAL EVALUATION REPORT | PC APPROVAL- COMBINED EVALUATION REPORT | CONTRACT AWARD & SIGNING | COMPLETION (FINAL REPORT) AND PAYMENT
PLANNED | 1 | IFB No. MCI/QCBS/001/14/15 | CONSULTANCY SERVICES |  |  | 89000 |  | QCBS |  | 2014-08-29 | N/A | N/A | N/A | N/A | 2014-09-12 | 2014-09-26 | 2014-09-29 | 2014-10-13 | 2014-10-20 | 2014-10-27 | 2014-11-10 | 2015-05-09
UPDATE
ACTUAL
PLANNED | 2
UPDATE
ACTUAL
PLANNED | 3
UPDATE
ACTUAL
GRAND TOTAL | [5 empty] | 89000
Prepared by: ___________________________________ |  |  |  | Approved by: ________________________________________ | Date: ________________
Procurement Director/ Manager Head of Entity/Chairman Proc. Cmttee

## NSL
1 | 2 | 3 | 4 | 5 |  |  | 6 |  | 7 |  | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 |  | 17 |  |  | 18 | 19
|  | BASIC DATA | [8 empty] | 8: IMPLEMENTATION DATES | [5 empty] | .
| ITEM NO. | PACKAGE NUMBER (CODE) | CONTRACT PACKAGE |  | QTY | QTY |  | ESTIMATED COST (USD) |  | PROCUREMENT METHOD | TECHNICAL SPECS/BOQ/DRAWINGS | PREP. OF BID DOCUMENT | PC APPROVAL - BID DOC/TECH SPECS | BID INVITATION & RELEASE OF BID DOC | BID SUBMISSION/PUBLIC OPENING | SUBMISSION OF BID EVALUATION REPORT | PC APPROVAL - BID EVALUATION REPORT | CONTRACT AWARD & SIGNING |  | ADVANCE PAYMENT (MOBILIZATION) |  | DELIVERY, INSPECTION (SUBSTANTIAL COMPLETION) | ACCEPTANCE & FINAL PAYMENT |  | REMARKS
PLANNED | 1 | IFB NO. MCI/NSL/RFQ/001/14/15 | Telecommunications, Internet, Postage & Courier |  |  | Assorted | 7000 |  |  | RFQ | 2015-01-05 | 2015-01-12 | 2015-01-19 | 2015-01-26 | 2015-02-02 | 2015-02-09 | 2015-02-16 | 2015-02-23 |  | N/A |  | 2015-06-03 | 2015-06-17
Update
Actual
Planned | 2 | IFB NO. MCI/NSL/RB/001/14/15 | Petroleum Product Veh. & Generator |  |  | 5440gal. |  | 21000 |  | RB | 2014-12-15 | 2014-12-22 | 2014-12-29 | 2015-01-05 | 2015-02-02 | 2015-02-09 | 2015-02-23 | 2015-03-09 |  | N/A |  | 2015-05-28 | 2015-06-25
Update
Actual
Planned | 3 | IFB NO. MCI/NSL/SS/001/14/15 | Repair & Maintenance Civil |  |  | 1bldg |  | 13993.75 |  | SS | 2015-01-05 | 2015-01-12 | 2015-01-19 | 2015-01-26 | 2015-02-02 | 2015-02-09 | 2015-02-16 | 2015-02-23 |  | N/A |  | 2015-05-19 | 2015-06-16
Update
Actual
Planned | 4 | IFB NO. MCI/NSL/RFQ/002/14/15 | Repair & Maintenance Vehicle |  |  | 2 vehicles |  | 3535.75 |  | RFQ | 2015-01-12 | 2015-01-19 | 2015-01-26 | 2015-02-02 | 2015-02-09 | 2015-02-16 | 2015-02-23 | 2015-03-02 |  | N/A |  | 2015-05-11 | 2015-06-08
Update
Actual
Planned | 5 | IFB NO. MCI/NSL/RFQ/003/14/15 | Repair & Maint. Machinery, Equip. & Furniture |  |  | Assorted |  | 509.25 |  | RFQ | 2015-01-19 | 2015-01-26 | 2015-02-02 | 2015-02-09 | 2015-02-16 | 2015-02-23 | 2015-03-02 | 2015-03-09 |  | N/A |  | 2015-05-18 | 2015-06-15
Update
Actual
Planned | 6 | IFB NO. MCI/NSL/RFQ/004/14/15 | Stationery |  |  | Assorted |  | 800 |  | RFQ | 2015-02-02 | 2015-02-09 | 2015-02-16 | 2015-02-23 | 2015-03-02 | 2015-03-09 | 2015-03-16 | 2015-03-23 |  | N/A |  | 2015-04-20 | 2015-05-18
Update
Actual
Planned | 7 | IFB NO. MCI/NSL/RFQ/005/14/15 | Workshops, Conferences, Symposia & Seminars |  |  | Assorted |  | 1000 |  | RFQ | 2015-01-26 | 2015-02-02 | 2015-02-09 | 2015-02-16 | 2015-02-23 | 2015-03-02 | 2015-03-09 | 2015-03-16 |  | N/A |  | 2015-05-15 | 2015-06-12
Update
Actual
PLANNED | 8 | IFB NO. MCI/NSL/RFQ/006/14/15 | Food & Catering Services |  |  | Assorted | 661.25 |  |  | RFQ | 2015-01-20 | 2015-01-27 | 2015-02-03 | 2015-02-10 | 2015-02-17 | 2015-02-24 | 2015-03-03 | 2015-03-10 |  | N/A |  | 2015-05-19 | 2015-06-16
UPDATE
Actual
Planned | 9 | IFB NO. MCI/NSL/NCB/001/14/15 | Machinery & Equipment |  |  | 1Gen. |  | 37000 |  | NCB | 2014-11-24 | 2014-12-01 | 2014-12-08 | 2014-12-15 | 2015-01-12 | 2015-01-19 | 2015-02-02 | 2015-02-16 |  | N/A |  | 2015-05-17 | 2015-06-14
Update
Actual
GRAND TOTAL | [6 empty] | 85500
Prepared by: ___________________________________ | [10 empty] | 8: Approved__________________________; 12: Date_______________
Procurement Director/ Manager Head of Entity/Chairman Proc. Cmttee
Electricity(1,500.00) |  |  |  | Contract package include-(sole sourcing) LEC electricitrification for power supply for the Lab
Telecommunication, internet |  |  |  | This package is divided into (2 lots) which include-Lot 1 Internet facility for communication purpose and Lot 2.Scratch Cards
postage and courier
Repair and Maintenance |  |  |  | Include- Repair and Maint of Air Conditioners, Computers, Photocopier, Printers etc
Machinery, Equipment
Stationery |  |  |  | Include -purchase of Reams of sheet, Box file, pens, Ledger, calculator, envelopes, inks, pencils including flip charts, marker note pad and materials for participants relative to the conference seminar held
Workhops, Conferences, |  |  |  | Hall Rental & facilitators fees for the upcoming workshops
Symposia and Seminar
Food and Catering services |  |  |  | July 26th & Dec. 25th Celebration, catering for workshops, seminars
Repair & Maintenance Civil |  |  |  | minor Renovation of the building currently occupy by the Lab at the Public Works yards including repair of doors, Curtains, raw etc
Repair & Maintenance Vehicle |  |  |  | Include- spare parts for vehicles (filters, tires, batteries etc) and maintenance services
Petroleum Product |  |  |  | Include purchasing of fuel and lubricants for vehicles assigned to the Standards Lab, And to facility the fueling of the generator for electricity in the absence of LEC
for Vehicles & Generator
Machinery & Equipment |  |  |  | Puchase of one generator for the Ministry of commerce & Industry

## LBR
Name of Entity: Ministry of Commerce Industry (LBR)
PROCUREMENT PLAN ( Core budget)
Source of Funding: GOL
Budget Period/Fiscal year: 2014/15
1 | 2 | 3 | 4 | 5 |  |  | 6 |  | 7 |  | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 |  | 17 |  |  | 18 | 19
|  | BASIC DATA | [8 empty] | 8: IMPLEMENTATION DATES | [5 empty] | .
| ITEM NO. | PACKAGE NUMBER (CODE) | CONTRACT PACKAGE |  | QTY |  |  | ESTIMATED COST (USD) |  | PROCUREMENT METHOD | TECHNICAL SPECS/BOQ/DRAWINGS | PREP. OF BID DOCUMENT | PC APPROVAL - BID DOC/TECH SPECS | BID INVITATION & RELEASE OF BID DOC | BID SUBMISSION/PUBLIC OPENING | SUBMISSION OF BID EVALUATION REPORT | PC APPROVAL - BID EVALUATION REPORT | CONTRACT AWARD & SIGNING |  | ADVANCE PAYMENT (MOBILIZATION) |  | DELIVERY, INSPECTION (SUBSTANTIAL COMPLETION) | ACCEPTANCE & FINAL PAYMENT |  | REMARKS
Planned | 1 | IFB NO. MCI/LBR/NCB/001/14/15 | Telecommunication, internet, postage |  |  | Assorted |  | 66891 |  | NCB | 2014-09-01 | 2014-09-08 | 2014-09-15 | 2014-09-22 | 2014-10-20 | 2014-10-27 | 2014-11-03 | 2015-03-30 |  | N/A |  | 2015-04-27 | 2015-05-25
Actual
Update
PLANNED | 2 | IFB No. MCI/LBR/RB/001/14/15 | Petroleum Product vehicles & Generator |  |  | 8270.842gals | 27790.03 |  |  | Restricted Bidding | 2014-07-28 | 2014-08-04 | 2014-08-11 | 2014-08-18 | 2014-09-15 | 2014-09-22 | 2014-09-29 | 2015-03-28 |  | N/A |  | 2015-06-18 | 2015-06-30
ACTUAL
PLANNED | 3 | IFB No. MCI/LBR/NCB/002/14/15 | ICT Infrastrature Servicing |  |  | Assorted | 17687 |  |  | NCB | 2014-09-29 | 2014-10-06 | 2014-10-13 | 2014-10-20 | 2014-11-17 | 2014-11-24 | 2014-12-01 | 2015-03-06 |  | N/A |  | 2015-06-03 | 2015-06-30
UPDATE
ACTUAL
Planned | 4 | IFB No. MCI/LBR/RFQ/001/14/15 | Repairs & Maintenance-Vehicles |  |  | 3veh | 5120 |  |  | RFQ | 2014-07-29 | 2014-08-05 | 2014-08-12 | 2014-08-19 | 2014-09-02 | 2014-09-09 | 2014-09-16 | 2015-03-30 |  | N/A |  | 2015-06-18 | 2015-06-30
Update
Actual
PLANNED | 5 | IFB No. MCI/LBR/RFQ/002/14/15 | Repairs & Maintenance-Generator |  |  | 2Generator | 3000 |  |  | RFQ | 2014-08-26 | 2014-09-02 | 2014-09-09 | 2014-09-16 | 2014-09-30 | 2014-10-07 | 2014-10-14 | 2015-03-02 |  | N/A |  | 2015-06-22 | 2015-06-22
UPDATE
ACTUAL
GRAND TOTAL | [6 empty] | 120488.03
Prepared by: ___________________________________ |  |  |  |  | Date: ________________ | [5 empty] | 2014-07-28: Approved by:________________________________
Procurement Director/ Manager Head of Entity/Chairman Proc. Cmttee