## Sheet1
Ministry of Finance
Prcurement Plan
For the fiscal year 2011 - 2012
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
| item | Code | Contract Package | Qty | Estimate Cost | Procure | Tec. | Prepare | Entity/Pc | Advertise | Bid | Bid Eva. | Entity | Cont. | Advance | Delivery | Acceptance | Remarks
[6 empty] | method | Spec | Bidding |  | Release | Sub/Pub. | Reports | Pc | Award/ | Payment |  | Final
[8 empty] | Document |  | Doc. | Opening |  | App. II | Signature | LC |  | Payment
Planned | 1 | IFB No. | Fuel & Lub. | 391275.9 | 1819433 | NCB | 2011-06-13 | 2011-06-24 | 2011-06-29 | 2011-07-04 | 2011-08-04 | 2011-08-11 | 2011-08-17 | 2011-08-31 | N/A | 2011-09-14 | 2011-09-28
|  | MOF/NCB | Vehicles/Generators
001/11/12
Up date
Act
Planned | 2 | IFB No. | Repair & Maint Civil |  | 85000 | NCB | 2011-06-21 | 2011-06-28 | 2011-07-07 | 2011-08-08 | 2011-08-08 | 2011-08-19 | 2011-08-25 | 2011-09-08 | N/A | 2011-09-22 | 2011-10-06
MOF/NCB
002/11/12
Up date
Act
Planned | 4 | IFB No. | Repair & Maintanence | 140 Veh. | 158722 | SS | 2011-06-28 | N/A | 2011-07-18 | N/A | N/A | N/A | 2011-08-19 | 2011-09-02 | N/A | 2011-09-16 | 2011-09-30
|  | MOF/S S/ | Vehicles | 11 Bikes
001/11/12
Up date
Act
Planned | 5 | IFB No. | Repair & Maintenance | Assorted | 51551 | NCB | 2011-07-11 | 2011-07-18 | 2011-07-20 | 2011-07-27 | 2011-08-26 | 2011-09-02 | 2011-09-09 | 2011-09-23 | N/A | 2011-10-07 | 2011-10-21
|  | MOF/NCB/. | Machinery, Equip &
|  | 003/11/12 | Furniture
Up date
Act
Planned | 6 | IFB No. | Cleaning materials & |  | 90902 | NCB | 2011-06-23 | 2011-07-04 | 2011-07-11 | 2011-07-18 | 2011-08-18 | 2011-08-25 | 2011-09-01 | 2011-09-15 | N/A | 2011-09-29 | 2011-10-13
|  | MOF/NCB | Services
004/11/12
Up date
Act
*IFB No. 004 - The Cleaning materials include: Hard and Smooth brooms, Hand Soap, Deltol etc.
*IFB No. 003 - Machinery, equipmenrt and furniture to be repair and maintenance include computers, generators, Desk, Chairs etc.
*IFB No 002 - Repair and Maintenance Civil include: central building and other annexes
Ministry of Finance
Broad Street, Monrovia
Procurment Plan for the fiscal year 2011 - 2012
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
| item | Code | Contract Package | Qty | Estimate Cost | Procure | Tec. | Prepare | Entity/Pc | Advertise | Bid | Bid Eva. | Entity | Cont. | Advance | Delivery | Acceptance | Remarks
[6 empty] | method | Spec | Bidding |  | Release | Sub/Pub. | Reports | Pc | Award/ | Payment |  | Final
[8 empty] | Document |  | Doc. | Opening |  | App. II | Signature | LC |  | Payment
Planned |  | IFB No. | Stationery | Assorted | 341210 | NCB | 2011-06-10 | 2011-06-21 | 2011-06-27 | 2011-07-04 | 2011-08-04 | 2011-08-11 | 2011-08-18 | 2011-09-01 | N/A | 2011-09-15 | 2011-09-29
MOF/NCB
005/11/12
Up date
Act
Planned |  | IFB No. | Printing, binding and |  | 280108 | NCB | 2011-06-20 | 2011-07-01 | 2011-07-06 | 2011-07-11 | 2011-08-11 | 2011-08-18 | 2011-08-25 | 2011-09-09 | N/A | 2011-09-23 | 2011-10-07
|  | MOF/NCB | publications services
006/11/12
Up date
Act
Planned |  | IFB No. | News Papers, books | Assorted | 120000 | NCB | 2011-07-01 | 2011-07-05 | 2011-07-11 | 2011-07-15 | 2011-08-15 | 2011-08-22 | 2011-08-29 | 2011-09-12 | N/A | 2011-09-26 | 2011-10-10
|  | MOF/NCB. | and Periodicals
007/11/12
Up date
Act
Planned |  | IFB No | Employees ID Cards | 228 | 5000 | RFQ | 2011-07-04 | 2011-07-07 | 2011-07-07 | 2011-07-11 | 2011-08-11 | 2011-08-19 | 2011-08-26 | 2011-09-09 | N/A | 2011-09-23 | 2011-10-07
MOF/RFQ
001/11/12
Up date
Act
Planned |  | ITB No. | Telecommunications |  | 494000 | NCB | 2011-06-13 | 2011-06-24 | 2011-06-29 | 2011-07-04 | 2011-08-04 | 2011-08-11 | 2011-08-18 | 2011-09-01 | N/A | 2011-09-15 | 2011-09-22
|  | MOF/NCB | Internet, postage and
|  | 008/11/12 | Countier
Act
IFB No. 006 - Printing, binding and publication services include: Printing, Letter head papers, Printing and binding of Annual Report, Customs code and Tarriff etc.
IFB No. 008 - Telecommunications, intern, postage and countier include: Telephone, Internet Services, Scratch cards etc.
IFB No. 007 - News paper, books, and Periodicals include:
Ministry of Finance
Broad Street, Monrovia
Procurment Plan for the fiscal year 2011 - 2012
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
| item | Code | Contract Package | Qty | Estimate Cost | Procure | Tec. | Prepare | Entity/Pc | Advertise | Bid | Bid Eva. | Entity | Cont. | Advance | Delivery | Acceptance | Remarks
[6 empty] | method | Spec | Bidding |  | Release | Sub/Pub. | Reports | Pc | Award/ | Payment |  | Final
[8 empty] | Document |  | Doc. | Opening |  | App. II | Signature | LC |  | Payment
Planned |  | IFB No. | Water and Sewage | N/A | 45000 | SS | N/A | N/A | 2011-07-18 | N/A | N/A | N/A | 2011-08-18 | 2011-09-20 | N/A | 2011-10-04 | 2011-10-18
MOF/SS/
002/11/12
Up date
Act
Planned |  | IFB No. | Electricity | N/A | 571884 | SS | N/A | N/A | 2011-07-11 | N/A | N/A | N/A | 2011-08-29 | 2011-09-05 | N/A | N/A | 2012-06-30
MOF/SS/
003/11/12
Up date
Act
Planned |  | IFB No. | Other specialized |  | 112000 | NCB | 2011-07-01 | 2011-07-05 | 2011-07-06 | N/A | N/A | N/A | 2011-08-09 | 2011-08-15 | N/A | 2011-09-14 | 2011-09-28
|  | MOF/NCB | Materials & services
013/11/12
Up date
Act
Planned |  | IFB No | Tax Education |  | 80000 | Restricted | 2011-06-30 | 2011-07-11 | 2011-07-18 | 2011-07-22 | 2011-08-22 | 2011-08-29 | 2011-09-05 | 2011-09-19 | N/A | 2011-10-03 | 2011-10-17
MOF/RB/001
11/12.
Up date
Act
Planned |  | IFB No. | Food and catering | Assorted | 50000 | NCB | 2011-07-08 | 2011-07-12 | 2011-07-18 | N/A | N/A | N/A | 2011-09-05 | 2011-09-20 | N/A | 2011-10-04 | 2011-11-09
|  | MOF/NCB/ | Services
014/11/12
Up date
Act
IFB No. NCB/013 - Other specialized materials include: Jango, Drama, etc.
IFB No. RB/001 - Tax education include: Tax Awareness thru drama, bill baord and etc.
Ministry of Finance
Procurement Plan
For the fiscal year , 2011 - 2012
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
| item | Code | Contract Package | Qty | Estimate Cost | Procure | Tec. | Prepare | Entity/Pc | Advertise | Bid | Bid Eva. | Entity | Cont. | Advance | Delivery | Acceptance | Remarks
[6 empty] | method | Spec | Bidding |  | Release | Sub/Pub. | Reports | Pc | Award/ | Payment |  | Final
[8 empty] | Document |  | Doc. | Opening |  | App. II | Signature | LC |  | Payment
Planned |  | IFB No. | Tools and Small |  | 29700 | NCB | 2011-06-08 | 2011-06-20 | 2011-06-28 | 2011-07-04 | 2011-08-04 | 2011-08-11 | 2011-08-18 | 2011-09-01 | N/A | 2011-09-15 | 2011-09-22
|  | MOF/NCB | Equipment & House
|  | 015/11/12 | Hold materials
Up date
Act
Planned |  | IFB No. | Personnel Insurance | 1500 | 67902 | NCB | 2011-06-06 | 2011-06-17 | 2011-06-22 | 2011-06-27 | 2011-07-27 | 2011-08-04 | 2011-08-11 | 2011-08-25 | N/A | 2011-09-08 | 2011-09-22
MOF/NCB
016/11/12
Up date
Act
Planned |  | IFB No. | Vehicles Insurance | 140 | 46234 | NCB | 2011-06-13 | 2011-06-24 | 2011-06-29 | 2011-07-05 | 2011-08-05 | 2011-08-12 | 2011-08-19 | 2011-09-02 | N/A | 2011-09-16 | 2011-09-30
MOF/NCB
017/11/12
Up date
Act
Planned |  | IFB No. | Non Residential | 33 | 125000 | NCB | 2011-06-24 | 7/5/12011 | 2011-07-11 | 2011-07-15 | 2011-08-15 | 2011-08-22 | 2011-08-29 | 2011-09-12 | N/A | 2011-09-26 | 2011-10-10
|  | MOF/NCB | Building
018/11/12
Up date
Act
Planned |  | IFB No. | Transport Equipment |  | 268999 | NCB | 2011-06-24 | 2011-06-27 | 2011-07-04 | 2011-07-08 | 2011-08-08 | 2011-08-15 | 2011-08-22 | 2011-09-05 | N/A | 2011-09-19 | 2011-10-03
|  | MOF/NCB |  | 20
019/11/12
Up date
Act
IFB No. MOF/NCB/019 - Transport equipment include- Sedan, Jeep, base and Motor bikes
Ministry of Finance
Procurement Plan
For the fiscal year 2011 - 2012
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
| item | Code | Contract Package | Qty | Estimate Cost | Procure | Tec. | Prepare | Entity/Pc | Advertise | Bid | Bid Eva. | Entity | Cont. | Advance | Delivery | Acceptance | Remarks
[6 empty] | method | Spec | Bidding |  | Release | Sub/Pub. | Reports | Pc | Award/ | Payment |  | Final
[8 empty] | Document |  | Doc. | Opening |  | App. II | Signature | LC |  | Payment
Planned |  | ITB No. | Machinery and Other |  | 101002 | NCB | 2011-06-21 | 2011-07-04 | 2011-07-11 | 2011-07-12 | 2011-08-12 | 2011-08-19 | 2011-08-26 | 2011-09-09 | 2011-09-23 | 2011-10-07 | 2011-10-05
|  | MOF/NCB | Equipment | 50
020/11/12
Up date
Act
Planned |  | ITB No. | Furniture and |  | 95000 | NCB | 2011-06-28 | 2011-07-11 | 2011-07-18 | 2011-07-22 | 2011-08-22 | 2011-08-29 | 2011-09-05 | 2011-09-19 | N/A | 2011-10-03 | 2011-10-17
|  | MOF/ | Fixture | 100
021/11/12
Up date
Act
Planned |  | IFB No. | ICT Infrasture | Assorted | 177100 | NCB | 2011-06-24 | 2011-07-01 | 2011-07-06 | 2011-07-11 | 2011-08-11 | 2011-08-18 | 2011-08-25 | 2011-09-08 | N/A | 2011-09-22 | 2011-10-06
|  | MOF/NCB | Hard ware, Nrework
|  | 022/11/12 | facilities
Signature: _________________________________________ | [6 empty] | 2011-06-24: Date: ____________________________________; 2011-08-25: Approved: ______________________________________
IFB No. 020 include - Generator, elevator, Air conditioners etc.
IFB No. 021 include - Desk, Chairs, Cabinets etc.
IFBNo.022 include: Computers, Printers etc.