Monrovia Consolidated school system

PROCUREMENT PLAN (Core budget)

Source of Funding: GOL

Budget Period/Fiscal year: 2014/2015

| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | ITEM NO. | BASIC DATA |  |  |  |  | IMPLEMENTATION DATES |  |  |  |  |  |  |  |  |  |  | . |
|  |  | PACKAGE NUMBER (CODE) | CONTRACT PACKAGE | QTY | ESTIMATED COST (USD) | PROCUREMENT METHOD | TECHNICAL SPECS/BOQ/DRAWINGS | PREP. OF BID DOCUMENT | PC APPROVAL - BID DOC/TECH SPECS | BID INVITATION & RELEASE OF BID DOC | BID SUBMISSION/PUBLIC OPENING | SUBMISSION OF BID EVALUATION REPORT | PC APPROVAL - BID EVALUATION REPORT | CONTRACT AWARD & SIGNING | ADVANCE PAYMENT (MOBILIZATION) | DELIVERY, INSPECTION (SUBSTANTIAL COMPLETION) | ACCEPTANCE & FINAL PAYMENT | REMARKS |
| PLANNED | 1 | IFB NO.MCSS/RFQ/001/14/15 | Telecommunication Internet Scratch cards (150 Pieces) | Assorted | 750 | RFQ | 8/22/14 | 9/11/14 | 9/22/14 | 10/1/14 | 10/21/14 | 11/10/14 | 11/28/14 | 1/5/15 | NA | 2/12/15 | 3/17/15 |  |
| UPDATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PLANNED | 2 | IFB NO.MCSS/RB/001/14/15 | Fuel &Lubricant- Vehicle &Generator | 4,927.0073 Gals | 20,250 | RB | 8/28/14 | 9/26/14 | 10/16/14 | 10/27/14 | 12/16/14 | 1/22/15 | 2/12/15 | 3/31/15 | NA | 4/15/15 | 6/18/15 |  |
| UPDATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PLANNED | 3 | IFB NO.MCSS/NCB/001/14/15 | Repair & Maintenance-Civil | 23 Schools | 15,000 | NCB | 8/29/14 | 9/24/14 | 10/14/14 | 10/23/14 | 12/4/14 | 1/6/15 | 1/23/15 | 1/30/15 | NA | 2/23/15 | 3/20/15 |  |
| UPDATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Monrovia Consolidated school system

PROCUREMENT PLAN (Core budget)

Source of Funding: GOL

Budget Period/Fiscal year: 2014/2015

| 1 | 2 | 3 | 4 | 5 | 6 | 7 |  | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 |  | 17 |  |  | 18 | 19 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | ITEM NO. | BASIC DATA |  |  |  |  |  | IMPLEMENTATION DATES |  |  |  |  |  |  |  |  |  |  |  |  |  | . |
|  |  | PACKAGE NUMBER (CODE) | CONTRACT PACKAGE | QTY | ESTIMATED COST (USD) |  | PROCUREMENT METHOD | TECHNICAL SPECS/BOQ/DRAWINGS | PREP. OF BID DOCUMENT | PC APPROVAL - BID DOC/TECH SPECS | BID INVITATION & RELEASE OF BID DOC | BID SUBMISSION/PUBLIC OPENING | SUBMISSION OF BID EVALUATION REPORT | PC APPROVAL - BID EVALUATION REPORT | CONTRACT AWARD & SIGNING |  | ADVANCE PAYMENT (MOBILIZATION) |  | DELIVERY, INSPECTION (SUBSTANTIAL COMPLETION) | ACCEPTANCE & FINAL PAYMENT |  | REMARKS |
| PLANNED | 4 | IFB NO.MCSS/RFQ/002/14/15 | Repair & Maintenance Vehicle | 6Vehic. | 3,750 |  | RFQ | 8/26/14 | 9/15/14 | 9/24/14 | 10/3/14 | 10/23/14 | 11/12/14 | 12/2/14 | 1/14/15 |  | NA |  | 3/26/15 | 4/24/15 |  |  |
| UPDATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PLANNED | 5 | IFB NO.MCSS/RFQ/003/14/15 | Repair &Maintenance -Machinery Equipments Furniture | Assorted | 2,250 |  | RFQ | 8/20/14 | 9/8/14 | 9/17/14 | 9/26/14 | 10/15/14 | 10/31/14 | 11/2014 | 12/29/14 |  | NA |  | 2/27/15 | 3/30/15 |  |  |
| UPDATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PLANNED | 6 | IFB NO.MCSS/RFQ/004/14/15 | Cleaning Materials & Services | Assorted | 7,500 |  | RFQ | 8/29/14 | 9/25/14 | 10/10/14 | 10/31/14 | 11/27/14 | 12/18/14 | 1/15/15 | 2/2/15 |  | NA |  | 2/27/15 | 3/24/15 |  |  |
| UPDATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Monrovia Consolidated school system

PROCUREMENT PLAN (Core budget)

Source of Funding: GOL

Budget Period/Fiscal year: 2014/2015

| 1 | 2 | 3 | 4 | 5 | 6 | 7 |  | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 |  | 17 |  |  | 18 | 19 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | ITEM NO. | BASIC DATA |  |  |  |  |  | IMPLEMENTATION DATES |  |  |  |  |  |  |  |  |  |  |  |  |  | . |
|  |  | PACKAGE NUMBER (CODE) | CONTRACT PACKAGE | QTY | ESTIMATED COST (USD) |  | PROCUREMENT METHOD | TECHNICAL SPECS/BOQ/DRAWINGS | PREP. OF BID DOCUMENT | PC APPROVAL - BID DOC/TECH SPECS | BID INVITATION & RELEASE OF BID DOC | BID SUBMISSION/PUBLIC OPENING | SUBMISSION OF BID EVALUATION REPORT | PC APPROVAL - BID EVALUATION REPORT | CONTRACT AWARD & SIGNING |  | ADVANCE PAYMENT (MOBILIZATION) |  | DELIVERY, INSPECTION (SUBSTANTIAL COMPLETION) | ACCEPTANCE & FINAL PAYMENT |  | REMARKS |
| PLANNED | 7 | IFB NO.MCSS/NCB/002/14/15 | Stationery | Assorted | 36,704 |  | NCB | 8/27/14 | 9/24/14 | 10/14/14 | 10/22/14 | 12/11/14 | 1/21/15 | 2/12/15 | 3/4/15 |  | NA |  | 3/24/15 | 4/23/15 |  |  |
| UPDATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PLANNED | 8 | IFB NO.MCSS/NCB/003/14/15 | Printing Binding & Publication | Assorted | 15,000 |  | NCB | 8/28/14 | 10/7/14 | 10/27/14 | 11/5/14 | 12/29/14 | 1/26/15 | 2/16/15 | 3/26/15 |  | NA |  | 5/6/15 | 6/29/15 |  |  |
| UPDATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PLANNED | 9 | IFB NO.MCSS/NCB/004/14/15 | Laboratory Consumable | Assorted | 36,705 |  | NCB | 8/27/14 | 9/18/14 | 10/17/14 | 10/27/14 | 11/6/14 | 11/28/14 | 12/18/14 | 2/3/15 |  | NA |  | 2/18/15 | 3/19/15 |  |  |
| UPDATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Monrovia Consolidated school system

PROCUREMENT PLAN (Core budget)

Source of Funding: GOL

Budget Period/Fiscal year: 2014/2015

| 1 | 2 | 3 |  | 4 | 5 | 6 | 7 |  | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 |  | 17 |  | 18 | 19 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | ITEM NO. | BASIC DATA |  |  |  |  |  |  | IMPLEMENTATION DATES |  |  |  |  |  |  |  |  |  |  |  |  | . |
|  |  | PACKAGE NUMBER (CODE) | CONTRACT PACKAGE |  | QTY | ESTIMATED COST (USD) |  | PROCUREMENT METHOD | TECHNICAL SPECS/BOQ/DRAWINGS | PREP. OF BID DOCUMENT | PC APPROVAL - BID DOC/TECH SPECS | BID INVITATION & RELEASE OF BID DOC | BID SUBMISSION/PUBLIC OPENING | SUBMISSION OF BID EVALUATION REPORT | PC APPROVAL - BID EVALUATION REPORT | CONTRACT AWARD & SIGNING |  | ADVANCE PAYMENT (MOBILIZATION) |  | DELIVERY, INSPECTION (SUBSTANTIAL COMPLETION) | ACCEPTANCE & FINAL PAYMENT | REMARKS |
| PLANNED | 10 | IFB NO.MCSS/RFQ/005/14/15 | Educational Materials & Supplies |  | Assorted | 1,125 |  | RFQ | 8/27/14 | 9/17/14 | 9/30/14 | 10/13/14 | 10/31/14 | 11/21/14 | 12/12/15 | 1/15/15 |  | NA |  | 2/23/15 | 5/3/15 |  |
| UPDATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PLANNED | 11 | IFB NO.MCSS/RFQ/006/14/15 | Workshops/ Seminars (Flip charts, markers, pens, pencils, catering) |  | 1 | 1,500 |  | RFQ | 8/20/14 | 9/9/14 | 9/18/14 | 10/11/14 | 11/3/14 | 12/30/14 | 1/12/15 | 2/26/15 |  | NA |  | 5/18/15 | 6/22/15 |  |
| UPDATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| GRAND TOTAL |  |  |  |  |  | 140, 534 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Prepared by: ______________________________________                                    Approved by: __________________________________________              Date: ____________________________

PROCUREMENT DIRECTOR/ MANAGER                                                                  HEAD OF ENTITY/CHAIRMAN PROC. COMMITTEE

Note to the procurement plan

Item 1. Purchase of Lonestar and Cellcom scratch cards for the senior staff/Directors =,     Item 2. Fuel and gas used to run vehicles and generato

Item 3. Repair of MCSS schools and the central office (repair of roof, replacement of damaged doors and windows, painting of walls etc).

Item 4. Repair and maintenance six (6) vehicles RL-2554, RL-2560, RL-2561 RL-2550, RL-2578, RL-2231.

Item 5. Repair and maintenance of computers, type writers, machines and furniture at the central office and schools.

Item 6. Purchase of cleaning materials (soap, dettol, towel, wheelbarrows, shovels, tissues, etc. for the central office and schools.

Item 7. Stationery (assorted materials for office and schools (papers, pens, postersheets, ink etc

Item 8. preparations of report cards, receipts book, lessonplans teachers roll books etc

Item 9.Scientific apparatus and other laboratory materials for all MCSS high schools (W.V.S.Tubman, D. Tweh and G.W. Gibson)

Item 10. Purchasing chalks, maps poster sheets etc for MCSS schools

Item 11. Purchasing of flip charts, markers, pens, pencils etc to host workshop for teachers and others.

Item 12. Electricity used by the MCSS administrative building at the cost of $ 2,086 USD Single sourced from Liberia Electricity corp. (LEC)

Item 13.Water supply used by the MCSS administrative building at the cost of $1,500 USD supplied by Liberia water and sewage corp. (LWSC)

Item 14. Other rental and lease, system leasing two (2) structures William Brumskine Elem. Sch. and Gaye Town Elem. Sch