NATIONAL COMMISSION ON DISABILITIES (NCD)

CORE BUDGET-PROCUREMENT PLAN

SOURCE OF FUNDING: GOL

Fiscal year: --2014/2015

| 1 | 2 | 3 | 4 |  |  | 5 | 6 |  | 7 |  | 8 | 9 |  | 10 |  | 11 | 12 | 13 |  | 14 |  | 15 | 16 |  | 17 | 18 |  | 19 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | ITEM NO. | BASIC DATA |  |  |  |  |  |  |  |  | IMPLEMENTATION DATES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | . |
|  |  | PACKAGE NUMBER (CODE) |  | CONTRACT PACKAGE | QTY |  |  | ESTIMATED COST (USD) |  | PROCUREMENT METHOD | TECHNICAL SPECS/BOQ/DRAWINGS | PREP. OF BID DOCUMENT | PC APPROVAL - BID DOC/TECH SPECS |  | BID INVITATION & RELEASE OF BID DOC |  | BID SUBMISSION/PUBLIC OPENING | SUBMISSION OF BID EVALUATION REPORT | PC APPROVAL - BID EVALUATION REPORT |  | CONTRACT AWARD & SIGNING |  |  | ADVANCE PAYMENT (MOBILIZATION) | DELIVERY, INSPECTION (SUBSTANTIAL COMPLETION) |  | ACCEPTANCE & FINAL PAYMENT | REMARKS |
| PLANNED | 1 | IFB N0:NCD/RB/ 001/14/15 |  | PETROLEUM PRODUCTS | 3641.618 Gal. |  |  | 12,600.00 |  | RB | 11/10/14 | 11/24/14 | 12/08/14 |  | 12/15/2014 |  | 1/15/2015 | 01/22/2015 | 01/29/2015 |  | 02/12/2015 |  |  | N/A | 6/1/2015 |  | 6/30/2015 |  |
| PLANNED | 2 | IFB N0:NCD/RFQ/ 001/14/15 |  | Guard & Security Services | 3 Guards |  |  | 1,900.00 |  | RFQ | 11/14/14 | 12/1/2014 | 12/8/2014 |  | 12/15/14 |  | 12/22/14 | 12/29/14 | 01/05/15 |  | 01/28/15 |  |  | N/A | 6/1/2015 |  | 6/30/2015 |  |
| GRAND TOTAL |  |  |  |  |  |  |  | 14,500.00 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Prepared by: __________________________              				Approved by: _________________________                                  DATE__________________

Moses G. Tarnue                                                                                                                                 Ricardia B. Dennis (Mrs.)

Procurement Officer     					             			                 Executive Director/PC Head

Note:

- NCD has an existing contract for office building with Mr. Thomas E. Mayor (LESSOR), Government has appropriated UD$ 25,000.00 (Twenty Five Thousands United States Dollars) for the office Building lease for the period of three (3) years commencing from July 1, 2013 through June 30, 2016.

- The total amount in the Draft Budget Fiscal Year 2014/2015 for the purchase of Petroleum for Fuel, Lubricants and Gasoline was in the tune of US$21,290.00, but due to late passage of the National Budget the Commission wrote the PPCC for use of Sole Source, thereby using the amount of US$8,690. The balance in appropriation for the purchase of  Fuel, Lubricants and Gasoline is in the tune of US$12,600.00 for the balance six months(January –June 30, 2015)

- The contract package, Petroleum Products is in one fort:

| Fuel for Vehicles | 3641.618@3.46 | US$12,600.00 |
| --- | --- | --- |