## Page 1of 5
MINISTRY OF PUBLIC WORKS
PROCUREMENT PLAN
( July 1, 2011 - June 30, 2012)
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
[8 empty] | Prepare | Entity | Adv. | Bid Sub | Bid | Entity | Contract | Advance |  | Accept
[5 empty] | Est. | Pro. | Tec. | Bidding | P. C. | Release | Public | Eva | P.C. | Award | Paym’t | Delivery | Final
| Item | Code | Cont’ Package | Qty | Cost | Method | Specs. | Document | Approved I | Doc | Opening | Reports | Approved II | Signed | L/C | Date | Paymnt | Remarks
Planed | 1 | IFB No. MPW/NCB/001/11/12 | Stationery | Assorted | 91577 | NCB | 2011-07-04 | 2011-07-11 | 2011-07-13 | 2011-07-18 | 2011-08-18 | 2011-08-25 | 2011-08-29 | 2011-09-05 | N/A | 2011-12-05 | 2012-01-05
Update
Act.
Planed | 2 | IFB No. MPW/SS/001/11/12 | Residential Property Rental & Lease * | 11 | 7000 | SS | N/A | N/A | 2011-09-09 | N/A | N/A | N/A | N/A | 2011-10-10 | N/A | N/A | 2012-04-10
Update
Act.
Planed | 3 | IFB No. MPW/SS/002/11/12 | Water & Sewerage | N/A | 11256 | SS | N/A | N/A | 2011-07-01 | N/A | N/A | N/A | N/A | 2011-08-01 | N/A | 2011-08-08 | 2012-06-08
Update
Act.
Planed | 4 | IFB No. MPW/SS/003/11/12 | Telecommunications, Internet, Postage & Courier | Assorted | 25695 | SS | N/A | N/A | 2011-08-10 | N/A | N/A | N/A | N/A | 2011-09-12 | N/A | 2011-10-12 | 2012-01-12
Update
Act.
Planed | 5 | IFB No. MPW/FA/001/11/12 | Repairs & Maint-Mach, Equipment & Furniture * | Assorted | 132624 | FA | N/A | N/A | 2011-07-15 | N/A | N/A | N/A | N/A | N/A | N/A | 2012-06-15 | N/A
Update
Act.
*See Attached
Page 1 of 5

## Page 2 of 5
MINISTRY OF PUBLIC WORKS
PROCUREMENT PLAN
( July 1, 2011 - June 30, 2012)
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
[8 empty] | Prepare | Entity | Adv. | Bid Sub | Bid | Entity | Contract | Advance |  | Accept
[5 empty] | Est. | Pro. | Tec. | Bidding | P.C. | Release | Public | Eva | P.C. | Award | Paym’t | Delivery | Final
| Item | Code | Cont’ Package | Qty | Cost | Method | Specs. | Document | Approved I | Doc | Opening | Reports | Approved II | Signed | L/C | Date | Paymnt | Remarks
Planed | 6 | IFB No. MPW/NCB/002/11/12 | Vehicles Insurance * | 112 | 100000 | NCB | 2011-08-08 | 2011-11-25 | 2011-11-28 | 2011-12-02 | 2012-01-04 | 2012-01-11 | 2012-01-18 | 2012-02-08 | 2012-03-01 | 2012-03-28 | 2012-05-31
Update
Act.
Planed | 7 | IFB No. MPW/NCB/003/11/12 | Transport Equipment * | 15 | 474363 | NCB | 2011-07-05 | 2011-07-12 | 2011-07-15 | 2011-07-18 | 2011-08-18 | 2011-08-25 | 2011-08-31 | 2011-09-20 | N/A | 2011-11-21 | 2011-12-05
Update
Act.
Planed | 8 | IFB No. MPW/NCB/004/11/12 | Carriage Haulag Freight & Transport Hire | Assorted | 55000 | NCB | 2011-08-01 | 2011-08-03 | 2011-08-10 | 2011-08-12 | 2011-09-12 | 2011-09-19 | 2011-09-26 | 2011-10-03 | N/A | 2011-10-17 | 2011-11-01
Update
Act.
Planed | 9 | IFB No. MPW/RFQ/001/11/12 | Uniform & Specialized Clothing * | Assorted | 9505 | RFQ | 2011-07-07 | 15/7/11 | 2011-07-20 | 2011-07-22 | 2011-07-22 | 2011-07-25 | 2011-07-28 | 2011-08-01 | N/A | 2011-08-08 | 2011-08-15
Update
Act.
Planed | 10 | IFB No. MPW/NCB/005/11/12 | Furniture & Fixtures * | Assorted | 65593 | NCB | 2011-07-15 | 2011-07-22 | 2011-07-27 | 2011-08-01 | 2011-09-01 | 2011-09-08 | 2011-09-12 | 2011-09-19 | N/A | 2011-11-21 | 2012-01-23
Update
Act.
Page 2 of 5

## Page 3 of 5
MINISTRY OF PUBLIC WORKS
PROCUREMENT PLAN
( July 1, 2011 - June 30, 2012)
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
[8 empty] | Prepare | Entity | Adv. | Bid Sub | Bid | Entity | Contract | Advance |  | Accept
[5 empty] | Est. | Pro. | Tec. | Bidding | P.C. | Release | Public | Eva | P.C. | Award | Paym’t | Delivery | Final
| Item | Code | Cont’ Package | Qty | Cost | Method | Specs. | Document | Approved I | Doc | Opening | Reports | Approved II | Signed | L/C | Date | Paymnt | Remarks
Planed | 11 | IFB No. MPW/NCB/006/11/12 | ICT Infrastructure Hardware Networks & Facilities * | Assorted | 84467 | NCB | 2011-07-04 | 2011-07-06 | 2011-07-13 | 2011-07-15 | 2011-08-15 | 2011-08-22 | 2011-08-24 | 2011-08-31 | N/A | 2011-09-14 | 2011-09-28
Update
Act.
Planed | 12 | IFB No. MPW/ICB/001/11/12 | Machinery & Other Equipment * | 5 | 1104206 | ICB | 2011-07-22 | 2011-08-05 | 2011-08-09 | 2011-08-11 | 2011-09-26 | 2011-10-03 | 2011-10-05 | 2011-10-25 | N/A | 2012-01-25 | 2012-02-08
Update
Act.
Planed | 13 | IFB No. MPW/ICB/002/11/12 | Reconstruction & Improvement Works * | Assorted | 28018015 | ICB | 2011-07-22 | 2011-08-12 | 2011-08-19 | 2011-08-22 | 2011-10-05 | 2011-10-12 | 2011-10-19 | 2011-11-09 | N/A | 2012-05-09 | 2012-06-11
Update
Act.
Planed | 14 | IFB No. MPW/NCB/007/11/12 | Non-Residential Building * | 40 | 107307 | NCB | 2011-07-14 | 2011-07-21 | 2011-07-28 | 2011-08-01 | 2011-08-31 | 2011-09-07 | 2011-09-09 | 2011-09-16 | N/A | 2011-10-17 | 2011-10-31
Update
Act.
Planed | 15 | IFB No. MPW/NCB/008/11/12 | Tool/Small Equipment & House-Hold Materials * | Assorted | 60000 | NCB | 2011-08-01 | 2011-08-03 | 2011-08-10 | 2011-08-12 | 2011-09-12 | 2011-09-19 | 2011-09-22 | 2011-09-29 | N/A | 2011-11-01 | 2011-12-01
Update
Act.
* See Attached
Page 3 of 5

## Page 4 of 5
MINISTRY OF PUBLIC WORKS
PROCUREMENT PLAN
( July 1, 2011 - June 30, 2012)
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
[8 empty] | Prepare | Entity | Adv. | Bid Sub | Bid | Entity | Contract | Advance |  | Accept
[5 empty] | Est. | Pro. | Tec. | Bidding | P.C. | Release | Public | Eva | P.C. | Award | Paym’t | Delivery | Final
| Item | Code | Cont’ Package | Qty | Cost | Method | Specs. | Document | Approved I | Doc | Opening | Reports | Approved II | Signed | L/C | Date | Paymnt | Remarks
Planed | 16 | IFB No. MPW/NCB/009/11/12 | Prinitng, Binding & Publications Services | Assorted | 79273 | NCB | N/A | 2011-08-15 | 2011-08-17 | 2011-08-19 | 2011-09-19 | 2011-09-26 | 2011-09-28 | 2011-10-05 | N/A | 2011-11-07 | 2011-12-07
Update
Act.
Planed | 17 | IFB No. MPW/NCB/0010/11/12 | Petroleum Products | 208899.56 | 971383 | NCB | N/A | 2011-07-21 | 2011-07-28 | 2011-08-02 | 2011-09-02 | 2011-09-09 | 2011-09-13 | 2011-09-20 | N/A | 2011-10-20 | 2011-11-03
Update
Act.
Planed | 18 | IFB No. MPW/NCB/0011/11/12 | Repair & Maintenance Vehicles | 112 | 302734 | NCB | N/A | 2011-08-08 | 2011-08-11 | 2011-08-15 | 2011-09-15 | 2011-09-22 | 2011-09-26 | 2011-10-14 | N/A | 2011-11-14 | 2011-11-28
Update
Act.
Planed | 19 | IFB No. MPW/NCB/0012/11/12 | Repairs & Maintenance Civil * | 51 | 262693 | NCB | N/A | 2011-09-05 | 2011-09-07 | 2011-09-09 | 2011-10-10 | 2011-10-17 | 2011-10-19 | 2011-11-07 | N/A | 2011-12-07 | 2011-12-21
Update
Act.
Planed | 20 | IFB No. MPW/SS/004/11/12 | Electricity | N/A | 20000 | SS | N/A | N/A | 2011-10-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2011-11-03
Update
Act.
* See Attached

## Page 5 of 5
MINISTRY OF PUBLIC WORKS
PROCUREMENT PLAN
( July 1, 2011 - June 30, 2012)
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
[8 empty] | Prepare | Entity | Adv. | Bid Sub | Bid | Entity | Contract | Advance |  | Accept
[5 empty] | Est. | Pro. | Tec. | Bidding | P.C. | Release | Public | Eva | P.C. | Award | Paym’t | Delivery | Final
| Item | Code | Cont’ Package | Qty | Cost | Method | Specs. | Document | Approved I | Doc | Opening | Reports | Approved II | Signed | L/C | Date | Paymnt | Remarks
Planed | 21 | IFB No. MPW/NCB/013/11/12 | Newspapers, Books and Specialized Publications | Assorted | 15000 | NCB | N/A | 2011-09-15 | 2011-09-19 | 2011-09-26 | 2011-10-26 | 2011-11-02 | 2011-11-04 | 2011-11-11 | N/A | 2011-12-12 | 2011-12-19
Update
Act.
Planed | 22 | IFB No. MPW/NCB/014/11/12 | Domestic Means of Travel * | Assorted | 50963 | NCB | N/A | N/A | 2011-09-01 | 2011-09-05 | 2011-09-12 | 2011-09-15 | 2011-09-19 | 2011-09-21 | N/A | 2011-09-23 | 2011-09-30
Update
Act.
Planed | 23 | IFB No. MPW/NCB/015/11/12 | Foreign Means of Travel * | Assorted | 25000 | NCB | N/A | N/A | 2011-10-03 | 2011-10-05 | 2011-10-12 | 2011-10-14 | 2011-10-17 | 2011-10-19 | N/A | 2011-10-26 | 2011-11-02
Update
Act.
Planed | 24 | IFB No. MPW/NCB/016/11/12 | Workshop, Conference, Symposia and Seminar * | Assorted | 18000 | NCB | N/A | N/A | 2011-12-01 | 2011-12-05 | 2011-12-12 | 2011-12-15 | 2011-12-19 | 2011-12-22 | N/A | 2011-12-27 | 2012-01-02
Update
Act.
Planed | 25 | IFB No. MPW/NCB/017/11/12 | Other Utilities * | 23 | 6400 | NCB | 2011-08-05 | 2011-08-19 | 2011-08-22 | 2011-08-25 | 2011-09-26 | 2011-10-03 | 2011-10-06 | 2011-10-13 | N/A | 2012-01-13 | 2012-03-13
Update
Act.
Planed | 26 | IFB No. MPW/NCB/018/11/12 | Other Office Materials & Consumables * | Assorted | 19243 | NCB | 2011-08-08 | 2011-08-15 | 2011-08-18 | 2011-08-22 | 2011-09-22 | 2011-09-29 | 2011-10-03 | 2011-10-10 | N/A | 2012-01-10 | 2012-02-10
Update
Act.
* See Attached
Page 5 of 5
Signed: ___________________________ Date: ___________________ Approved: ___________________________________________ Date: ___________________
DIRECTOR OF PROCUREMENT ACTING CHAIRMAN/PROCUREMENT COMMITTEE