## Document 1
Ministry of Lands, Mines and Energy
Procurement Plan for
July 1, 2011-June 30, 2012
Date May 5, 2011
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
|  | Items | Code | Contract Package | Qty | Est. Cost | Procu. Method | Tech. Specs | Prepare Bidding Doc. | Entity/Pc App 1 | Advertise Release Doc. | Bid Sub/Pub. Opening | Bid Eva Reports | Entity/Pc App 11 | Contract award signature | Advance Payment LC | Delivery | Final Payment | Remarks
| Planned | 1 | IFB N0: MLME/NCB 001/11/12 | Petroleum product * | 84301gals | 392000 | NCB | 2011-01-06 | 2011-08-06 | 2011-01-07 | 2011-04-07 | 2011-04-08 | 2011-11-08 | 18/08/2011 | 25/08/2011 | N/A | 2012-08-06 | 22/6/2012
Update
Actual
| Planned | 2 | IFB N0:MLME/NCB/002/11/12 | Repair & Maint.- Vehicles ** | 39 Vehicles | 154329 | NCB | 2011-06-06 | 13/06/2011 | 2011-04-07 | 2011-05-07 | 2011-05-08 | 2011-12-08 | 19/08/2011 | 26/08/2011 | N/A | 2012-02-06 | 16/6/2011
Update
Actual
| Planned | 3 | IFB N0: MLME/NCB/003/11/12 | Stationery | Assorted | 66230 | NCB | 2011-02-06 | 2011-09-06 | 2011-07-07 | 2011-08-07 | 2011-08-08 | 15/08/2011 | 22/08/2011 | 29/08/2011 | N/A | 2012-07-06 | 15/6/2012
Update
Actual
| Planned | 4 | IFB N0: MLME/NCB/004/11/12 | Printing, Binding & Publication Services | Assorted | 24508 | NCB | 2011-07-06 | 13/6/2011 | 2011-04-07 | 2011-05-07 | 2011-05-08 | 2011-12-08 | 19/08/2011 | 26/08/2011 | N/A | 2012-02-06 | 16/6/2012
Update
Actual
Should be base on allotment from the budget for item in question
| Signature ________________________________ | 6: Date _________________________; 10: * 41290gals fuel and lubricants for vehicles
|  |  | Saturday B. Henries | [7 empty] | 43010.75gals fuel for generator
Acting Procurement Director
| Approved __________________________________ | 6: Date __________________________
|  |  | Walter S. McCarthy | [7 empty] | **20,000 Repairs & Maintenance of Generator
|  | Deputy Minister for Administration | [8 empty] | 134,329 Repairs & Maintenance of Vehicles

## Document 2
Ministry of Lands, Mines & Energy
Procurement Plan for
July 1, 2011- June 30 2012
Date May 5, 2011
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
| Items | Code | Contract Package | Qty | Est. Cost | Procu. Method | Tech. Specs | Prepare Bidding Doc. | Entity/Pc App 1 | Advertise Release Doc. | Bid Sub/Pub. Opening | Bid Eva Reports | Entity/Pc App 11 | Contract award signature | Advance Payment LC | Delivery | Final Payment | Remarks
Planned | 5 | IFB NO: MLME/NCB 005/11/12 | Non- residential * | 2blds | 65165 | NCB | 2011-02-06 | 2011-09-06 | 15/7/2011 | 16/7/2011 | 16/8/2011 | 23/8/2011 | 30/8/2011 | 2011-06-09 | N/A | 2012-03-05 | 17/5/2012
Update
Actual
Planned | 6 | IFB NO: MLME/SS 001/11/12 | Acquisition of Land and Building Site * * | Acreas | 81000 | SS | 2011-03-06 | 2011-10-06 | 2011-01-08 | 2011-02-08 | 2011-02-09 | 2011-09-09 | 16/9/2011 | 23/9/2011 | N/A | 2012-01-06 | 15/6/2012
Update
Actual
Planned | 7 | IFB NO: MLME/NCB /006/11/12 | Other Office Materials & Consumable | Assorted | 20461 | NCB | 2011-03-06 | 2011-10-06 | 27/7/2011 | 28/7/2011 | 27/8/2011 | 2011-02-09 | 2011-09-09 | 16/9/2011 | N/A | 2012-07-06 | 21/6/2012
Update
Actual
Planned | 8 | IFB NO: MLME/SS 002/11/12 | Office Building Rental & Lease *** |  | 47900 | S/S | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-04-05
Update
Actual
* For construction
** Purchase of Land
*** For Lands, Survey and Cartography Building in Sinkor, Fiamah for USD 18,000.00
Geological and Hydrological Building in Sinkor, Old Road Joe Bar for USD29,900

## Document 3
Ministry of Lands, Mines & Energy
Procurement Plan for
July 1, 2011- June 30, 2012
Date May 5, 2011
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
| Items | Code | Contract Package | Qty | Est. Cost | Procu. Method | Tech. Specs | Prepare Bidding Doc. | Entity/Pc App 1 | Advertise Release Doc. | Bid Sub/Pub. Opening | Bid Eva Reports | Entity/Pc App 11 | Contract award signature | Advance Payment LC | Delivery | Accaptance Final Payment | Remarks
Planned | 9 | IFB NO: MLME/NCB/007/11/12 | Domestic Means of Travel * |  | 64000 | NCB | 2011-07-07 | 21/7/11 | 2011-03-10 | 2011-04-10 | 2011-04-11 | 2011-11-11 | 18/11/2011 | 25/11/2011 | N/A | 2011-02-06 | 16/6/2011
Update
Actual
Planned | 10 | IFB NO MLME/NCB/008/11/12 | Foregin Travel Means of Travel ** |  | 103150 | NCB | 2011-08-08 | 20/8/11 | 2011-04-10 | 2011-06-10 | 2011-05-11 | 2011-12-11 | 19/11/2011 | 26/11/2011 | N/A | 2012-07-06 | 21/6/2011
Update
Actual
Planned | 11 | IFB NO:MLME/NCB/009/11/12 | Repair, Maint. Machinery, Plant & Furniture |  | 57904 | NCB | 21/6/2011 | 28/6/2011 | 2011-01-08 | 2011-02-08 | 2011-02-09 | 2011-09-09 | 16/9/2011 | 23/9/2011 | N/A | 2012-07-06 | 22/6/2012
Update
Actual
Planned | 12 | IFB NO: MLME/RFQ/001/11/12 | Repair, Maint.-ICT Equipment |  | 2000 | RFQ | 21/7/11 | 30/7/11 | 2011-05-09 | 2011-06-09 | 2011-06-10 | 13/10/2011 | 20/11/2011 | 27/10/2011 | N/A | 2012-01-06 | 15/6/2012
Update
Actual
* For Vehicles Rental
** For Airline ticketing

## document 4
Ministry of Lands, Mines & Energy
Procurement Plan for
July 1, 2011- June 30, 2012
Date May 5, 2011
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
| Items | Code | Contract Package | Qty | Est. Cost | Procu. Method | Tech. Specs | Prepare Bidding Doc. | Entity/Pc App 1 | Advertise Release Doc. | Bid Sub/Pub. Opening | Bid Eva Reports | Entity/Pc App 11 | Contract award signature | Advance Payment LC | Delivery | Accaptance Final Payment | Remarks
Planned | 13 | IFB NO: MLME/NCB /010/11/12 | Vehicles | 3 | 95000 | NCB | 2011-02-06 | 2011-09-06 | 2011-01-10 | 2011-06-10 | 2011-05-11 | 2011-12-11 | 19/11/2011 | 26/11/2011 | N/A | 26/1/2012 | 25/2/2012
Update
Actual
Planned | 14 | IFB NO: MLME/RFQ/002/11/12 | Motor bikes | 4 | 10000 | RFQ | 2011-03-06 | 2011-10-06 | 4/10/201 | 2011-07-10 | 2011-08-11 | 15/11/2011 | 22/11/2011 | 30/11/2011 | N/A | 13/12/2011 | 21/12/2011
Update
Actual
Planned | 15 | IFB NO: MLME/NCB/011/11/12 | Other Office Materials & Consumable | Assorted | 15411 | NCB | 2011-03-06 | 2011-10-06 | 2011-05-10 | 2011-08-10 | 2011-08-11 | 15/11/2011 | 23/11/2011 | 30/11/2011 | N/A | 2011-07-12 | 21/12/2011
Update
Actual
Planned | 16 | IFB NO: MLME/SS /002/11/12 | Office Building Rental & Lease |  | 68448 | SS | N/A | N/A | 2011-07-07 | N/A | N/A | N/A | N/A | N/A | N/A | 2012-06-06 | 30/7/2011
Update
Actual

## Document 5
Ministry of Lands, Mines & Energy
Procurement Plan for
July 1, 2011- June 30, 2012
Date May 5, 2011
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
| Items | Code | Contract Package | Qty | Est. Cost | Procu. Method | Tech. Specs | Prepare Bidding Doc. | Entity/Pc App 1 | Advertise Release Doc. | Bid Sub/Pub. Opening | Bid Eva Reports | Entity/Pc App 11 | Contract award signature | Advance Payment LC | Delivery | Final Payment | Remarks
Planned | 17 | IFB NO: MLME/NCB/012/11/12 | Tel. Fax & E-mail |  | 30700 | NCB | 2011-07-07 | 21/7/11 | 2011-08-09 | 7/10/201 | 2011-08-09 | 2011-10-10 | 17/10/2011 | 21/10/2011 | N/A | 2012-09-06 | 23/6/2012
Update
Actual
Planned | 18 | IFB NO: MLME/NCB/013/11/12 | Repair & Maint. -Civil * |  | 16496 | NCB | 17/6/2011 | 24/6/2011 | 2011-03-09 | 2011-05-09 | 2011-05-10 | 2011-11-10 | 17/10/2011 | 24/10/2011 | N/A | 2012-07-06 | 21/6/2012
Update
Actual
Planned | 18 | IFB NO: MLME/SS/003/11/12 | Water and Sewage |  | 5500 | S/S | N/A | N/A | 2011-07-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 15/6/2012
Update
Actual
Planned | 19 | IFB NO: MLME/SS/004/11/12 | Electricity |  | 7000 | S/S | N/A | N/A | 2011-07-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 17/6/2012
Update
Actual
* Renovation of Praperties